## Sheet1
x | y | z | major_activity | code | minor_activity
1 | 1 | 0 | M000 | M00009 | project_completion
1 | 1 | 0 | M000 | M00001 | project_start
1 | 1 | 0 | T100 | T10010 | fence-line_marking
1 | 1 | 0 | T100 | T10020 | fence-excavation
1 | 1 | 0 | T100 | T10030 | fence-compaction
1 | 1 | 0 | T100 | T10040 | fence-foundation
1 | 1 | 0 | T100 | T10050 | fence-backfilling
1 | 1 | 0 | T100 | T10060 | fence-steel
1 | 1 | 0 | T100 | T10070 | fence-panel
1 | 1 | 0 | T100 | T10080 | fence-wrapping
1 | 1 | 0 | T100 | T10090 | fence-inspection
1 | 1 | 0 | W100 | W10010 | CIP-line_marking
1 | 1 | 0 | W100 | W10020 | CIP-guidebeam
1 | 1 | 0 | W100 | W10030 | CIP-soil_compaction_for_machine
1 | 1 | 0 | W100 | W10040 | CIP-dig&rebar_1
1 | 1 | 0 | W100 | W10041 | CIP-casting_1
1 | 1 | 0 | W100 | W10050 | CIP-dig&rebar_2
1 | 1 | 0 | W100 | W10051 | CIP-casting_2
1 | 1 | 0 | W100 | W10060 | CIP-dig&rebar_3
1 | 1 | 0 | W100 | W10061 | CIP-casting_3
1 | 1 | 0 | W100 | W10070 | CIP-capbeam
1 | 1 | 0 | W100 | W10080 | CIP-capbeam_casting
1 | 1 | 0 | W110 | W11010 | waterblock-line_marking
1 | 1 | 0 | W110 | W11020 | waterblock-dig&piping
1 | 1 | 0 | W110 | W11030 | waterblock-injection
1 | 1 | 0 | W110 | W11040 | waterblock-cleaning
1 | 1 | 0 | R100 | R10010 | post_pile-line_marking
1 | 1 | 0 | R100 | R10020 | post_pile-dig&piling
1 | 2 | 0 | T100 | T10010 | fence-line_marking
1 | 2 | 0 | T100 | T10020 | fence-excavation
1 | 2 | 0 | T100 | T10030 | fence-compaction
1 | 2 | 0 | T100 | T10040 | fence-foundation
1 | 2 | 0 | T100 | T10050 | fence-backfilling
1 | 2 | 0 | T100 | T10060 | fence-steel
1 | 2 | 0 | T100 | T10070 | fence-panel
1 | 2 | 0 | T100 | T10080 | fence-wrapping
1 | 2 | 0 | T100 | T10090 | fence-inspection
1 | 2 | 0 | W100 | W10010 | CIP-line_marking
1 | 2 | 0 | W100 | W10020 | CIP-guidebeam
1 | 2 | 0 | W100 | W10030 | CIP-soil_compaction_for_machine
1 | 2 | 0 | W100 | W10040 | CIP-dig&rebar_1
1 | 2 | 0 | W100 | W10041 | CIP-casting_1
1 | 2 | 0 | W100 | W10050 | CIP-dig&rebar_2
1 | 2 | 0 | W100 | W10051 | CIP-casting_2
1 | 2 | 0 | W100 | W10060 | CIP-dig&rebar_3
1 | 2 | 0 | W100 | W10061 | CIP-casting_3
1 | 2 | 0 | W100 | W10070 | CIP-capbeam
1 | 2 | 0 | W100 | W10080 | CIP-capbeam_casting
1 | 2 | 0 | W110 | W11010 | waterblock-line_marking
1 | 2 | 0 | W110 | W11020 | waterblock-dig&piping
1 | 2 | 0 | W110 | W11030 | waterblock-injection
1 | 2 | 0 | W110 | W11040 | waterblock-cleaning
1 | 3 | 0 | T100 | T10010 | fence-line_marking
1 | 3 | 0 | T100 | T10020 | fence-excavation
1 | 3 | 0 | T100 | T10030 | fence-compaction
1 | 3 | 0 | T100 | T10040 | fence-foundation
1 | 3 | 0 | T100 | T10050 | fence-backfilling
1 | 3 | 0 | T100 | T10060 | fence-steel
1 | 3 | 0 | T100 | T10070 | fence-panel
1 | 3 | 0 | T100 | T10080 | fence-wrapping
1 | 3 | 0 | T100 | T10090 | fence-inspection
1 | 3 | 0 | W100 | W10010 | CIP-line_marking
1 | 3 | 0 | W100 | W10020 | CIP-guidebeam
1 | 3 | 0 | W100 | W10030 | CIP-soil_compaction_for_machine
1 | 3 | 0 | W100 | W10040 | CIP-dig&rebar_1
1 | 3 | 0 | W100 | W10041 | CIP-casting_1
1 | 3 | 0 | W100 | W10050 | CIP-dig&rebar_2
1 | 3 | 0 | W100 | W10051 | CIP-casting_2
1 | 3 | 0 | W100 | W10060 | CIP-dig&rebar_3
1 | 3 | 0 | W100 | W10061 | CIP-casting_3
1 | 3 | 0 | W100 | W10070 | CIP-capbeam
1 | 3 | 0 | W100 | W10080 | CIP-capbeam_casting
1 | 3 | 0 | W110 | W11010 | waterblock-line_marking
1 | 3 | 0 | W110 | W11020 | waterblock-dig&piping
1 | 3 | 0 | W110 | W11030 | waterblock-injection
1 | 3 | 0 | W110 | W11040 | waterblock-cleaning
1 | 3 | 0 | R100 | R10010 | post_pile-line_marking
1 | 3 | 0 | R100 | R10020 | post_pile-dig&piling
2 | 1 | 0 | T100 | T10010 | fence-line_marking
2 | 1 | 0 | T100 | T10020 | fence-excavation
2 | 1 | 0 | T100 | T10030 | fence-compaction
2 | 1 | 0 | T100 | T10040 | fence-foundation
2 | 1 | 0 | T100 | T10050 | fence-backfilling
2 | 1 | 0 | T100 | T10060 | fence-steel
2 | 1 | 0 | T100 | T10070 | fence-panel
2 | 1 | 0 | T100 | T10080 | fence-wrapping
2 | 1 | 0 | T100 | T10090 | fence-inspection
2 | 1 | 0 | W100 | W10010 | CIP-line_marking
2 | 1 | 0 | W100 | W10020 | CIP-guidebeam
2 | 1 | 0 | W100 | W10030 | CIP-soil_compaction_for_machine
2 | 1 | 0 | W100 | W10040 | CIP-dig&rebar_1
2 | 1 | 0 | W100 | W10041 | CIP-casting_1
2 | 1 | 0 | W100 | W10050 | CIP-dig&rebar_2
2 | 1 | 0 | W100 | W10051 | CIP-casting_2
2 | 1 | 0 | W100 | W10060 | CIP-dig&rebar_3
2 | 1 | 0 | W100 | W10061 | CIP-casting_3
2 | 1 | 0 | W100 | W10070 | CIP-capbeam
2 | 1 | 0 | W100 | W10080 | CIP-capbeam_casting
2 | 1 | 0 | W110 | W11010 | waterblock-line_marking
2 | 1 | 0 | W110 | W11020 | waterblock-dig&piping
2 | 1 | 0 | W110 | W11030 | waterblock-injection
2 | 1 | 0 | W110 | W11040 | waterblock-cleaning
2 | 1 | 0 | R100 | R10010 | post_pile-line_marking
2 | 1 | 0 | R100 | R10020 | post_pile-dig&piling
2 | 3 | 0 | T100 | T10010 | fence-line_marking
2 | 3 | 0 | T100 | T10020 | fence-excavation
2 | 3 | 0 | T100 | T10030 | fence-compaction
2 | 3 | 0 | T100 | T10040 | fence-foundation
2 | 3 | 0 | T100 | T10050 | fence-backfilling
2 | 3 | 0 | T100 | T10060 | fence-steel
2 | 3 | 0 | T100 | T10070 | fence-panel
2 | 3 | 0 | T100 | T10080 | fence-wrapping
2 | 3 | 0 | T100 | T10090 | fence-inspection
3 | 1 | 0 | T100 | T10010 | fence-line_marking
3 | 1 | 0 | T100 | T10020 | fence-excavation
3 | 1 | 0 | T100 | T10030 | fence-compaction
3 | 1 | 0 | T100 | T10040 | fence-foundation
3 | 1 | 0 | T100 | T10050 | fence-backfilling
3 | 1 | 0 | T100 | T10060 | fence-steel
3 | 1 | 0 | T100 | T10070 | fence-panel
3 | 1 | 0 | T100 | T10080 | fence-wrapping
3 | 1 | 0 | T100 | T10090 | fence-inspection
3 | 1 | 0 | W100 | W10010 | CIP-line_marking
3 | 1 | 0 | W100 | W10020 | CIP-guidebeam
3 | 1 | 0 | W100 | W10030 | CIP-soil_compaction_for_machine
3 | 1 | 0 | W100 | W10040 | CIP-dig&rebar_1
3 | 1 | 0 | W100 | W10041 | CIP-casting_1
3 | 1 | 0 | W100 | W10050 | CIP-dig&rebar_2
3 | 1 | 0 | W100 | W10051 | CIP-casting_2
3 | 1 | 0 | W100 | W10060 | CIP-dig&rebar_3
3 | 1 | 0 | W100 | W10061 | CIP-casting_3
3 | 1 | 0 | W100 | W10070 | CIP-capbeam
3 | 1 | 0 | W100 | W10080 | CIP-capbeam_casting
3 | 1 | 0 | W110 | W11010 | waterblock-line_marking
3 | 1 | 0 | W110 | W11020 | waterblock-dig&piping
3 | 1 | 0 | W110 | W11030 | waterblock-injection
3 | 1 | 0 | W110 | W11040 | waterblock-cleaning
3 | 1 | 0 | R100 | R10010 | post_pile-line_marking
3 | 1 | 0 | R100 | R10020 | post_pile-dig&piling
3 | 3 | 0 | T100 | T10010 | fence-line_marking
3 | 3 | 0 | T100 | T10020 | fence-excavation
3 | 3 | 0 | T100 | T10030 | fence-compaction
3 | 3 | 0 | T100 | T10040 | fence-foundation
3 | 3 | 0 | T100 | T10050 | fence-backfilling
3 | 3 | 0 | T100 | T10060 | fence-steel
3 | 3 | 0 | T100 | T10070 | fence-panel
3 | 3 | 0 | T100 | T10080 | fence-wrapping
3 | 3 | 0 | T100 | T10090 | fence-inspection
3 | 2 | 0 | T100 | T10010 | fence-line_marking
3 | 2 | 0 | T100 | T10020 | fence-excavation
3 | 2 | 0 | T100 | T10030 | fence-compaction
3 | 2 | 0 | T100 | T10040 | fence-foundation
3 | 2 | 0 | T100 | T10050 | fence-backfilling
3 | 2 | 0 | T100 | T10060 | fence-steel
3 | 2 | 0 | T100 | T10070 | fence-panel
3 | 2 | 0 | T100 | T10080 | fence-wrapping
3 | 2 | 0 | T100 | T10090 | fence-inspection
3 | 2 | 0 | W100 | W10010 | CIP-line_marking
3 | 2 | 0 | W100 | W10020 | CIP-guidebeam
3 | 2 | 0 | W100 | W10030 | CIP-soil_compaction_for_machine
3 | 2 | 0 | W100 | W10040 | CIP-dig&rebar_1
3 | 2 | 0 | W100 | W10041 | CIP-casting_1
3 | 2 | 0 | W100 | W10050 | CIP-dig&rebar_2
3 | 2 | 0 | W100 | W10051 | CIP-casting_2
3 | 2 | 0 | W100 | W10060 | CIP-dig&rebar_3
3 | 2 | 0 | W100 | W10061 | CIP-casting_3
3 | 2 | 0 | W100 | W10070 | CIP-capbeam
3 | 2 | 0 | W100 | W10080 | CIP-capbeam_casting
3 | 2 | 0 | W110 | W11010 | waterblock-line_marking
3 | 2 | 0 | W110 | W11020 | waterblock-dig&piping
3 | 2 | 0 | W110 | W11030 | waterblock-injection
3 | 2 | 0 | W110 | W11040 | waterblock-cleaning
3 | 2 | 0 | R100 | R10010 | post_pile-line_marking
3 | 2 | 0 | R100 | R10020 | post_pile-dig&piling

## Sheet1 (2)
x | y | z | major_activity
1 | 1 | 0 | M000
1 | 1 | 0 | R100
1 | 3 | 0 | R100
2 | 1 | 0 | R100
3 | 1 | 0 | R100
3 | 2 | 0 | R100
1 | 1 | 0 | T100
1 | 2 | 0 | T100
1 | 3 | 0 | T100
2 | 1 | 0 | T100
2 | 3 | 0 | T100
3 | 1 | 0 | T100
3 | 3 | 0 | T100
3 | 2 | 0 | T100
1 | 1 | 0 | W100
1 | 2 | 0 | W100
1 | 3 | 0 | W100
2 | 1 | 0 | W100
3 | 1 | 0 | W100
3 | 2 | 0 | W100
1 | 1 | 0 | W110
1 | 2 | 0 | W110
1 | 3 | 0 | W110
2 | 1 | 0 | W110
3 | 1 | 0 | W110
3 | 2 | 0 | W110

## Sheet2
project_completion | major_activity
project_start | M000
fence-line_marking | T100
fence-excavation | W100
fence-compaction | W110
fence-foundation | R100
fence-backfilling | R110
fence-steel | R120
fence-panel | T350
fence-wrapping | T370
fence-inspection
CIP-line_marking
CIP-guidebeam
CIP-soil_compaction_for_machine
CIP-dig&rebar_1
CIP-casting_1
CIP-dig&rebar_2
CIP-casting_2
CIP-dig&rebar_3
CIP-casting_3
CIP-capbeam
CIP-capbeam_casting
waterblock-line_marking
waterblock-dig&piping
waterblock-injection
waterblock-cleaning
post_pile-dig&piling
strut_installation-wale
strut_installation-strut
strut_installation-inspection
strut_dismatling-check
strut_dismatling-remove
lift_installation-form
lift_installation-rebar
lift_installation-casting
lift_installation-curing1
lift_installation-curing2
lift_installation-curing3
lift_installation-curing4
lift_installation-curing5
lift_installation-curing6
lift_installation-installation
lift_installation-inspection
lift_dismantling-dismantling
post_pile-line_marking