## Sheet1
x | y | z | major_activity | code | minor_activity
4 | 4 | 0 | M000 | M00001 | Milestone-project_Start
4 | 4 | 0 | M000 | M00009 | Milestone-project_completion
2 | 2 | 0 | R100 | R10010 | post_pile-line_marking
2 | 2 | 0 | R100 | R10020 | post_pile-dig&piling
1 | 1 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
1 | 1 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
1 | 1 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
1 | 1 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
1 | 1 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
1 | 1 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
1 | 1 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
1 | 1 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
1 | 2 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
1 | 2 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
1 | 2 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
1 | 2 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
1 | 2 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
1 | 2 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
1 | 2 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
1 | 2 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
1 | 3 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
1 | 3 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
1 | 3 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
1 | 3 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
1 | 3 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
1 | 3 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
1 | 3 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
1 | 3 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
2 | 1 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
2 | 1 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
2 | 1 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
2 | 1 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
2 | 1 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
2 | 1 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
2 | 1 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
2 | 1 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
3 | 1 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
3 | 1 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
3 | 1 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
3 | 1 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
3 | 1 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
3 | 1 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
3 | 1 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
3 | 1 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
3 | 2 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
3 | 2 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
3 | 2 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
3 | 2 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
3 | 2 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
3 | 2 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
3 | 2 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
3 | 2 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting