## activity_list
category | major_activity | minor_activity | code | productivity | pre_dist
마일스톤 | Milestone | project_Start | M00001 | 1 | 0
마일스톤 | Milestone | project_completion | M00009 | 1 | 5
가설공사 | fence | fence-line_marking | T10010 | 10 | 5
가설공사 | fence | fence-excavation | T10020 | 3 | 1
가설공사 | fence | fence-compaction | T10030 | 3 | 1
가설공사 | fence | fence-foundation | T10040 | 3 | 0
가설공사 | fence | fence-backfilling | T10050 | 3 | 0
가설공사 | fence | fence-steel | T10060 | 3 | 0
가설공사 | fence | fence-panel | T10070 | 5 | 2
가설공사 | fence | fence-wrapping | T10080 | 10 | 5
가설공사 | fence | fence-inspection | T10090 | 10 | 5