## grid_activity_list
x | y | z | major_activity | code | minor_activity
0 | 0 | 0 | milestone | M00009 | project_completion
0 | 0 | 0 | milestone | M00001 | project_start
0 | 0 | 0 | milestone | M00007 | elevator
1 | 1 | 1 | fence | T10010 | fence_line_marking
1 | 1 | 1 | fence | T10020 | fence_excavation
1 | 1 | 1 | fence | T10030 | fence_compaction
1 | 1 | 1 | fence | T10040 | fence_foundation
1 | 1 | 1 | fence | T10050 | fence_backfilling
1 | 1 | 1 | fence | T10060 | fence_steel
1 | 1 | 1 | fence | T10070 | fence_panel
1 | 1 | 1 | fence | T10080 | fence_wrapping
1 | 1 | 1 | fence | T10090 | fence_inspection
1 | 2 | 1 | fence | T10010 | fence_line_marking
1 | 2 | 1 | fence | T10020 | fence_excavation
1 | 2 | 1 | fence | T10030 | fence_compaction
1 | 2 | 1 | fence | T10040 | fence_foundation
1 | 2 | 1 | fence | T10050 | fence_backfilling
1 | 2 | 1 | fence | T10060 | fence_steel
1 | 2 | 1 | fence | T10070 | fence_panel
1 | 2 | 1 | fence | T10080 | fence_wrapping
1 | 2 | 1 | fence | T10090 | fence_inspection
1 | 3 | 1 | fence | T10010 | fence_line_marking
1 | 3 | 1 | fence | T10020 | fence_excavation
1 | 3 | 1 | fence | T10030 | fence_compaction
1 | 3 | 1 | fence | T10040 | fence_foundation
1 | 3 | 1 | fence | T10050 | fence_backfilling
1 | 3 | 1 | fence | T10060 | fence_steel
1 | 3 | 1 | fence | T10070 | fence_panel
1 | 3 | 1 | fence | T10080 | fence_wrapping
1 | 3 | 1 | fence | T10090 | fence_inspection
3 | 1 | 1 | fence | T10010 | fence_line_marking
3 | 1 | 1 | fence | T10020 | fence_excavation
3 | 1 | 1 | fence | T10030 | fence_compaction
3 | 1 | 1 | fence | T10040 | fence_foundation
3 | 1 | 1 | fence | T10050 | fence_backfilling
3 | 1 | 1 | fence | T10060 | fence_steel
3 | 1 | 1 | fence | T10070 | fence_panel
3 | 1 | 1 | fence | T10080 | fence_wrapping
3 | 1 | 1 | fence | T10090 | fence_inspection
3 | 2 | 1 | fence | T10010 | fence_line_marking
3 | 2 | 1 | fence | T10020 | fence_excavation
3 | 2 | 1 | fence | T10030 | fence_compaction
3 | 2 | 1 | fence | T10040 | fence_foundation
3 | 2 | 1 | fence | T10050 | fence_backfilling
3 | 2 | 1 | fence | T10060 | fence_steel
3 | 2 | 1 | fence | T10070 | fence_panel
3 | 2 | 1 | fence | T10080 | fence_wrapping
3 | 2 | 1 | fence | T10090 | fence_inspection
3 | 3 | 1 | fence | T10010 | fence_line_marking
3 | 3 | 1 | fence | T10020 | fence_excavation
3 | 3 | 1 | fence | T10030 | fence_compaction
3 | 3 | 1 | fence | T10040 | fence_foundation
3 | 3 | 1 | fence | T10050 | fence_backfilling
3 | 3 | 1 | fence | T10060 | fence_steel
3 | 3 | 1 | fence | T10070 | fence_panel
3 | 3 | 1 | fence | T10080 | fence_wrapping
3 | 3 | 1 | fence | T10090 | fence_inspection
2 | 1 | 1 | fence | T10010 | fence_line_marking
2 | 1 | 1 | fence | T10020 | fence_excavation
2 | 1 | 1 | fence | T10030 | fence_compaction
2 | 1 | 1 | fence | T10040 | fence_foundation
2 | 1 | 1 | fence | T10050 | fence_backfilling
2 | 1 | 1 | fence | T10060 | fence_steel
2 | 1 | 1 | fence | T10070 | fence_panel
2 | 1 | 1 | fence | T10080 | fence_wrapping
2 | 1 | 1 | fence | T10090 | fence_inspection
2 | 3 | 1 | fence | T10010 | fence_line_marking
2 | 3 | 1 | fence | T10020 | fence_excavation
2 | 3 | 1 | fence | T10030 | fence_compaction
2 | 3 | 1 | fence | T10040 | fence_foundation
2 | 3 | 1 | fence | T10050 | fence_backfilling
2 | 3 | 1 | fence | T10060 | fence_steel
2 | 3 | 1 | fence | T10070 | fence_panel
2 | 3 | 1 | fence | T10080 | fence_wrapping
2 | 3 | 1 | fence | T10090 | fence_inspection
1 | 2 | 1 | t_crane_installation | T30010 | t_crane_installation_form
1 | 2 | 1 | t_crane_installation | T30020 | t_crane_installation_rebar
1 | 2 | 1 | t_crane_installation | T30030 | t_crane_installation_casting
1 | 2 | 1 | t_crane_installation | T30031 | t_crane_installation_curing1
1 | 2 | 1 | t_crane_installation | T30032 | t_crane_installation_curing2
1 | 2 | 1 | t_crane_installation | T30033 | t_crane_installation_curing3
1 | 2 | 1 | t_crane_installation | T30034 | t_crane_installation_curing4
1 | 2 | 1 | t_crane_installation | T30035 | t_crane_installation_curing5
1 | 2 | 1 | t_crane_installation | T30036 | t_crane_installation_curing6
1 | 2 | 1 | t_crane_installation | T30040 | t_crane_installation_installation
1 | 2 | 1 | t_crane_installation | T30050 | t_crane_installation_inspection
1 | 2 | 1 | t_crane_dismantling | T32010 | t_crane_dismantling_machine
1 | 2 | 1 | t_crane_dismantling | T32020 | t_crane_dismantling_dismantling
1 | 3 | 1 | lift_installation | T35010 | lift_installation_form
1 | 3 | 1 | lift_installation | T35020 | lift_installation_rebar
1 | 3 | 1 | lift_installation | T35030 | lift_installation_casting
1 | 3 | 1 | lift_installation | T35031 | lift_installation_curing1
1 | 3 | 1 | lift_installation | T35032 | lift_installation_curing2
1 | 3 | 1 | lift_installation | T35033 | lift_installation_curing3
1 | 3 | 1 | lift_installation | T35034 | lift_installation_curing4
1 | 3 | 1 | lift_installation | T35035 | lift_installation_curing5
1 | 3 | 1 | lift_installation | T35036 | lift_installation_curing6
1 | 3 | 1 | lift_installation | T35040 | lift_installation_installation
1 | 3 | 1 | lift_installation | T35050 | lift_installation_inspection
1 | 3 | 1 | lift_dismantling
1 | 1 | 1 | CIP | W10010 | CIP_line_marking
1 | 1 | 1 | CIP | W10020 | CIP_guidebeam
1 | 1 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
1 | 1 | 1 | CIP | W10040 | CIP_dig&rebar_1
1 | 1 | 1 | CIP | W10050 | CIP_casting_1
1 | 1 | 1 | CIP | W10050 | CIP_dig&rebar_2
1 | 1 | 1 | CIP | W10050 | CIP_casting_2
1 | 1 | 1 | CIP | W10050 | CIP_dig&rebar_3
1 | 1 | 1 | CIP | W10050 | CIP_casting_3
1 | 1 | 1 | CIP | W10060 | CIP_capbeam
1 | 1 | 1 | CIP | W10070 | CIP_capbeam_casting
1 | 1 | 1 | waterblock | W11010 | waterblock_line_marking
1 | 1 | 1 | waterblock | W11020 | waterblock_dig&piping
1 | 1 | 1 | waterblock | W11030 | waterblock_injection
1 | 1 | 1 | waterblock | W11040 | waterblock_cleaning
2 | 1 | 1 | CIP | W10010 | CIP_line_marking
2 | 1 | 1 | CIP | W10020 | CIP_guidebeam
2 | 1 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
2 | 1 | 1 | CIP | W10040 | CIP_dig&rebar_1
2 | 1 | 1 | CIP | W10050 | CIP_casting_1
2 | 1 | 1 | CIP | W10050 | CIP_dig&rebar_2
2 | 1 | 1 | CIP | W10050 | CIP_casting_2
2 | 1 | 1 | CIP | W10050 | CIP_dig&rebar_3
2 | 1 | 1 | CIP | W10050 | CIP_casting_3
2 | 1 | 1 | CIP | W10060 | CIP_capbeam
2 | 1 | 1 | CIP | W10070 | CIP_capbeam_casting
2 | 1 | 1 | waterblock | W11010 | waterblock_line_marking
2 | 1 | 1 | waterblock | W11020 | waterblock_dig&piping
2 | 1 | 1 | waterblock | W11030 | waterblock_injection
2 | 1 | 1 | waterblock | W11040 | waterblock_cleaning
3 | 1 | 1 | CIP | W10010 | CIP_line_marking
3 | 1 | 1 | CIP | W10020 | CIP_guidebeam
3 | 1 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
3 | 1 | 1 | CIP | W10040 | CIP_dig&rebar_1
3 | 1 | 1 | CIP | W10050 | CIP_casting_1
3 | 1 | 1 | CIP | W10050 | CIP_dig&rebar_2
3 | 1 | 1 | CIP | W10050 | CIP_casting_2
3 | 1 | 1 | CIP | W10050 | CIP_dig&rebar_3
3 | 1 | 1 | CIP | W10050 | CIP_casting_3
3 | 1 | 1 | CIP | W10060 | CIP_capbeam
3 | 1 | 1 | CIP | W10070 | CIP_capbeam_casting
3 | 1 | 1 | waterblock | W11010 | waterblock_line_marking
3 | 1 | 1 | waterblock | W11020 | waterblock_dig&piping
3 | 1 | 1 | waterblock | W11030 | waterblock_injection
3 | 1 | 1 | waterblock | W11040 | waterblock_cleaning
1 | 3 | 1 | CIP | W10010 | CIP_line_marking
1 | 3 | 1 | CIP | W10020 | CIP_guidebeam
1 | 3 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
1 | 3 | 1 | CIP | W10040 | CIP_dig&rebar_1
1 | 3 | 1 | CIP | W10050 | CIP_casting_1
1 | 3 | 1 | CIP | W10050 | CIP_dig&rebar_2
1 | 3 | 1 | CIP | W10050 | CIP_casting_2
1 | 3 | 1 | CIP | W10050 | CIP_dig&rebar_3
1 | 3 | 1 | CIP | W10050 | CIP_casting_3
1 | 3 | 1 | CIP | W10060 | CIP_capbeam
1 | 3 | 1 | CIP | W10070 | CIP_capbeam_casting
1 | 3 | 1 | waterblock | W11010 | waterblock_line_marking
1 | 3 | 1 | waterblock | W11020 | waterblock_dig&piping
1 | 3 | 1 | waterblock | W11030 | waterblock_injection
1 | 3 | 1 | waterblock | W11040 | waterblock_cleaning
2 | 3 | 1 | CIP | W10010 | CIP_line_marking
2 | 3 | 1 | CIP | W10020 | CIP_guidebeam
2 | 3 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
2 | 3 | 1 | CIP | W10040 | CIP_dig&rebar_1
2 | 3 | 1 | CIP | W10050 | CIP_casting_1
2 | 3 | 1 | CIP | W10050 | CIP_dig&rebar_2
2 | 3 | 1 | CIP | W10050 | CIP_casting_2
2 | 3 | 1 | CIP | W10050 | CIP_dig&rebar_3
2 | 3 | 1 | CIP | W10050 | CIP_casting_3
2 | 3 | 1 | CIP | W10060 | CIP_capbeam
2 | 3 | 1 | CIP | W10070 | CIP_capbeam_casting
2 | 3 | 1 | waterblock | W11010 | waterblock_line_marking
2 | 3 | 1 | waterblock | W11020 | waterblock_dig&piping
2 | 3 | 1 | waterblock | W11030 | waterblock_injection
2 | 3 | 1 | waterblock | W11040 | waterblock_cleaning
3 | 3 | 1 | CIP | W10010 | CIP_line_marking
3 | 3 | 1 | CIP | W10020 | CIP_guidebeam
3 | 3 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
3 | 3 | 1 | CIP | W10040 | CIP_dig&rebar_1
3 | 3 | 1 | CIP | W10050 | CIP_casting_1
3 | 3 | 1 | CIP | W10050 | CIP_dig&rebar_2
3 | 3 | 1 | CIP | W10050 | CIP_casting_2
3 | 3 | 1 | CIP | W10050 | CIP_dig&rebar_3
3 | 3 | 1 | CIP | W10050 | CIP_casting_3
3 | 3 | 1 | CIP | W10060 | CIP_capbeam
3 | 3 | 1 | CIP | W10070 | CIP_capbeam_casting
3 | 3 | 1 | waterblock | W11010 | waterblock_line_marking
3 | 3 | 1 | waterblock | W11020 | waterblock_dig&piping
3 | 3 | 1 | waterblock | W11030 | waterblock_injection
3 | 3 | 1 | waterblock | W11040 | waterblock_cleaning
1 | 2 | 1 | CIP | W10010 | CIP_line_marking
1 | 2 | 1 | CIP | W10020 | CIP_guidebeam
1 | 2 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
1 | 2 | 1 | CIP | W10040 | CIP_dig&rebar_1
1 | 2 | 1 | CIP | W10050 | CIP_casting_1
1 | 2 | 1 | CIP | W10050 | CIP_dig&rebar_2
1 | 2 | 1 | CIP | W10050 | CIP_casting_2
1 | 2 | 1 | CIP | W10050 | CIP_dig&rebar_3
1 | 2 | 1 | CIP | W10050 | CIP_casting_3
1 | 2 | 1 | CIP | W10060 | CIP_capbeam
1 | 2 | 1 | CIP | W10070 | CIP_capbeam_casting
1 | 2 | 1 | waterblock | W11010 | waterblock_line_marking
1 | 2 | 1 | waterblock | W11020 | waterblock_dig&piping
1 | 2 | 1 | waterblock | W11030 | waterblock_injection
1 | 2 | 1 | waterblock | W11040 | waterblock_cleaning
3 | 2 | 1 | CIP | W10010 | CIP_line_marking
3 | 2 | 1 | CIP | W10020 | CIP_guidebeam
3 | 2 | 1 | CIP | W10030 | CIP_soil_compaction_for_machine
3 | 2 | 1 | CIP | W10040 | CIP_dig&rebar_1
3 | 2 | 1 | CIP | W10050 | CIP_casting_1
3 | 2 | 1 | CIP | W10050 | CIP_dig&rebar_2
3 | 2 | 1 | CIP | W10050 | CIP_casting_2
3 | 2 | 1 | CIP | W10050 | CIP_dig&rebar_3
3 | 2 | 1 | CIP | W10050 | CIP_casting_3
3 | 2 | 1 | CIP | W10060 | CIP_capbeam
3 | 2 | 1 | CIP | W10070 | CIP_capbeam_casting
3 | 2 | 1 | waterblock | W11010 | waterblock_line_marking
3 | 2 | 1 | waterblock | W11020 | waterblock_dig&piping
3 | 2 | 1 | waterblock | W11030 | waterblock_injection
3 | 2 | 1 | waterblock | W11040 | waterblock_cleaning
3 | 3 | 3 | excavation_test | D10010 | excavation_test_planning
3 | 3 | 3 | excavation_test | D10020 | excavation_test_excavation
3 | 3 | 3 | excavation_test | D10030 | excavation_test_inspection
1 | 1 | 1 | excavation
2 | 1 | 1 | excavation
3 | 1 | 1 | excavation
1 | 2 | 1 | excavation | R11010 | strut_installation_wale
2 | 2 | 1 | excavation | R11010 | strut_installation_wale
3 | 2 | 1 | excavation | R11010 | strut_installation_wale
1 | 3 | 1 | excavation | R11010 | strut_installation_wale
2 | 3 | 1 | excavation | R11010 | strut_installation_wale
3 | 3 | 1 | excavation | R11010 | strut_installation_wale
1 | 1 | -1 | excavation | R11010 | strut_installation_wale
2 | 1 | -1 | excavation | R11010 | strut_installation_wale
3 | 1 | -1 | excavation | R11010 | strut_installation_wale
1 | 2 | -1 | excavation | R11010 | strut_installation_wale
2 | 2 | -1 | excavation | R11010 | strut_installation_wale
3 | 2 | -1 | excavation | R11010 | strut_installation_wale
1 | 3 | -1 | excavation | R11010 | strut_installation_wale
2 | 3 | -1 | excavation | R11010 | strut_installation_wale
3 | 3 | -1 | excavation | R11010 | strut_installation_wale
1 | 1 | -2 | excavation | R11010 | strut_installation_wale
2 | 1 | -2 | excavation | R11010 | strut_installation_wale
3 | 1 | -2 | excavation | R11010 | strut_installation_wale
1 | 2 | -2 | excavation | R11010 | strut_installation_wale
2 | 2 | -2 | excavation | R11010 | strut_installation_wale
3 | 2 | -2 | excavation | R11010 | strut_installation_wale
1 | 3 | -2 | excavation | R11010 | strut_installation_wale
2 | 3 | -2 | excavation | R11010 | strut_installation_wale
3 | 3 | -2 | excavation | R11010 | strut_installation_wale
1 | 1 | 1 | post_pile | R10010 | post_pile_line_marking
1 | 1 | 1 | post_pile | R10020 | post_pile_dig&piling
1 | 1 | 1 | strut_installation | R11010 | strut_installation_wale
1 | 1 | 1 | strut_installation | R11020 | strut_installation_strut
1 | 1 | 1 | strut_installation | R11030 | strut_installation_inspection
1 | 1 | 1 | strut_dismatling | R12010 | strut_dismatling_check
1 | 1 | 1 | strut_dismatling | R12020 | strut_dismatling_remove
2 | 1 | 1 | post_pile | R10010 | post_pile_line_marking
2 | 1 | 1 | post_pile | R10020 | post_pile_dig&piling
2 | 1 | 1 | strut_installation | R11010 | strut_installation_wale
2 | 1 | 1 | strut_installation | R11020 | strut_installation_strut
2 | 1 | 1 | strut_installation | R11030 | strut_installation_inspection
2 | 1 | 1 | strut_dismatling | R12010 | strut_dismatling_check
2 | 1 | 1 | strut_dismatling | R12020 | strut_dismatling_remove
3 | 1 | 1 | post_pile | R10010 | post_pile_line_marking
3 | 1 | 1 | post_pile | R10020 | post_pile_dig&piling
3 | 1 | 1 | strut_installation | R11010 | strut_installation_wale
3 | 1 | 1 | strut_installation | R11020 | strut_installation_strut
3 | 1 | 1 | strut_installation | R11030 | strut_installation_inspection
3 | 1 | 1 | strut_dismatling | R12010 | strut_dismatling_check
3 | 1 | 1 | strut_dismatling | R12020 | strut_dismatling_remove
1 | 3 | 1 | post_pile | R10010 | post_pile_line_marking
1 | 3 | 1 | post_pile | R10020 | post_pile_dig&piling
1 | 3 | 1 | strut_installation | R11010 | strut_installation_wale
1 | 3 | 1 | strut_installation | R11020 | strut_installation_strut
1 | 3 | 1 | strut_installation | R11030 | strut_installation_inspection
1 | 3 | 1 | strut_dismatling | R12010 | strut_dismatling_check
1 | 3 | 1 | strut_dismatling | R12020 | strut_dismatling_remove
2 | 3 | 1 | post_pile | R10010 | post_pile_line_marking
2 | 3 | 1 | post_pile | R10020 | post_pile_dig&piling
2 | 3 | 1 | strut_installation | R11010 | strut_installation_wale
2 | 3 | 1 | strut_installation | R11020 | strut_installation_strut
2 | 3 | 1 | strut_installation | R11030 | strut_installation_inspection
2 | 3 | 1 | strut_dismatling | R12010 | strut_dismatling_check
2 | 3 | 1 | strut_dismatling | R12020 | strut_dismatling_remove
3 | 3 | 1 | post_pile | R10010 | post_pile_line_marking
3 | 3 | 1 | post_pile | R10020 | post_pile_dig&piling
3 | 3 | 1 | strut_installation | R11010 | strut_installation_wale
3 | 3 | 1 | strut_installation | R11020 | strut_installation_strut
3 | 3 | 1 | strut_installation | R11030 | strut_installation_inspection
3 | 3 | 1 | strut_dismatling | R12010 | strut_dismatling_check
3 | 3 | 1 | strut_dismatling | R12020 | strut_dismatling_remove
1 | 1 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
1 | 1 | -2 | foundation | F20020 | foundation_line_marking
1 | 1 | -2 | foundation | F20030 | foundation_re_bar
1 | 1 | -2 | foundation | F20040 | foundation_form
1 | 1 | -2 | foundation | F20050 | foundation_casting
1 | 1 | -2 | foundation | F20051 | foundation_curing
1 | 1 | -2 | foundation | F20060 | foundation_dismantling
1 | 1 | -2 | foundation | F20070 | foundation_backfill
2 | 1 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
2 | 1 | -2 | foundation | F20020 | foundation_line_marking
2 | 1 | -2 | foundation | F20030 | foundation_re_bar
2 | 1 | -2 | foundation | F20040 | foundation_form
2 | 1 | -2 | foundation | F20050 | foundation_casting
2 | 1 | -2 | foundation | F20051 | foundation_curing
2 | 1 | -2 | foundation | F20060 | foundation_dismantling
2 | 1 | -2 | foundation | F20070 | foundation_backfill
3 | 1 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
3 | 1 | -2 | foundation | F20020 | foundation_line_marking
3 | 1 | -2 | foundation | F20030 | foundation_re_bar
3 | 1 | -2 | foundation | F20040 | foundation_form
3 | 1 | -2 | foundation | F20050 | foundation_casting
3 | 1 | -2 | foundation | F20051 | foundation_curing
3 | 1 | -2 | foundation | F20060 | foundation_dismantling
3 | 1 | -2 | foundation | F20070 | foundation_backfill
1 | 2 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
1 | 2 | -2 | foundation | F20020 | foundation_line_marking
1 | 2 | -2 | foundation | F20030 | foundation_re_bar
1 | 2 | -2 | foundation | F20040 | foundation_form
1 | 2 | -2 | foundation | F20050 | foundation_casting
1 | 2 | -2 | foundation | F20051 | foundation_curing
1 | 2 | -2 | foundation | F20060 | foundation_dismantling
1 | 2 | -2 | foundation | F20070 | foundation_backfill
2 | 2 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
2 | 2 | -2 | foundation | F20020 | foundation_line_marking
2 | 2 | -2 | foundation | F20030 | foundation_re_bar
2 | 2 | -2 | foundation | F20040 | foundation_form
2 | 2 | -2 | foundation | F20050 | foundation_casting
2 | 2 | -2 | foundation | F20051 | foundation_curing
2 | 2 | -2 | foundation | F20060 | foundation_dismantling
2 | 2 | -2 | foundation | F20070 | foundation_backfill
3 | 2 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
3 | 2 | -2 | foundation | F20020 | foundation_line_marking
3 | 2 | -2 | foundation | F20030 | foundation_re_bar
3 | 2 | -2 | foundation | F20040 | foundation_form
3 | 2 | -2 | foundation | F20050 | foundation_casting
3 | 2 | -2 | foundation | F20051 | foundation_curing
3 | 2 | -2 | foundation | F20060 | foundation_dismantling
3 | 2 | -2 | foundation | F20070 | foundation_backfill
1 | 3 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
1 | 3 | -2 | foundation | F20020 | foundation_line_marking
1 | 3 | -2 | foundation | F20030 | foundation_re_bar
1 | 3 | -2 | foundation | F20040 | foundation_form
1 | 3 | -2 | foundation | F20050 | foundation_casting
1 | 3 | -2 | foundation | F20051 | foundation_curing
1 | 3 | -2 | foundation | F20060 | foundation_dismantling
1 | 3 | -2 | foundation | F20070 | foundation_backfill
2 | 3 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
2 | 3 | -2 | foundation | F20020 | foundation_line_marking
2 | 3 | -2 | foundation | F20030 | foundation_re_bar
2 | 3 | -2 | foundation | F20040 | foundation_form
2 | 3 | -2 | foundation | F20050 | foundation_casting
2 | 3 | -2 | foundation | F20051 | foundation_curing
2 | 3 | -2 | foundation | F20060 | foundation_dismantling
2 | 3 | -2 | foundation | F20070 | foundation_backfill
3 | 3 | -2 | foundation | F20010 | foundation_vapor_proof&lean_conc.
3 | 3 | -2 | foundation | F20020 | foundation_line_marking
3 | 3 | -2 | foundation | F20030 | foundation_re_bar
3 | 3 | -2 | foundation | F20040 | foundation_form
3 | 3 | -2 | foundation | F20050 | foundation_casting
3 | 3 | -2 | foundation | F20051 | foundation_curing
3 | 3 | -2 | foundation | F20060 | foundation_dismantling
3 | 3 | -2 | foundation | F20070 | foundation_backfill
2 | 1 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 1 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 1 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 1 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 1 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 1 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 1 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 1 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 1 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 1 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 1 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 1 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 1 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 1 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 1 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 2 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 2 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 2 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 2 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 2 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 2 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 2 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 2 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 2 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 2 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 2 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 2 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 2 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 2 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 2 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 3 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 3 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 3 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 3 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 3 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 3 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 3 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 3 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 3 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 3 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 3 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 3 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 3 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 3 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 3 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 1 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 1 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 1 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 1 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 1 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 1 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 1 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 1 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 1 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 1 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 1 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 1 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 1 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 1 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 1 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 2 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 2 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 2 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 2 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 2 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 2 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 2 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 2 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 2 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 2 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 2 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 2 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 2 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 2 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 2 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 3 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 3 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 3 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 3 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 3 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 3 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 3 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 3 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 3 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 3 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 3 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 3 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 3 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 3 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 3 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 1 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 1 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 1 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 1 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 1 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 1 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 1 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 1 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 1 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 1 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 1 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 1 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 1 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 1 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 1 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 2 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 2 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 2 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 2 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 2 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 2 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 2 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 2 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 2 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 2 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 2 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 2 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 2 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 2 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 2 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 3 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 3 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 3 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 3 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 3 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 3 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 3 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 3 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 3 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 3 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 3 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 3 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 3 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 3 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 3 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 1 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 1 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 1 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 1 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 1 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 1 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 1 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 1 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 1 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 1 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 1 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 1 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 1 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 1 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 1 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 2 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 2 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 2 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 2 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 2 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 2 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 2 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 2 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 2 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 2 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 2 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 2 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 2 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 2 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 2 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 3 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 3 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 3 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 3 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 3 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 3 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 3 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 3 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 3 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 3 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 3 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 3 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 3 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 3 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 3 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 1 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 1 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 1 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 1 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 1 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 1 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 1 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 1 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 1 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 1 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 1 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 1 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 1 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 1 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 1 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 2 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 2 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 2 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 2 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 2 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 2 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 2 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 2 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 2 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 2 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 2 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 2 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 2 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 2 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 2 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 3 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 3 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 3 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 3 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 3 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 3 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 3 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 3 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 3 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 3 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 3 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 3 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 3 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 3 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 3 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 1 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 1 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 1 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 1 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 1 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 1 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 1 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 1 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 1 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 1 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 1 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 1 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 1 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 1 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 1 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 2 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 2 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 2 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 2 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 2 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 2 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 2 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 2 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 2 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 2 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 2 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 2 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 2 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 2 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 2 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 3 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 3 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 3 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 3 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 3 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 3 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 3 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 3 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 3 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 3 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 3 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 3 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 3 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 3 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 3 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling

## grid_wp_list
x | y | z | wp_code | wp_name_en
0 | 0 | 0 | M000 | milestone
1 | 1 | 1 | T100 | fence
1 | 2 | 1 | T100 | fence
1 | 3 | 1 | T100 | fence
3 | 1 | 1 | T100 | fence
3 | 2 | 1 | T100 | fence
3 | 3 | 1 | T100 | fence
2 | 1 | 1 | T100 | fence
2 | 3 | 1 | T100 | fence
1 | 2 | 1 | T300 | t-crane_installation
1 | 2 | 1 | T320 | t-crane_dismantling
1 | 3 | 1 | T350 | lift_installation
1 | 3 | 1 | T370 | lift_dismantling
1 | 1 | 1 | W100 | CIP
1 | 1 | 1 | W110 | waterblock
2 | 1 | 1 | W100 | CIP
2 | 1 | 1 | W110 | waterblock
3 | 1 | 1 | W100 | CIP
3 | 1 | 1 | W110 | waterblock
1 | 3 | 1 | W100 | CIP
1 | 3 | 1 | W110 | waterblock
2 | 3 | 1 | W100 | CIP
2 | 3 | 1 | W110 | waterblock
3 | 3 | 1 | W100 | CIP
3 | 3 | 1 | W110 | waterblock
1 | 2 | 1 | W100 | CIP
1 | 2 | 1 | W110 | waterblock
3 | 2 | 1 | W100 | CIP
3 | 2 | 1 | W110 | waterblock
3 | 3 | 1 | D100 | excavation_test
1 | 1 | 1 | D110 | excavation
2 | 1 | 1 | D110 | excavation
3 | 1 | 1 | D110 | excavation
1 | 2 | 1 | D110 | excavation
2 | 2 | 1 | D110 | excavation
3 | 2 | 1 | D110 | excavation
1 | 3 | 1 | D110 | excavation
2 | 3 | 1 | D110 | excavation
3 | 3 | 1 | D110 | excavation
1 | 1 | -1 | D110 | excavation
2 | 1 | -1 | D110 | excavation
3 | 1 | -1 | D110 | excavation
1 | 2 | -1 | D110 | excavation
2 | 2 | -1 | D110 | excavation
3 | 2 | -1 | D110 | excavation
1 | 3 | -1 | D110 | excavation
2 | 3 | -1 | D110 | excavation
3 | 3 | -1 | D110 | excavation
1 | 1 | -2 | D110 | excavation
2 | 1 | -2 | D110 | excavation
3 | 1 | -2 | D110 | excavation
1 | 2 | -2 | D110 | excavation
2 | 2 | -2 | D110 | excavation
3 | 2 | -2 | D110 | excavation
1 | 3 | -2 | D110 | excavation
2 | 3 | -2 | D110 | excavation
3 | 3 | -2 | D110 | excavation
1 | 1 | 1 | R100 | post_pile
1 | 1 | 1 | R110 | strut_installation
1 | 1 | 1 | R120 | strut_dismatling
2 | 1 | 1 | R100 | post_pile
2 | 1 | 1 | R110 | strut_installation
2 | 1 | 1 | R120 | strut_dismatling
3 | 1 | 1 | R100 | post_pile
3 | 1 | 1 | R110 | strut_installation
3 | 1 | 1 | R120 | strut_dismatling
1 | 3 | 1 | R100 | post_pile
1 | 3 | 1 | R110 | strut_installation
1 | 3 | 1 | R120 | strut_dismatling
2 | 3 | 1 | R100 | post_pile
2 | 3 | 1 | R110 | strut_installation
2 | 3 | 1 | R120 | strut_dismatling
3 | 3 | 1 | R100 | post_pile
3 | 3 | 1 | R110 | strut_installation
3 | 3 | 1 | R120 | strut_dismatling
1 | 1 | -2 | F200 | foundation
2 | 1 | -2 | F200 | foundation
3 | 1 | -2 | F200 | foundation
1 | 2 | -2 | F200 | foundation
2 | 2 | -2 | F200 | foundation
3 | 2 | -2 | F200 | foundation
1 | 3 | -2 | F200 | foundation
2 | 3 | -2 | F200 | foundation
3 | 3 | -2 | F200 | foundation
2 | 1 | -1 | S100 | rc_structure_vertical
2 | 1 | -1 | S110 | rc_structure_horizontal
2 | 2 | -1 | S100 | rc_structure_vertical
2 | 2 | -1 | S110 | rc_structure_horizontal
2 | 3 | -1 | S100 | rc_structure_vertical
2 | 3 | -1 | S110 | rc_structure_horizontal
3 | 1 | -1 | S100 | rc_structure_vertical
3 | 1 | -1 | S110 | rc_structure_horizontal
3 | 2 | -1 | S100 | rc_structure_vertical
3 | 2 | -1 | S110 | rc_structure_horizontal
3 | 3 | -1 | S100 | rc_structure_vertical
3 | 3 | -1 | S110 | rc_structure_horizontal
2 | 1 | 1 | S100 | rc_structure_vertical
2 | 1 | 1 | S110 | rc_structure_horizontal
2 | 2 | 1 | S100 | rc_structure_vertical
2 | 2 | 1 | S110 | rc_structure_horizontal
2 | 3 | 1 | S100 | rc_structure_vertical
2 | 3 | 1 | S110 | rc_structure_horizontal
3 | 1 | 1 | S100 | rc_structure_vertical
3 | 1 | 1 | S110 | rc_structure_horizontal
3 | 2 | 1 | S100 | rc_structure_vertical
3 | 2 | 1 | S110 | rc_structure_horizontal
3 | 3 | 1 | S100 | rc_structure_vertical
3 | 3 | 1 | S110 | rc_structure_horizontal
2 | 1 | 2 | S100 | rc_structure_vertical
2 | 1 | 2 | S110 | rc_structure_horizontal
2 | 2 | 2 | S100 | rc_structure_vertical
2 | 2 | 2 | S110 | rc_structure_horizontal
2 | 3 | 2 | S100 | rc_structure_vertical
2 | 3 | 2 | S110 | rc_structure_horizontal
3 | 1 | 2 | S100 | rc_structure_vertical
3 | 1 | 2 | S110 | rc_structure_horizontal
3 | 2 | 2 | S100 | rc_structure_vertical
3 | 2 | 2 | S110 | rc_structure_horizontal
3 | 3 | 2 | S100 | rc_structure_vertical
3 | 3 | 2 | S110 | rc_structure_horizontal