## grid_activity_list
x | y | z | wp_code | wp_name_en | act_id | step | act_name_en | productivity
0 | 0 | 0 | M000 | milestone | M00009 |  | project_completion | 1
0 | 0 | 0 | M000 | milestone | M00001 |  | project_start | 1
0 | 0 | 0 | M000 | milestone | M00007 |  | elevator | 1
1 | 1 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
1 | 1 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
1 | 1 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
1 | 1 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
1 | 1 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
1 | 1 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
1 | 1 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
1 | 1 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
1 | 1 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
1 | 2 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
1 | 2 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
1 | 2 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
1 | 2 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
1 | 2 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
1 | 2 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
1 | 2 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
1 | 2 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
1 | 2 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
1 | 3 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
1 | 3 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
1 | 3 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
1 | 3 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
1 | 3 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
1 | 3 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
1 | 3 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
1 | 3 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
1 | 3 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
3 | 1 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
3 | 1 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
3 | 1 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
3 | 1 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
3 | 1 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
3 | 1 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
3 | 1 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
3 | 1 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
3 | 1 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
3 | 2 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
3 | 2 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
3 | 2 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
3 | 2 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
3 | 2 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
3 | 2 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
3 | 2 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
3 | 2 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
3 | 2 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
3 | 3 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
3 | 3 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
3 | 3 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
3 | 3 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
3 | 3 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
3 | 3 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
3 | 3 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
3 | 3 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
3 | 3 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
2 | 1 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
2 | 1 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
2 | 1 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
2 | 1 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
2 | 1 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
2 | 1 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
2 | 1 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
2 | 1 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
2 | 1 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
2 | 3 | 1 | T100 | fence | T10010 | line_marking | fence-line_marking | 5
2 | 3 | 1 | T100 | fence | T10020 | excavation | fence-excavation | 3
2 | 3 | 1 | T100 | fence | T10030 | compaction | fence-compaction | 3
2 | 3 | 1 | T100 | fence | T10040 | foundation | fence-foundation | 3
2 | 3 | 1 | T100 | fence | T10050 | backfilling | fence-backfilling | 3
2 | 3 | 1 | T100 | fence | T10060 | steel | fence-steel | 3
2 | 3 | 1 | T100 | fence | T10070 | panel | fence-panel | 5
2 | 3 | 1 | T100 | fence | T10080 | wrapping | fence-wrapping | 10
2 | 3 | 1 | T100 | fence | T10090 | inspection | fence-inspection | 20
1 | 2 | 1 | T300 | t-crane_installation | T30010 | form | t-crane_installation-form | 1
1 | 2 | 1 | T300 | t-crane_installation | T30020 | rebar | t-crane_installation-rebar | 1
1 | 2 | 1 | T300 | t-crane_installation | T30030 | casting | t-crane_installation-casting | 1
1 | 2 | 1 | T300 | t-crane_installation | T30031 | curing1 | t-crane_installation-curing1 | 1
1 | 2 | 1 | T300 | t-crane_installation | T30032 | curing2 | t-crane_installation-curing2 | 1
1 | 2 | 1 | T300 | t-crane_installation | T30033 | curing3 | t-crane_installation-curing3 | 1
1 | 2 | 1 | T300 | t-crane_installation | T30034 | curing4 | t-crane_installation-curing4 | 1
1 | 2 | 1 | T300 | t-crane_installation | T30035 | curing5 | t-crane_installation-curing5 | 1
1 | 2 | 1 | T300 | t-crane_installation | T30036 | curing6 | t-crane_installation-curing6 | 1
1 | 2 | 1 | T300 | t-crane_installation | T30040 | installation | t-crane_installation-installation | 1
1 | 2 | 1 | T300 | t-crane_installation | T30050 | inspection | t-crane_installation-inspection | 1
1 | 2 | 1 | T320 | t-crane_dismantling | T32010 | machine | t-crane_dismantling-machine | 1
1 | 2 | 1 | T320 | t-crane_dismantling | T32020 | dismantling | t-crane_dismantling-dismantling | 1
1 | 3 | 1 | T350 | lift_installation | T35010 | form | lift_installation-form | 1
1 | 3 | 1 | T350 | lift_installation | T35020 | rebar | lift_installation-rebar | 1
1 | 3 | 1 | T350 | lift_installation | T35030 | casting | lift_installation-casting | 1
1 | 3 | 1 | T350 | lift_installation | T35031 | curing1 | lift_installation-curing1 | 1
1 | 3 | 1 | T350 | lift_installation | T35032 | curing2 | lift_installation-curing2 | 1
1 | 3 | 1 | T350 | lift_installation | T35033 | curing3 | lift_installation-curing3 | 1
1 | 3 | 1 | T350 | lift_installation | T35034 | curing4 | lift_installation-curing4 | 1
1 | 3 | 1 | T350 | lift_installation | T35035 | curing5 | lift_installation-curing5 | 1
1 | 3 | 1 | T350 | lift_installation | T35036 | curing6 | lift_installation-curing6 | 1
1 | 3 | 1 | T350 | lift_installation | T35040 | installation | lift_installation-installation | 1
1 | 3 | 1 | T350 | lift_installation | T35050 | inspection | lift_installation-inspection | 1
1 | 3 | 1 | T370 | lift_dismantling
1 | 1 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
1 | 1 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
1 | 1 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
1 | 1 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
1 | 1 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
1 | 1 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
1 | 1 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
1 | 1 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
1 | 1 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
1 | 1 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
1 | 1 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
1 | 1 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
1 | 1 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
1 | 1 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
1 | 1 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
2 | 1 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
2 | 1 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
2 | 1 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
2 | 1 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
2 | 1 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
2 | 1 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
2 | 1 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
2 | 1 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
2 | 1 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
2 | 1 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
2 | 1 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
2 | 1 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
2 | 1 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
2 | 1 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
2 | 1 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
3 | 1 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
3 | 1 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
3 | 1 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
3 | 1 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
3 | 1 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
3 | 1 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
3 | 1 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
3 | 1 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
3 | 1 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
3 | 1 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
3 | 1 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
3 | 1 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
3 | 1 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
3 | 1 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
3 | 1 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
1 | 3 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
1 | 3 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
1 | 3 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
1 | 3 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
1 | 3 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
1 | 3 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
1 | 3 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
1 | 3 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
1 | 3 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
1 | 3 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
1 | 3 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
1 | 3 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
1 | 3 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
1 | 3 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
1 | 3 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
2 | 3 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
2 | 3 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
2 | 3 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
2 | 3 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
2 | 3 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
2 | 3 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
2 | 3 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
2 | 3 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
2 | 3 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
2 | 3 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
2 | 3 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
2 | 3 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
2 | 3 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
2 | 3 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
2 | 3 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
3 | 3 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
3 | 3 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
3 | 3 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
3 | 3 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
3 | 3 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
3 | 3 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
3 | 3 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
3 | 3 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
3 | 3 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
3 | 3 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
3 | 3 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
3 | 3 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
3 | 3 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
3 | 3 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
3 | 3 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
1 | 2 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
1 | 2 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
1 | 2 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
1 | 2 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
1 | 2 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
1 | 2 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
1 | 2 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
1 | 2 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
1 | 2 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
1 | 2 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
1 | 2 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
1 | 2 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
1 | 2 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
1 | 2 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
1 | 2 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
3 | 2 | 1 | W100 | CIP | W10010 | line_marking | CIP-line_marking | 10
3 | 2 | 1 | W100 | CIP | W10020 | guidebeam | CIP-guidebeam | 5
3 | 2 | 1 | W100 | CIP | W10030 | soil_compaction_for_machine | CIP-soil_compaction_for_machine | 4
3 | 2 | 1 | W100 | CIP | W10040 | dig&rebar_1 | CIP-dig&rebar_1 | 3
3 | 2 | 1 | W100 | CIP | W10050 | casting_1 | CIP-casting_1 | 3
3 | 2 | 1 | W100 | CIP | W10050 | dig&rebar_2 | CIP-dig&rebar_2 | 3
3 | 2 | 1 | W100 | CIP | W10050 | casting_2 | CIP-casting_2 | 3
3 | 2 | 1 | W100 | CIP | W10050 | dig&rebar_3 | CIP-dig&rebar_3 | 3
3 | 2 | 1 | W100 | CIP | W10050 | casting_3 | CIP-casting_3 | 3
3 | 2 | 1 | W100 | CIP | W10060 | capbeam | CIP-capbeam | 10
3 | 2 | 1 | W100 | CIP | W10070 | capbeam_casting | CIP-capbeam_casting | 10
3 | 2 | 1 | W110 | waterblock | W11010 | line_marking | waterblock-line_marking | 10
3 | 2 | 1 | W110 | waterblock | W11020 | dig&piping | waterblock-dig&piping | 5
3 | 2 | 1 | W110 | waterblock | W11030 | injection | waterblock-injection | 5
3 | 2 | 1 | W110 | waterblock | W11040 | cleaning | waterblock-cleaning | 10
3 | 3 | 3 | D100 | excavation_test | D10010 | planning | excavation_test-planning | 10
3 | 3 | 3 | D100 | excavation_test | D10020 | excavation | excavation_test-excavation | 1
3 | 3 | 3 | D100 | excavation_test | D10030 | inspection | excavation_test-inspection | 1
1 | 1 | 1 | D110 | excavation
2 | 1 | 1 | D110 | excavation
3 | 1 | 1 | D110 | excavation
1 | 2 | 1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 2 | 1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 2 | 1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 3 | 1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 3 | 1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 3 | 1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 1 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 1 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 1 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 2 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 2 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 2 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 3 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 3 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 3 | -1 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 1 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 1 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 1 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 2 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 2 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 2 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 3 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
2 | 3 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
3 | 3 | -2 | D110 | excavation | R11010 | wale | strut_installation-wale | 3
1 | 1 | 1 | R100 | post_pile | R10010 | line_marking | post_pile-line_marking | 10
1 | 1 | 1 | R100 | post_pile | R10020 | dig&piling | post_pile-dig&piling | 3
1 | 1 | 1 | R110 | strut_installation | R11010 | wale | strut_installation-wale | 3
1 | 1 | 1 | R110 | strut_installation | R11020 | strut | strut_installation-strut | 3
1 | 1 | 1 | R110 | strut_installation | R11030 | inspection | strut_installation-inspection | 3
1 | 1 | 1 | R120 | strut_dismatling | R12010 | check | strut_dismatling-check | 5
1 | 1 | 1 | R120 | strut_dismatling | R12020 | remove | strut_dismatling-remove | 4
2 | 1 | 1 | R100 | post_pile | R10010 | line_marking | post_pile-line_marking | 10
2 | 1 | 1 | R100 | post_pile | R10020 | dig&piling | post_pile-dig&piling | 3
2 | 1 | 1 | R110 | strut_installation | R11010 | wale | strut_installation-wale | 3
2 | 1 | 1 | R110 | strut_installation | R11020 | strut | strut_installation-strut | 3
2 | 1 | 1 | R110 | strut_installation | R11030 | inspection | strut_installation-inspection | 3
2 | 1 | 1 | R120 | strut_dismatling | R12010 | check | strut_dismatling-check | 5
2 | 1 | 1 | R120 | strut_dismatling | R12020 | remove | strut_dismatling-remove | 4
3 | 1 | 1 | R100 | post_pile | R10010 | line_marking | post_pile-line_marking | 10
3 | 1 | 1 | R100 | post_pile | R10020 | dig&piling | post_pile-dig&piling | 3
3 | 1 | 1 | R110 | strut_installation | R11010 | wale | strut_installation-wale | 3
3 | 1 | 1 | R110 | strut_installation | R11020 | strut | strut_installation-strut | 3
3 | 1 | 1 | R110 | strut_installation | R11030 | inspection | strut_installation-inspection | 3
3 | 1 | 1 | R120 | strut_dismatling | R12010 | check | strut_dismatling-check | 5
3 | 1 | 1 | R120 | strut_dismatling | R12020 | remove | strut_dismatling-remove | 4
1 | 3 | 1 | R100 | post_pile | R10010 | line_marking | post_pile-line_marking | 10
1 | 3 | 1 | R100 | post_pile | R10020 | dig&piling | post_pile-dig&piling | 3
1 | 3 | 1 | R110 | strut_installation | R11010 | wale | strut_installation-wale | 3
1 | 3 | 1 | R110 | strut_installation | R11020 | strut | strut_installation-strut | 3
1 | 3 | 1 | R110 | strut_installation | R11030 | inspection | strut_installation-inspection | 3
1 | 3 | 1 | R120 | strut_dismatling | R12010 | check | strut_dismatling-check | 5
1 | 3 | 1 | R120 | strut_dismatling | R12020 | remove | strut_dismatling-remove | 4
2 | 3 | 1 | R100 | post_pile | R10010 | line_marking | post_pile-line_marking | 10
2 | 3 | 1 | R100 | post_pile | R10020 | dig&piling | post_pile-dig&piling | 3
2 | 3 | 1 | R110 | strut_installation | R11010 | wale | strut_installation-wale | 3
2 | 3 | 1 | R110 | strut_installation | R11020 | strut | strut_installation-strut | 3
2 | 3 | 1 | R110 | strut_installation | R11030 | inspection | strut_installation-inspection | 3
2 | 3 | 1 | R120 | strut_dismatling | R12010 | check | strut_dismatling-check | 5
2 | 3 | 1 | R120 | strut_dismatling | R12020 | remove | strut_dismatling-remove | 4
3 | 3 | 1 | R100 | post_pile | R10010 | line_marking | post_pile-line_marking | 10
3 | 3 | 1 | R100 | post_pile | R10020 | dig&piling | post_pile-dig&piling | 3
3 | 3 | 1 | R110 | strut_installation | R11010 | wale | strut_installation-wale | 3
3 | 3 | 1 | R110 | strut_installation | R11020 | strut | strut_installation-strut | 3
3 | 3 | 1 | R110 | strut_installation | R11030 | inspection | strut_installation-inspection | 3
3 | 3 | 1 | R120 | strut_dismatling | R12010 | check | strut_dismatling-check | 5
3 | 3 | 1 | R120 | strut_dismatling | R12020 | remove | strut_dismatling-remove | 4
1 | 1 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
1 | 1 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
1 | 1 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
1 | 1 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
1 | 1 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
1 | 1 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
1 | 1 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
1 | 1 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
2 | 1 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
2 | 1 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
2 | 1 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
2 | 1 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
2 | 1 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
2 | 1 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
2 | 1 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
2 | 1 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
3 | 1 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
3 | 1 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
3 | 1 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
3 | 1 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
3 | 1 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
3 | 1 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
3 | 1 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
3 | 1 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
1 | 2 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
1 | 2 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
1 | 2 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
1 | 2 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
1 | 2 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
1 | 2 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
1 | 2 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
1 | 2 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
2 | 2 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
2 | 2 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
2 | 2 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
2 | 2 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
2 | 2 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
2 | 2 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
2 | 2 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
2 | 2 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
3 | 2 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
3 | 2 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
3 | 2 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
3 | 2 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
3 | 2 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
3 | 2 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
3 | 2 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
3 | 2 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
1 | 3 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
1 | 3 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
1 | 3 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
1 | 3 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
1 | 3 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
1 | 3 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
1 | 3 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
1 | 3 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
2 | 3 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
2 | 3 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
2 | 3 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
2 | 3 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
2 | 3 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
2 | 3 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
2 | 3 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
2 | 3 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
3 | 3 | -2 | F200 | foundation | F20010 | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | 4
3 | 3 | -2 | F200 | foundation | F20020 | line_marking | foundation-line_marking | 4
3 | 3 | -2 | F200 | foundation | F20030 | re-bar | foundation-re-bar | 2
3 | 3 | -2 | F200 | foundation | F20040 | form | foundation-form | 2
3 | 3 | -2 | F200 | foundation | F20050 | casting | foundation-casting | 3
3 | 3 | -2 | F200 | foundation | F20051 | curing | foundation-curing | 3
3 | 3 | -2 | F200 | foundation | F20060 | dismantling | foundation-dismantling | 3
3 | 3 | -2 | F200 | foundation | F20070 | backfill | foundation-backfill | 5
2 | 1 | -1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 1 | -1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 1 | -1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 1 | -1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 1 | -1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 1 | -1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 1 | -1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 1 | -1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 1 | -1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 1 | -1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 1 | -1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 1 | -1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 1 | -1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 1 | -1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 1 | -1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 2 | -1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 2 | -1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 2 | -1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 2 | -1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 2 | -1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 2 | -1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 2 | -1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 2 | -1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 2 | -1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 2 | -1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 2 | -1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 2 | -1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 2 | -1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 2 | -1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 2 | -1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 3 | -1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 3 | -1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 3 | -1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 3 | -1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 3 | -1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 3 | -1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 3 | -1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 3 | -1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 3 | -1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 3 | -1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 3 | -1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 3 | -1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 3 | -1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 3 | -1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 3 | -1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 1 | -1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 1 | -1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 1 | -1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 1 | -1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 1 | -1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 1 | -1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 1 | -1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 1 | -1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 1 | -1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 1 | -1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 1 | -1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 1 | -1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 1 | -1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 1 | -1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 1 | -1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 2 | -1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 2 | -1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 2 | -1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 2 | -1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 2 | -1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 2 | -1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 2 | -1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 2 | -1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 2 | -1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 2 | -1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 2 | -1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 2 | -1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 2 | -1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 2 | -1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 2 | -1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 3 | -1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 3 | -1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 3 | -1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 3 | -1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 3 | -1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 3 | -1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 3 | -1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 3 | -1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 3 | -1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 3 | -1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 3 | -1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 3 | -1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 3 | -1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 3 | -1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 3 | -1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 1 | 1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 1 | 1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 1 | 1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 1 | 1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 1 | 1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 1 | 1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 1 | 1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 1 | 1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 1 | 1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 1 | 1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 1 | 1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 1 | 1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 1 | 1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 1 | 1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 1 | 1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 2 | 1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 2 | 1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 2 | 1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 2 | 1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 2 | 1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 2 | 1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 2 | 1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 2 | 1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 2 | 1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 2 | 1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 2 | 1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 2 | 1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 2 | 1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 2 | 1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 2 | 1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 3 | 1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 3 | 1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 3 | 1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 3 | 1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 3 | 1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 3 | 1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 3 | 1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 3 | 1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 3 | 1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 3 | 1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 3 | 1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 3 | 1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 3 | 1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 3 | 1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 3 | 1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 1 | 1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 1 | 1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 1 | 1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 1 | 1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 1 | 1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 1 | 1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 1 | 1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 1 | 1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 1 | 1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 1 | 1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 1 | 1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 1 | 1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 1 | 1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 1 | 1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 1 | 1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 2 | 1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 2 | 1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 2 | 1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 2 | 1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 2 | 1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 2 | 1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 2 | 1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 2 | 1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 2 | 1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 2 | 1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 2 | 1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 2 | 1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 2 | 1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 2 | 1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 2 | 1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 3 | 1 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 3 | 1 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 3 | 1 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 3 | 1 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 3 | 1 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 3 | 1 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 3 | 1 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 3 | 1 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 3 | 1 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 3 | 1 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 3 | 1 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 3 | 1 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 3 | 1 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 3 | 1 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 3 | 1 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 1 | 2 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 1 | 2 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 1 | 2 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 1 | 2 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 1 | 2 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 1 | 2 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 1 | 2 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 1 | 2 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 1 | 2 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 1 | 2 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 1 | 2 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 1 | 2 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 1 | 2 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 1 | 2 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 1 | 2 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 2 | 2 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 2 | 2 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 2 | 2 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 2 | 2 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 2 | 2 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 2 | 2 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 2 | 2 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 2 | 2 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 2 | 2 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 2 | 2 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 2 | 2 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 2 | 2 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 2 | 2 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 2 | 2 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 2 | 2 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
2 | 3 | 2 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
2 | 3 | 2 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
2 | 3 | 2 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
2 | 3 | 2 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
2 | 3 | 2 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
2 | 3 | 2 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
2 | 3 | 2 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
2 | 3 | 2 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
2 | 3 | 2 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
2 | 3 | 2 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
2 | 3 | 2 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
2 | 3 | 2 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
2 | 3 | 2 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
2 | 3 | 2 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
2 | 3 | 2 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 1 | 2 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 1 | 2 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 1 | 2 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 1 | 2 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 1 | 2 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 1 | 2 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 1 | 2 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 1 | 2 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 1 | 2 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 1 | 2 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 1 | 2 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 1 | 2 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 1 | 2 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 1 | 2 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 1 | 2 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 2 | 2 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 2 | 2 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 2 | 2 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 2 | 2 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 2 | 2 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 2 | 2 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 2 | 2 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 2 | 2 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 2 | 2 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 2 | 2 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 2 | 2 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 2 | 2 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 2 | 2 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 2 | 2 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 2 | 2 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3
3 | 3 | 2 | S100 | rc_structure_vertical | S10010 | line_marking | rc_structure_vertical-line_marking | 5
3 | 3 | 2 | S100 | rc_structure_vertical | S10020 | re-bar | rc_structure_vertical-re-bar | 3
3 | 3 | 2 | S100 | rc_structure_vertical | S10030 | embedding | rc_structure_vertical-embedding | 3
3 | 3 | 2 | S100 | rc_structure_vertical | S10040 | form | rc_structure_vertical-form | 3
3 | 3 | 2 | S100 | rc_structure_vertical | S10050 | inspection | rc_structure_vertical-inspection | 5
3 | 3 | 2 | S100 | rc_structure_vertical | S10060 | casting | rc_structure_vertical-casting | 5
3 | 3 | 2 | S100 | rc_structure_vertical | S10061 | curing | rc_structure_vertical-curing | 5
3 | 3 | 2 | S100 | rc_structure_vertical | S10070 | dismantling | rc_structure_vertical-dismantling | 3
3 | 3 | 2 | S110 | rc_structure_horizontal | S11010 | form | rc_structure_horizontal-form | 2
3 | 3 | 2 | S110 | rc_structure_horizontal | S11020 | re-bar | rc_structure_horizontal-re-bar | 3
3 | 3 | 2 | S110 | rc_structure_horizontal | S11030 | embedding | rc_structure_horizontal-embedding | 3
3 | 3 | 2 | S110 | rc_structure_horizontal | S11040 | inspection | rc_structure_horizontal-inspection | 5
3 | 3 | 2 | S110 | rc_structure_horizontal | S11050 | casting | rc_structure_horizontal-casting | 5
3 | 3 | 2 | S110 | rc_structure_horizontal | S11051 | curing | rc_structure_horizontal-curing | 5
3 | 3 | 2 | S110 | rc_structure_horizontal | S11060 | dismantling | rc_structure_horizontal-dismantling | 3

## grid_wp_list
x | y | z | wp_code | wp_name_en
0 | 0 | 0 | M000 | milestone
1 | 1 | 1 | T100 | fence
1 | 2 | 1 | T100 | fence
1 | 3 | 1 | T100 | fence
3 | 1 | 1 | T100 | fence
3 | 2 | 1 | T100 | fence
3 | 3 | 1 | T100 | fence
2 | 1 | 1 | T100 | fence
2 | 3 | 1 | T100 | fence
1 | 2 | 1 | T300 | t-crane_installation
1 | 2 | 1 | T320 | t-crane_dismantling
1 | 3 | 1 | T350 | lift_installation
1 | 3 | 1 | T370 | lift_dismantling
1 | 1 | 1 | W100 | CIP
1 | 1 | 1 | W110 | waterblock
2 | 1 | 1 | W100 | CIP
2 | 1 | 1 | W110 | waterblock
3 | 1 | 1 | W100 | CIP
3 | 1 | 1 | W110 | waterblock
1 | 3 | 1 | W100 | CIP
1 | 3 | 1 | W110 | waterblock
2 | 3 | 1 | W100 | CIP
2 | 3 | 1 | W110 | waterblock
3 | 3 | 1 | W100 | CIP
3 | 3 | 1 | W110 | waterblock
1 | 2 | 1 | W100 | CIP
1 | 2 | 1 | W110 | waterblock
3 | 2 | 1 | W100 | CIP
3 | 2 | 1 | W110 | waterblock
3 | 3 | 1 | D100 | excavation_test
1 | 1 | 1 | D110 | excavation
2 | 1 | 1 | D110 | excavation
3 | 1 | 1 | D110 | excavation
1 | 2 | 1 | D110 | excavation
2 | 2 | 1 | D110 | excavation
3 | 2 | 1 | D110 | excavation
1 | 3 | 1 | D110 | excavation
2 | 3 | 1 | D110 | excavation
3 | 3 | 1 | D110 | excavation
1 | 1 | -1 | D110 | excavation
2 | 1 | -1 | D110 | excavation
3 | 1 | -1 | D110 | excavation
1 | 2 | -1 | D110 | excavation
2 | 2 | -1 | D110 | excavation
3 | 2 | -1 | D110 | excavation
1 | 3 | -1 | D110 | excavation
2 | 3 | -1 | D110 | excavation
3 | 3 | -1 | D110 | excavation
1 | 1 | -2 | D110 | excavation
2 | 1 | -2 | D110 | excavation
3 | 1 | -2 | D110 | excavation
1 | 2 | -2 | D110 | excavation
2 | 2 | -2 | D110 | excavation
3 | 2 | -2 | D110 | excavation
1 | 3 | -2 | D110 | excavation
2 | 3 | -2 | D110 | excavation
3 | 3 | -2 | D110 | excavation
1 | 1 | 1 | R100 | post_pile
1 | 1 | 1 | R110 | strut_installation
1 | 1 | 1 | R120 | strut_dismatling
2 | 1 | 1 | R100 | post_pile
2 | 1 | 1 | R110 | strut_installation
2 | 1 | 1 | R120 | strut_dismatling
3 | 1 | 1 | R100 | post_pile
3 | 1 | 1 | R110 | strut_installation
3 | 1 | 1 | R120 | strut_dismatling
1 | 3 | 1 | R100 | post_pile
1 | 3 | 1 | R110 | strut_installation
1 | 3 | 1 | R120 | strut_dismatling
2 | 3 | 1 | R100 | post_pile
2 | 3 | 1 | R110 | strut_installation
2 | 3 | 1 | R120 | strut_dismatling
3 | 3 | 1 | R100 | post_pile
3 | 3 | 1 | R110 | strut_installation
3 | 3 | 1 | R120 | strut_dismatling
1 | 1 | -2 | F200 | foundation
2 | 1 | -2 | F200 | foundation
3 | 1 | -2 | F200 | foundation
1 | 2 | -2 | F200 | foundation
2 | 2 | -2 | F200 | foundation
3 | 2 | -2 | F200 | foundation
1 | 3 | -2 | F200 | foundation
2 | 3 | -2 | F200 | foundation
3 | 3 | -2 | F200 | foundation
2 | 1 | -1 | S100 | rc_structure_vertical
2 | 1 | -1 | S110 | rc_structure_horizontal
2 | 2 | -1 | S100 | rc_structure_vertical
2 | 2 | -1 | S110 | rc_structure_horizontal
2 | 3 | -1 | S100 | rc_structure_vertical
2 | 3 | -1 | S110 | rc_structure_horizontal
3 | 1 | -1 | S100 | rc_structure_vertical
3 | 1 | -1 | S110 | rc_structure_horizontal
3 | 2 | -1 | S100 | rc_structure_vertical
3 | 2 | -1 | S110 | rc_structure_horizontal
3 | 3 | -1 | S100 | rc_structure_vertical
3 | 3 | -1 | S110 | rc_structure_horizontal
2 | 1 | 1 | S100 | rc_structure_vertical
2 | 1 | 1 | S110 | rc_structure_horizontal
2 | 2 | 1 | S100 | rc_structure_vertical
2 | 2 | 1 | S110 | rc_structure_horizontal
2 | 3 | 1 | S100 | rc_structure_vertical
2 | 3 | 1 | S110 | rc_structure_horizontal
3 | 1 | 1 | S100 | rc_structure_vertical
3 | 1 | 1 | S110 | rc_structure_horizontal
3 | 2 | 1 | S100 | rc_structure_vertical
3 | 2 | 1 | S110 | rc_structure_horizontal
3 | 3 | 1 | S100 | rc_structure_vertical
3 | 3 | 1 | S110 | rc_structure_horizontal
2 | 1 | 2 | S100 | rc_structure_vertical
2 | 1 | 2 | S110 | rc_structure_horizontal
2 | 2 | 2 | S100 | rc_structure_vertical
2 | 2 | 2 | S110 | rc_structure_horizontal
2 | 3 | 2 | S100 | rc_structure_vertical
2 | 3 | 2 | S110 | rc_structure_horizontal
3 | 1 | 2 | S100 | rc_structure_vertical
3 | 1 | 2 | S110 | rc_structure_horizontal
3 | 2 | 2 | S100 | rc_structure_vertical
3 | 2 | 2 | S110 | rc_structure_horizontal
3 | 3 | 2 | S100 | rc_structure_vertical
3 | 3 | 2 | S110 | rc_structure_horizontal