## grid_activity_list
x | y | z | major_activity | code | minor_activity
2 | 1 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 1 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 1 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 1 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 1 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 1 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 1 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 1 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 1 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 1 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 1 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 1 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 1 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 1 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 1 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 2 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 2 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 2 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 2 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 2 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 2 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 2 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 2 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 2 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 2 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 2 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 2 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 2 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 2 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 2 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 3 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 3 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 3 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 3 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 3 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 3 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 3 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 3 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 3 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 3 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 3 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 3 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 3 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 3 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 3 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 1 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 1 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 1 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 1 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 1 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 1 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 1 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 1 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 1 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 1 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 1 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 1 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 1 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 1 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 1 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 2 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 2 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 2 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 2 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 2 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 2 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 2 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 2 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 2 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 2 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 2 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 2 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 2 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 2 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 2 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 3 | -1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 3 | -1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 3 | -1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 3 | -1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 3 | -1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 3 | -1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 3 | -1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 3 | -1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 3 | -1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 3 | -1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 3 | -1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 3 | -1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 3 | -1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 3 | -1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 3 | -1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 1 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 1 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 1 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 1 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 1 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 1 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 1 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 1 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 1 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 1 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 1 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 1 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 1 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 1 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 1 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 2 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 2 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 2 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 2 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 2 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 2 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 2 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 2 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 2 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 2 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 2 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 2 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 2 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 2 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 2 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 3 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 3 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 3 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 3 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 3 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 3 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 3 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 3 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 3 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 3 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 3 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 3 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 3 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 3 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 3 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 1 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 1 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 1 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 1 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 1 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 1 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 1 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 1 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 1 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 1 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 1 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 1 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 1 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 1 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 1 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 2 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 2 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 2 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 2 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 2 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 2 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 2 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 2 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 2 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 2 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 2 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 2 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 2 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 2 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 2 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 3 | 1 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 3 | 1 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 3 | 1 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 3 | 1 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 3 | 1 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 3 | 1 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 3 | 1 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 3 | 1 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 3 | 1 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 3 | 1 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 3 | 1 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 3 | 1 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 3 | 1 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 3 | 1 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 3 | 1 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 1 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 1 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 1 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 1 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 1 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 1 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 1 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 1 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 1 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 1 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 1 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 1 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 1 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 1 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 1 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 2 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 2 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 2 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 2 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 2 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 2 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 2 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 2 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 2 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 2 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 2 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 2 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 2 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 2 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 2 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
2 | 3 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
2 | 3 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
2 | 3 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
2 | 3 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
2 | 3 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
2 | 3 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
2 | 3 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
2 | 3 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
2 | 3 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
2 | 3 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
2 | 3 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
2 | 3 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
2 | 3 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
2 | 3 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
2 | 3 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 1 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 1 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 1 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 1 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 1 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 1 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 1 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 1 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 1 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 1 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 1 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 1 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 1 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 1 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 1 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 2 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 2 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 2 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 2 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 2 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 2 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 2 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 2 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 2 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 2 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 2 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 2 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 2 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 2 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 2 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling
3 | 3 | 2 | rc_structure_vertical | S10010 | rc_structure_vertical_line_marking
3 | 3 | 2 | rc_structure_vertical | S10020 | rc_structure_vertical_re_bar
3 | 3 | 2 | rc_structure_vertical | S10030 | rc_structure_vertical_embedding
3 | 3 | 2 | rc_structure_vertical | S10040 | rc_structure_vertical_form
3 | 3 | 2 | rc_structure_vertical | S10050 | rc_structure_vertical_inspection
3 | 3 | 2 | rc_structure_vertical | S10060 | rc_structure_vertical_casting
3 | 3 | 2 | rc_structure_vertical | S10061 | rc_structure_vertical_curing
3 | 3 | 2 | rc_structure_vertical | S10070 | rc_structure_vertical_dismantling
3 | 3 | 2 | rc_structure_horizontal | S11010 | rc_structure_horizontal_form
3 | 3 | 2 | rc_structure_horizontal | S11020 | rc_structure_horizontal_re_bar
3 | 3 | 2 | rc_structure_horizontal | S11030 | rc_structure_horizontal_embedding
3 | 3 | 2 | rc_structure_horizontal | S11040 | rc_structure_horizontal_inspection
3 | 3 | 2 | rc_structure_horizontal | S11050 | rc_structure_horizontal_casting
3 | 3 | 2 | rc_structure_horizontal | S11051 | rc_structure_horizontal_curing
3 | 3 | 2 | rc_structure_horizontal | S11060 | rc_structure_horizontal_dismantling

## grid_wp_list
x | y | z | wp_code | wp_name_en
0 | 0 | 0 | M000 | milestone
1 | 1 | 1 | T100 | fence
1 | 2 | 1 | T100 | fence
1 | 3 | 1 | T100 | fence
3 | 1 | 1 | T100 | fence
3 | 2 | 1 | T100 | fence
3 | 3 | 1 | T100 | fence
2 | 1 | 1 | T100 | fence
2 | 3 | 1 | T100 | fence
1 | 2 | 1 | T300 | t-crane_installation
1 | 2 | 1 | T320 | t-crane_dismantling
1 | 3 | 1 | T350 | lift_installation
1 | 3 | 1 | T370 | lift_dismantling
1 | 1 | 1 | W100 | CIP
1 | 1 | 1 | W110 | waterblock
2 | 1 | 1 | W100 | CIP
2 | 1 | 1 | W110 | waterblock
3 | 1 | 1 | W100 | CIP
3 | 1 | 1 | W110 | waterblock
1 | 3 | 1 | W100 | CIP
1 | 3 | 1 | W110 | waterblock
2 | 3 | 1 | W100 | CIP
2 | 3 | 1 | W110 | waterblock
3 | 3 | 1 | W100 | CIP
3 | 3 | 1 | W110 | waterblock
1 | 2 | 1 | W100 | CIP
1 | 2 | 1 | W110 | waterblock
3 | 2 | 1 | W100 | CIP
3 | 2 | 1 | W110 | waterblock
3 | 3 | 1 | D100 | excavation_test
1 | 1 | 1 | D110 | excavation
2 | 1 | 1 | D110 | excavation
3 | 1 | 1 | D110 | excavation
1 | 2 | 1 | D110 | excavation
2 | 2 | 1 | D110 | excavation
3 | 2 | 1 | D110 | excavation
1 | 3 | 1 | D110 | excavation
2 | 3 | 1 | D110 | excavation
3 | 3 | 1 | D110 | excavation
1 | 1 | -1 | D110 | excavation
2 | 1 | -1 | D110 | excavation
3 | 1 | -1 | D110 | excavation
1 | 2 | -1 | D110 | excavation
2 | 2 | -1 | D110 | excavation
3 | 2 | -1 | D110 | excavation
1 | 3 | -1 | D110 | excavation
2 | 3 | -1 | D110 | excavation
3 | 3 | -1 | D110 | excavation
1 | 1 | -2 | D110 | excavation
2 | 1 | -2 | D110 | excavation
3 | 1 | -2 | D110 | excavation
1 | 2 | -2 | D110 | excavation
2 | 2 | -2 | D110 | excavation
3 | 2 | -2 | D110 | excavation
1 | 3 | -2 | D110 | excavation
2 | 3 | -2 | D110 | excavation
3 | 3 | -2 | D110 | excavation
1 | 1 | 1 | R100 | post_pile
1 | 1 | 1 | R110 | strut_installation
1 | 1 | 1 | R120 | strut_dismatling
2 | 1 | 1 | R100 | post_pile
2 | 1 | 1 | R110 | strut_installation
2 | 1 | 1 | R120 | strut_dismatling
3 | 1 | 1 | R100 | post_pile
3 | 1 | 1 | R110 | strut_installation
3 | 1 | 1 | R120 | strut_dismatling
1 | 3 | 1 | R100 | post_pile
1 | 3 | 1 | R110 | strut_installation
1 | 3 | 1 | R120 | strut_dismatling
2 | 3 | 1 | R100 | post_pile
2 | 3 | 1 | R110 | strut_installation
2 | 3 | 1 | R120 | strut_dismatling
3 | 3 | 1 | R100 | post_pile
3 | 3 | 1 | R110 | strut_installation
3 | 3 | 1 | R120 | strut_dismatling
1 | 1 | -2 | F200 | foundation
2 | 1 | -2 | F200 | foundation
3 | 1 | -2 | F200 | foundation
1 | 2 | -2 | F200 | foundation
2 | 2 | -2 | F200 | foundation
3 | 2 | -2 | F200 | foundation
1 | 3 | -2 | F200 | foundation
2 | 3 | -2 | F200 | foundation
3 | 3 | -2 | F200 | foundation
2 | 1 | -1 | S100 | rc_structure_vertical
2 | 1 | -1 | S110 | rc_structure_horizontal
2 | 2 | -1 | S100 | rc_structure_vertical
2 | 2 | -1 | S110 | rc_structure_horizontal
2 | 3 | -1 | S100 | rc_structure_vertical
2 | 3 | -1 | S110 | rc_structure_horizontal
3 | 1 | -1 | S100 | rc_structure_vertical
3 | 1 | -1 | S110 | rc_structure_horizontal
3 | 2 | -1 | S100 | rc_structure_vertical
3 | 2 | -1 | S110 | rc_structure_horizontal
3 | 3 | -1 | S100 | rc_structure_vertical
3 | 3 | -1 | S110 | rc_structure_horizontal
2 | 1 | 1 | S100 | rc_structure_vertical
2 | 1 | 1 | S110 | rc_structure_horizontal
2 | 2 | 1 | S100 | rc_structure_vertical
2 | 2 | 1 | S110 | rc_structure_horizontal
2 | 3 | 1 | S100 | rc_structure_vertical
2 | 3 | 1 | S110 | rc_structure_horizontal
3 | 1 | 1 | S100 | rc_structure_vertical
3 | 1 | 1 | S110 | rc_structure_horizontal
3 | 2 | 1 | S100 | rc_structure_vertical
3 | 2 | 1 | S110 | rc_structure_horizontal
3 | 3 | 1 | S100 | rc_structure_vertical
3 | 3 | 1 | S110 | rc_structure_horizontal
2 | 1 | 2 | S100 | rc_structure_vertical
2 | 1 | 2 | S110 | rc_structure_horizontal
2 | 2 | 2 | S100 | rc_structure_vertical
2 | 2 | 2 | S110 | rc_structure_horizontal
2 | 3 | 2 | S100 | rc_structure_vertical
2 | 3 | 2 | S110 | rc_structure_horizontal
3 | 1 | 2 | S100 | rc_structure_vertical
3 | 1 | 2 | S110 | rc_structure_horizontal
3 | 2 | 2 | S100 | rc_structure_vertical
3 | 2 | 2 | S110 | rc_structure_horizontal
3 | 3 | 2 | S100 | rc_structure_vertical
3 | 3 | 2 | S110 | rc_structure_horizontal