## 가설공사
| 대 | 중 | 타입 | 작업 |  |  |  | act_id | act_name | productivity | wp_code | id | wp_name_ko | wp_name_en | step
| 가설공사 | 가설휀스A | 1 | 기준선측량, 마킹 | T | 100 | 10 | T10010 | 가설휀스A [기준선측량, 마킹] |  | T100 | 10 |  | fence
| 가설공사 | 가설휀스A | 1 | 굴착 | T | 100 | 20 | T10020 | 가설휀스A [굴착] |  | T100 | 20
| 가설공사 | 가설휀스A | 1 | 다짐 | T | 100 | 30 | T10030 | 가설휀스A [다짐] |  | T100 | 30
| 가설공사 | 가설휀스A | 1 | 기초설치 | T | 100 | 40 | T10040 | 가설휀스A [기초설치] |  | T100 | 40
| 가설공사 | 가설휀스A | 1 | 되메우기 | T | 100 | 50 | T10050 | 가설휀스A [되메우기] |  | T100 | 50
| 가설공사 | 가설휀스A | 1 | 철골설치 | T | 100 | 60 | T10060 | 가설휀스A [철골설치] |  | T100 | 60
| 가설공사 | 가설휀스A | 1 | 판넬설치 | T | 100 | 70 | T10070 | 가설휀스A [판넬설치] |  | T100 | 70
| 가설공사 | 가설휀스A | 1 | 이미지 랩핑 | T | 100 | 80 | T10080 | 가설휀스A [이미지 랩핑] |  | T100 | 80
| 가설공사 | 가설휀스A | 1 | 검사 | T | 100 | 90 | T10090 | 가설휀스A [검사] |  | T100 | 90
미적용 | 가설공사 | 가설휀스B | 2 | 기준선측량, 마킹 | T | 110 | 10 | T11010 | 가설휀스B [기준선측량, 마킹] |  | T110 | 10
미적용 | 가설공사 | 가설휀스B | 2 | 굴착 | T | 110 | 20 | T11020 | 가설휀스B [굴착] |  | T110 | 20
미적용 | 가설공사 | 가설휀스B | 2 | 다짐 | T | 110 | 30 | T11030 | 가설휀스B [다짐] |  | T110 | 30
미적용 | 가설공사 | 가설휀스B | 2 | 기초설치 | T | 110 | 40 | T11040 | 가설휀스B [기초설치] |  | T110 | 40
미적용 | 가설공사 | 가설휀스B | 2 | 되메우기 | T | 110 | 50 | T11050 | 가설휀스B [되메우기] |  | T110 | 50
미적용 | 가설공사 | 가설휀스B | 2 | 철골설치 | T | 110 | 60 | T11060 | 가설휀스B [철골설치] |  | T110 | 60
미적용 | 가설공사 | 가설휀스B | 2 | 판넬설치 | T | 110 | 70 | T11070 | 가설휀스B [판넬설치] |  | T110 | 70
미적용 | 가설공사 | 가설휀스B | 2 | 검사 | T | 110 | 80 | T11080 | 가설휀스B [검사] |  | T110 | 80
미적용 | 가설공사 | 가설휀스C | 3 | 기준선측량, 마킹 | T | 120 | 10 | T12010 | 가설휀스C [기준선측량, 마킹] |  | T120 | 10
미적용 | 가설공사 | 가설휀스C | 3 | 굴착 | T | 120 | 20 | T12020 | 가설휀스C [굴착] |  | T120 | 20
미적용 | 가설공사 | 가설휀스C | 3 | 다짐 | T | 120 | 30 | T12030 | 가설휀스C [다짐] |  | T120 | 30
미적용 | 가설공사 | 가설휀스C | 3 | 철골설치 | T | 120 | 40 | T12040 | 가설휀스C [철골설치] |  | T120 | 40
미적용 | 가설공사 | 가설휀스C | 3 | 판넬설치 | T | 120 | 50 | T12050 | 가설휀스C [판넬설치] |  | T120 | 50
미적용 | 가설공사 | 가설휀스C | 3 | 검사 | T | 120 | 60 | T12060 | 가설휀스C [검사] |  | T120 | 60
미적용 | 가설공사 | 매직판넬 | 1 | 지반보강 | T | 200 | 10 | T20010 | 매직판넬 [지반보강] |  | T200 | 10
미적용 | 가설공사 | 매직판넬 | 1 | 기준선측량, 마킹 | T | 200 | 20 | T20020 | 매직판넬 [기준선측량, 마킹] |  | T200 | 20
미적용 | 가설공사 | 매직판넬 | 1 | 프레임설치 | T | 200 | 30 | T20030 | 매직판넬 [프레임설치] |  | T200 | 30
미적용 | 가설공사 | 매직판넬 | 1 | 판넬설치 | T | 200 | 40 | T20040 | 매직판넬 [판넬설치] |  | T200 | 40
미적용 | 가설공사 | 매직판넬 | 1 | 이미지 랩핑 | T | 200 | 50 | T20050 | 매직판넬 [이미지 랩핑] |  | T200 | 50
미적용 | 가설공사 | 매직판넬 | 1 | 검사 | T | 200 | 60 | T20060 | 매직판넬 [검사] |  | T200 | 60
| 가설공사 | 타워크레인설치 | 1 | 기초거푸집 | T | 300 | 10 | T30010 | 타워크레인설치 [기초거푸집] |  | T300 | 10
| 가설공사 | 타워크레인설치 | 1 | 기초철근 | T | 300 | 20 | T30020 | 타워크레인설치 [기초철근] |  | T300 | 20
| 가설공사 | 타워크레인설치 | 1 | 기초타설 | T | 300 | 30 | T30030 | 타워크레인설치 [기초타설] |  | T300 | 30
| 가설공사 | 타워크레인설치 | 1 | 양생1 | T | 300 | 31 | T30031 | 타워크레인설치 [양생1] |  | T300 | 31
| 가설공사 | 타워크레인설치 | 1 | 양생2 | T | 300 | 32 | T30032 | 타워크레인설치 [양생2] |  | T300 | 32
| 가설공사 | 타워크레인설치 | 1 | 양생3 | T | 300 | 33 | T30033 | 타워크레인설치 [양생3] |  | T300 | 33
| 가설공사 | 타워크레인설치 | 1 | 양생4 | T | 300 | 34 | T30034 | 타워크레인설치 [양생4] |  | T300 | 34
| 가설공사 | 타워크레인설치 | 1 | 양생5 | T | 300 | 35 | T30035 | 타워크레인설치 [양생5] |  | T300 | 35
| 가설공사 | 타워크레인설치 | 1 | 양생6 | T | 300 | 36 | T30036 | 타워크레인설치 [양생6] |  | T300 | 36
| 가설공사 | 타워크레인설치 | 1 | 설치 | T | 300 | 40 | T30040 | 타워크레인설치 [설치] |  | T300 | 40
| 가설공사 | 타워크레인설치 | 1 | 검사 | T | 300 | 50 | T30050 | 타워크레인설치 [검사] |  | T300 | 50
미적용 | 가설공사 | 타워크레인연장 | 1 | 설치,보강 | T | 310 | 10 | T31010 | 타워크레인연장 [설치,보강] |  | T310 | 10
미적용 | 가설공사 | 타워크레인연장 | 1 | 검사 | T | 310 | 20 | T31020 | 타워크레인연장 [검사] |  | T310 | 20
| 가설공사 | 타워크레인 | 1 | 해체장비설치 | T | 320 | 10 | T32010 | 타워크레인 [해체장비설치] |  | T320 | 10
| 가설공사 | 타워크레인 | 1 | 해체 | T | 320 | 20 | T32020 | 타워크레인 [해체] |  | T320 | 20
| 가설공사 | 리프트카설치 | 1 | 기초거푸집 | T | 350 | 10 | T35010 | 리프트카설치 [기초거푸집] |  | T350 | 10
| 가설공사 | 리프트카설치 | 1 | 기초철근 | T | 350 | 20 | T35020 | 리프트카설치 [기초철근] |  | T350 | 20
| 가설공사 | 리프트카설치 | 1 | 기초타설 | T | 350 | 30 | T35030 | 리프트카설치 [기초타설] |  | T350 | 30
| 가설공사 | 리프트카설치 | 1 | 양생1 | T | 350 | 31 | T35031 | 리프트카설치 [양생1] |  | T350 | 31
| 가설공사 | 리프트카설치 | 1 | 양생2 | T | 350 | 32 | T35032 | 리프트카설치 [양생2] |  | T350 | 32
| 가설공사 | 리프트카설치 | 1 | 양생3 | T | 350 | 33 | T35033 | 리프트카설치 [양생3] |  | T350 | 33
| 가설공사 | 리프트카설치 | 1 | 양생4 | T | 350 | 34 | T35034 | 리프트카설치 [양생4] |  | T350 | 34
| 가설공사 | 리프트카설치 | 1 | 양생5 | T | 350 | 35 | T35035 | 리프트카설치 [양생5] |  | T350 | 35
| 가설공사 | 리프트카설치 | 1 | 양생6 | T | 350 | 36 | T35036 | 리프트카설치 [양생6] |  | T350 | 36
| 가설공사 | 리프트카설치 | 1 | 설치 | T | 350 | 40 | T35040 | 리프트카설치 [설치] |  | T350 | 40
| 가설공사 | 리프트카설치 | 1 | 검사 | T | 350 | 50 | T35050 | 리프트카설치 [검사] |  | T350 | 50
미적용 | 가설공사 | 리프트카연장 | 1 | 설치,보강 | T | 360 | 10 | T36010 | 리프트카연장 [설치,보강] |  | T360 | 10
미적용 | 가설공사 | 리프트카연장 | 1 | 검사 | T | 360 | 10 | T36010 | 리프트카연장 [검사] |  | T360 | 10
| 가설공사 | 리프트카 | 1 | 해체 | T | 370 | 10 | T37010 | 리프트카 [해체] |  | T370 | 10

## 흙막이토공사
| 대 | 중 | 타입 | 작업 |  |  |  | act_id | act_name | productivity | wp_code | id | wp_name_ko | wp_name_en | step
| 흙막이공사 | CIP공사 | 1 | 기준선측량, 마킹 | W | 100 | #REF! | #REF! | CIP공사 [기준선측량, 마킹] |  | W100 | 10
| 흙막이공사 | CIP공사 | 1 | 가이드빔설치 | W | 100 | #REF! | #REF! | CIP공사 [가이드빔설치] |  | W100 | 20
| 흙막이공사 | CIP공사 | 1 | 지반보강 | W | 100 | #REF! | #REF! | CIP공사 [지반보강] |  | W100 | 30
| 흙막이공사 | CIP공사 | 1 | 굴착, 철근망, 철골삽입 | W | 100 | #REF! | #REF! | CIP공사 [굴착, 철근망, 철골삽입] |  | W100 | 40
| 흙막이공사 | CIP공사 | 1 | CIP타설 | W | 100 | #REF! | #REF! | CIP공사 [CIP타설] |  | W100 | 50
| 흙막이공사 | CIP공사 | 1 | 캡빔 배근 | W | 100 | #REF! | #REF! | CIP공사 [캡빔 배근] |  | W100 | 60
| 흙막이공사 | CIP공사 | 1 | 캡빔타설 | W | 100 | #REF! | #REF! | CIP공사 [캡빔타설] |  | W100 | 70
| 흙막이공사 | 차수공사 | 1 | 기준선측량, 마킹 | W | 110 | 10 | W11010 | 차수공사 [기준선측량, 마킹] |  | W110 | 10
| 흙막이공사 | 차수공사 | 1 | 굴착, 배관삽입 | W | 110 | 20 | W11020 | 차수공사 [굴착, 배관삽입] |  | W110 | 20
| 흙막이공사 | 차수공사 | 1 | 차수재주입 | W | 110 | 30 | W11030 | 차수공사 [차수재주입] |  | W110 | 30
| 흙막이공사 | 차수공사 | 1 | 정리 | W | 110 | 40 | W11040 | 차수공사 [정리] |  | W110 | 40
| 토공사 | 시험굴착 | 1 | 계획수립 | D | 100 | 10 | D10010 | 시험굴착 [계획수립] |  | D100 | 10
| 토공사 | 시험굴착 | 1 | 굴착 | D | 100 | 20 | D10020 | 시험굴착 [굴착] |  | D100 | 20
| 토공사 | 시험굴착 | 1 | 검사 | D | 100 | 30 | D10030 | 시험굴착 [검사] |  | D100 | 30
| 토공사 | 굴착공사 | 1 | 장비굴착 | D | 110 | 10 | D11010 | 굴착공사 [장비굴착] |  | D110 | 10
미적용 | 토공사 | 발파굴착공사 | 1 | 계획수립 | D | 120 | 10 | D12010 | 발파굴착공사 [계획수립] |  | D120 | 10
미적용 | 토공사 | 발파굴착공사 | 1 | 천공 | D | 120 | 20 | D12020 | 발파굴착공사 [천공] |  | D120 | 20
미적용 | 토공사 | 발파굴착공사 | 1 | 장약설치, 덮개설치, 발파 | D | 120 | 30 | D12030 | 발파굴착공사 [장약설치, 덮개설치, 발파] |  | D120 | 30
미적용 | 토공사 | 발파굴착공사 | 1 | 굴착 | D | 120 | 40 | D12040 | 발파굴착공사 [굴착] |  | D120 | 40
미적용 | 토공사 | 토사반출A | 1 | 직상차 | D | 130 | 10 | D13010 | 토사반출A [직상차] |  | D130 | 10
미적용 | 토공사 | 토사반출B | 2 | 크람쉐상차 | D | 140 | 10 | D14010 | 토사반출B [크람쉐상차] |  | D140 | 10
| 흙막이지지공사 | 지지말뚝공사 | 1 | 기준선측량, 마킹 | R | 100 | 10 | R10010 | 지지말뚝공사 [기준선측량, 마킹] |  | R100 | 10
| 흙막이지지공사 | 지지말뚝공사 | 1 | 포스트파일설치 | R | 100 | 20 | R10020 | 지지말뚝공사 [포스트파일설치] |  | R100 | 20
| 흙막이지지공사 | 스트러트설치 | 1 | Wale설치 | R | 110 | 10 | R11010 | 스트러트설치 [Wale설치] |  | R110 | 10
| 흙막이지지공사 | 스트러트설치 | 1 | 스트러트설치 | R | 110 | 20 | R11020 | 스트러트설치 [스트러트설치] |  | R110 | 20
| 흙막이지지공사 | 스트러트설치 | 1 | 검사 | R | 110 | 30 | R11030 | 스트러트설치 [검사] |  | R110 | 30
| 흙막이지지공사 | 스트러트해체 | 1 | 안전성확인 | R | 120 | 10 | R12010 | 스트러트해체 [안전성확인] |  | R120 | 10
| 흙막이지지공사 | 스트러트해체 | 1 | 해체 | R | 120 | 20 | R12020 | 스트러트해체 [해체] |  | R120 | 20

## 골조공사
| 대 | 중 | 타입 | 작업 |  |  |  | act_id | act_name | productivity | wp_code | id | wp_name_ko | wp_name_en | step
샘플미적용 | 기초공사 | PHC파일공사 | 1 | 기준선측량, 마킹 | F | 100 | 10 | F10010 | PHC파일공사 [기준선측량, 마킹] | 10 | F100 | 10
샘플미적용 | 기초공사 | PHC파일공사 | 1 | 천공&파일근입 | F | 100 | 20 | F10020 | PHC파일공사 [천공&파일근입] | 2 | F100 | 20
샘플미적용 | 기초공사 | PHC파일공사 | 1 | 사춤 | F | 100 | 30 | F10030 | PHC파일공사 [사춤] | 2 | F100 | 30
샘플미적용 | 기초공사 | PHC파일공사 | 1 | 굴착 | F | 100 | 40 | F10040 | PHC파일공사 [굴착] | 3 | F100 | 40
샘플미적용 | 기초공사 | PHC파일공사 | 1 | 파일두부정리 | F | 100 | 50 | F10050 | PHC파일공사 [파일두부정리] | 3 | F100 | 50
샘플미적용 | 기초공사 | 치환지반보강공사 | 1 | 굴착 | F | 110 | 10 | F11010 | 치환지반보강공사 [굴착] |  | F110 | 10
샘플미적용 | 기초공사 | 치환지반보강공사 | 1 | 치환, 다짐 | F | 110 | 20 | F11020 | 치환지반보강공사 [치환, 다짐] |  | F110 | 20
샘플미적용 | 기초공사 | PF기초공사 | 1 | 기준선측량, 마킹 | F | 120 | 10 | F12010 | PF기초공사 [기준선측량, 마킹] |  | F120 | 10
샘플미적용 | 기초공사 | PF기초공사 | 1 | 구근형성 | F | 120 | 20 | F12020 | PF기초공사 [구근형성] |  | F120 | 20
샘플미적용 | 기초공사 | PF기초공사 | 1 | 양생 | F | 120 | 30 | F12030 | PF기초공사 [양생] |  | F120 | 30
미적용 | 기초공사 | 지내력기초 | 1 | 굴착 | F | 130 | 10 | F13010 | 지내력기초 [굴착] |  | F130 | 10
미적용 | 기초공사 | 지내력기초 | 1 | 지내력검사 | F | 130 | 20 | F13020 | 지내력기초 [지내력검사] |  | F130 | 20
미적용 | 기초공사 | 배수드레인공사 | 1 | 기준선측량, 마킹 | F | 140 | 10 | F14010 | 배수드레인공사 [기준선측량, 마킹] |  | F140 | 10
미적용 | 기초공사 | 배수드레인공사 | 1 | 드레인설치 | F | 140 | 20 | F14020 | 배수드레인공사 [드레인설치] |  | F140 | 20
미적용 | 기초공사 | 배수드레인공사 | 1 | 자갈포설 | F | 140 | 30 | F14030 | 배수드레인공사 [자갈포설] |  | F140 | 30
| 기초공사 | 기초판 공사 | 1 | 방습층설치, 버림타설 | F | 200 | 10 | F20010 | 기초판 공사 [방습층설치, 버림타설] | 4 | F200 | 10 | 기초판 공사 | foundation | vapor_proof&lean_conc.
| 기초공사 | 기초판 공사 | 1 | 측량, 먹놓기 | F | 200 | 20 | F20020 | 기초판 공사 [측량, 먹놓기] | 4 | F200 | 20 | 기초판 공사 | foundation | line_marking
| 기초공사 | 기초판 공사 | 1 | 철근설치 | F | 200 | 30 | F20030 | 기초판 공사 [철근설치] | 2 | F200 | 30 | 기초판 공사 | foundation | re-bar
| 기초공사 | 기초판 공사 | 1 | 거푸집설치 | F | 200 | 40 | F20040 | 기초판 공사 [거푸집설치] | 2 | F200 | 40 | 기초판 공사 | foundation | form
| 기초공사 | 기초판 공사 | 1 | 레미콘타설 | F | 200 | 50 | F20050 | 기초판 공사 [레미콘타설] | 3 | F200 | 50 | 기초판 공사 | foundation | casting
| 기초공사 | 기초판 공사 | 1 | 양생 | F | 200 | 51 | F20051 | 기초판 공사 [양생] | 3 | F200 | 51 | 기초판 공사 | foundation | curing
| 기초공사 | 기초판 공사 | 1 | 거푸집해체 | F | 200 | 60 | F20060 | 기초판 공사 [거푸집해체] | 3 | F200 | 60 | 기초판 공사 | foundation | dismantling
| 기초공사 | 기초판 공사 | 1 | 되메우기 | F | 200 | 70 | F20070 | 기초판 공사 [되메우기] | 5 | F200 | 70 | 기초판 공사 | foundation | backfill
| 골조공사 | 철콘골조공사(수직) | 1 | 측량, 먹놓기 | S | 100 | 10 | S10010 | 철콘골조공사(수직) [측량, 먹놓기] | 5 | S100 | 10 | 철콘골조공사(수직) | rc_structure_vertical | line_marking
| 골조공사 | 철콘골조공사(수직) | 1 | 철근설치 | S | 100 | 20 | S10020 | 철콘골조공사(수직) [철근설치] | 3 | S100 | 20 | 철콘골조공사(수직) | rc_structure_vertical | re-bar
| 골조공사 | 철콘골조공사(수직) | 1 | 매입물설치 | S | 100 | 30 | S10030 | 철콘골조공사(수직) [매입물설치] | 3 | S100 | 30 | 철콘골조공사(수직) | rc_structure_vertical | embedding
| 골조공사 | 철콘골조공사(수직) | 1 | 거푸집설치 | S | 100 | 40 | S10040 | 철콘골조공사(수직) [거푸집설치] | 3 | S100 | 40 | 철콘골조공사(수직) | rc_structure_vertical | form
| 골조공사 | 철콘골조공사(수직) | 1 | 검측 | S | 100 | 50 | S10050 | 철콘골조공사(수직) [검측] | 5 | S100 | 50 | 철콘골조공사(수직) | rc_structure_vertical | inspection
| 골조공사 | 철콘골조공사(수직) | 1 | 레미콘타설 | S | 100 | 60 | S10060 | 철콘골조공사(수직) [레미콘타설] | 5 | S100 | 60 | 철콘골조공사(수직) | rc_structure_vertical | casting
| 골조공사 | 철콘골조공사(수직) | 1 | 양생 | S | 100 | 61 | S10061 | 철콘골조공사(수직) [양생] | 5 | S100 | 61 | 철콘골조공사(수직) | rc_structure_vertical | curing
| 골조공사 | 철콘골조공사(수직) | 1 | 거푸집해체 | S | 100 | 70 | S10070 | 철콘골조공사(수직) [거푸집해체] | 3 | S100 | 70 | 철콘골조공사(수직) | rc_structure_vertical | dismantling
| 골조공사 | 철콘골조공사(수평) | 1 | 거푸집설치 | S | 110 | 10 | S11010 | 철콘골조공사(수평) [거푸집설치] | 2 | S110 | 10 | 철콘골조공사(수평) | rc_structure_horizontal | form
| 골조공사 | 철콘골조공사(수평) | 1 | 철근설치 | S | 110 | 20 | S11020 | 철콘골조공사(수평) [철근설치] | 3 | S110 | 20 | 철콘골조공사(수평) | rc_structure_horizontal | re-bar
| 골조공사 | 철콘골조공사(수평) | 1 | 매입물설치 | S | 110 | 30 | S11030 | 철콘골조공사(수평) [매입물설치] | 3 | S110 | 30 | 철콘골조공사(수평) | rc_structure_horizontal | embedding
| 골조공사 | 철콘골조공사(수평) | 1 | 검측 | S | 110 | 40 | S11040 | 철콘골조공사(수평) [검측] | 5 | S110 | 40 | 철콘골조공사(수평) | rc_structure_horizontal | inspection
| 골조공사 | 철콘골조공사(수평) | 1 | 레미콘타설 | S | 110 | 50 | S11050 | 철콘골조공사(수평) [레미콘타설] | 5 | S110 | 50 | 철콘골조공사(수평) | rc_structure_horizontal | casting
| 골조공사 | 철콘골조공사(수평) | 1 | 양생 | S | 110 | 51 | S11051 | 철콘골조공사(수평) [양생] | 5 | S110 | 51 | 철콘골조공사(수평) | rc_structure_horizontal | curing
| 골조공사 | 철콘골조공사(수평) | 1 | 거푸집해체 | S | 110 | 60 | S11060 | 철콘골조공사(수평) [거푸집해체] | 3 | S110 | 60 | 철콘골조공사(수평) | rc_structure_horizontal | dismantling
샘플미적용 | 골조공사 | PC골조공사(수직) | 1 | 측량, 먹놓기 | S | 200 | 10 | S20010 | PC골조공사(수직) [측량, 먹놓기] |  | S200 | 10
샘플미적용 | 골조공사 | PC골조공사(수직) | 1 | 앵커조정 | S | 200 | 20 | S20020 | PC골조공사(수직) [앵커조정] |  | S200 | 20
샘플미적용 | 골조공사 | PC골조공사(수직) | 1 | PC세우기 | S | 200 | 30 | S20030 | PC골조공사(수직) [PC세우기] |  | S200 | 30
샘플미적용 | 골조공사 | PC골조공사(수직) | 1 | 고정 | S | 200 | 40 | S20040 | PC골조공사(수직) [고정] |  | S200 | 40
샘플미적용 | 골조공사 | PC골조공사(수직) | 1 | 검측 | S | 200 | 50 | S20050 | PC골조공사(수직) [검측] |  | S200 | 50
샘플미적용 | 골조공사 | PC골조공사(수직) | 1 | 그라우팅 | S | 200 | 60 | S20060 | PC골조공사(수직) [그라우팅] |  | S200 | 60
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 보PC설치 | S | 210 | 10 | S21010 | PC골조공사(수평) [보PC설치] |  | S210 | 10
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 고정철물설치 | S | 210 | 20 | S21020 | PC골조공사(수평) [고정철물설치] |  | S210 | 20
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 슬래브PC설치 | S | 210 | 30 | S21030 | PC골조공사(수평) [슬래브PC설치] |  | S210 | 30
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 연결철근설치 | S | 210 | 40 | S21040 | PC골조공사(수평) [연결철근설치] |  | S210 | 40
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 채움콘크리트, 그라우팅타설 | S | 210 | 50 | S21050 | PC골조공사(수평) [채움콘크리트, 그라우팅타설] |  | S210 | 50
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 철근설치 | S | 210 | 60 | S21060 | PC골조공사(수평) [철근설치] |  | S210 | 60
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 레미콘타설 | S | 210 | 70 | S21070 | PC골조공사(수평) [레미콘타설] |  | S210 | 70
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 바닥미장 | S | 210 | 80 | S21080 | PC골조공사(수평) [바닥미장] |  | S210 | 80
샘플미적용 | 골조공사 | PC골조공사(수평) | 1 | 양생 | S | 210 | 90 | S21090 | PC골조공사(수평) [양생] |  | S210 | 90
샘플미적용 | 골조공사 | 바닥미장A | 1 | 거푸집설치 | S | 220 | 10 | S22010 | 바닥미장A [거푸집설치] |  | S220 | 10
샘플미적용 | 골조공사 | 바닥미장A | 1 | 레미콘타설 | S | 220 | 20 | S22020 | 바닥미장A [레미콘타설] |  | S220 | 20
샘플미적용 | 골조공사 | 바닥미장A | 1 | 바닥미장 | S | 220 | 30 | S22030 | 바닥미장A [바닥미장] |  | S220 | 30
샘플미적용 | 골조공사 | 바닥미장A | 1 | 하드너작업 | S | 220 | 40 | S22040 | 바닥미장A [하드너작업] |  | S220 | 40
샘플미적용 | 골조공사 | 바닥미장A | 1 | 평탄도, 마모도검사 | S | 220 | 50 | S22050 | 바닥미장A [평탄도, 마모도검사] |  | S220 | 50
샘플미적용 | 골조공사 | 바닥미장B | 2 | 하드너작업 | S | 230 | 10 | S23010 | 바닥미장B [하드너작업] |  | S230 | 10
샘플미적용 | 골조공사 | 바닥미장B | 2 | 평탄도, 마모도검사 | S | 230 | 20 | S23020 | 바닥미장B [평탄도, 마모도검사] |  | S230 | 20
샘플미적용 | 골조공사 | 철골조공사 | 1 | 측량, 먹놓기 | S | 300 | 10 | S30010 | 철골조공사 [측량, 먹놓기] |  | S300 | 10
샘플미적용 | 골조공사 | 철골조공사 | 1 | 철골세우기 | S | 300 | 20 | S30020 | 철골조공사 [철골세우기] |  | S300 | 20
샘플미적용 | 골조공사 | 철골조공사 | 1 | 보설치 | S | 300 | 30 | S30030 | 철골조공사 [보설치] |  | S300 | 30
샘플미적용 | 골조공사 | 철골조공사 | 1 | 본조립 | S | 300 | 40 | S30040 | 철골조공사 [본조립] |  | S300 | 40
샘플미적용 | 골조공사 | 철골조공사 | 1 | 검측 | S | 300 | 50 | S30050 | 철골조공사 [검측] |  | S300 | 50
샘플미적용 | 골조공사 | 데크슬래브공사 | 1 | 데크설치, 고정 | S | 310 | 10 | S31010 | 데크슬래브공사 [데크설치, 고정] |  | S310 | 10
샘플미적용 | 골조공사 | 데크슬래브공사 | 1 | 스터드앵커 설치 | S | 310 | 20 | S31020 | 데크슬래브공사 [스터드앵커 설치] |  | S310 | 20
샘플미적용 | 골조공사 | 데크슬래브공사 | 1 | 슬래브배근 | S | 310 | 30 | S31030 | 데크슬래브공사 [슬래브배근] |  | S310 | 30
샘플미적용 | 골조공사 | 데크슬래브공사 | 1 | 레미콘타설 | S | 310 | 40 | S31040 | 데크슬래브공사 [레미콘타설] |  | S310 | 40
샘플미적용 | 골조공사 | 데크슬래브공사 | 1 | 양생 | S | 310 | 50 | S31050 | 데크슬래브공사 [양생] |  | S310 | 50
샘플미적용 | 골조공사 | 내화뿜칠 | 1 | 바탕면 정리, 고정핀설치, 보양 | S | 320 | 10 | S32010 | 내화뿜칠 [바탕면 정리, 고정핀설치, 보양] |  | S320 | 10
샘플미적용 | 골조공사 | 내화뿜칠 | 1 | 뿜칠 | S | 320 | 20 | S32020 | 내화뿜칠 [뿜칠] |  | S320 | 20
샘플미적용 | 골조공사 | 내화뿜칠 | 1 | 검측 | S | 320 | 30 | S32030 | 내화뿜칠 [검측] |  | S320 | 30
샘플미적용 | 골조공사 | 내화도장 | 1 | 바탕면 정리 | S | 330 | 10 | S33010 | 내화도장 [바탕면 정리] |  | S330 | 10
샘플미적용 | 골조공사 | 내화도장 | 1 | 도장1차 | S | 330 | 20 | S33020 | 내화도장 [도장1차] |  | S330 | 20
샘플미적용 | 골조공사 | 내화도장 | 1 | 도장2차 | S | 330 | 30 | S33030 | 내화도장 [도장2차] |  | S330 | 30
샘플미적용 | 골조공사 | 내화도장 | 1 | 도장3차 | S | 330 | 40 | S33040 | 내화도장 [도장3차] |  | S330 | 40

## 마감작업
층 |  | 실 |  | 작업코드 | 작업명 | ID | 작업명 | 생산성 | 구역수 | 기간 | WBS Code
1층 | 1 | 코어 | O | A41510 | 기준먹메김 | 1CA41510 | 1층 - 코어 - 기준먹메김 | 2 | 6 | 3 | P.N.1.O | A415
1층 | 1 | 코어 | O | A44510 | 조적시공 [운반작업] | 1CA44510 | 1층 - 코어 - 조적시공 [운반작업] | 2 | 6 | 3 | P.N.1.O | A445
1층 | 1 | 코어 | O | A44520 | 조적시공 [조적1차] | 1CA44520 | 1층 - 코어 - 조적시공 [조적1차] | 1 | 6 | 6 | P.N.1.O | A445
1층 | 1 | 코어 | O | A44521 | 조적시공 [조적2차] | 1CA44521 | 1층 - 코어 - 조적시공 [조적2차] | 1 | 6 | 6 | P.N.1.O | A445
1층 | 1 | 코어 | O | A45010 | 미장공사 [바탕면처리] | 1CA45010 | 1층 - 코어 - 미장공사 [바탕면처리] | 2 | 6 | 3 | P.N.1.O | A450
1층 | 1 | 코어 | O | A45011 | 미장공사 [미장 초벌] | 1CA45011 | 1층 - 코어 - 미장공사 [미장 초벌] | 1 | 6 | 6 | P.N.1.O | A450
1층 | 1 | 코어 | O | A45012 | 미장공사 [미장 정벌] | 1CA45012 | 1층 - 코어 - 미장공사 [미장 정벌] | 1 | 6 | 6 | P.N.1.O | A450
1층 | 1 | 코어 | O | A48510 | 석고보드 벽공사 [먹놓기] | 1CA48510 | 1층 - 코어 - 석고보드 벽공사 [먹놓기] | 2 | 6 | 3 | P.N.1.O | A485
1층 | 1 | 코어 | O | A48520 | 석고보드 벽공사 [스터드] | 1CA48520 | 1층 - 코어 - 석고보드 벽공사 [스터드] | 1 | 6 | 6 | P.N.1.O | A485
1층 | 1 | 코어 | O | A48530 | 석고보드 벽공사 [석고보드시공] | 1CA48530 | 1층 - 코어 - 석고보드 벽공사 [석고보드시공] | 1 | 6 | 6 | P.N.1.O | A485
1층 | 1 | 코어 | O | A50510 | 천정틀시공 [행거설치] | 1CA50510 | 1층 - 코어 - 천정틀시공 [행거설치] | 1 | 6 | 6 | P.N.1.O | A505
1층 | 1 | 코어 | O | A50520 | 천정틀시공 [틀설치] | 1CA50520 | 1층 - 코어 - 천정틀시공 [틀설치] | 1 | 6 | 6 | P.N.1.O | A505
1층 | 1 | 코어 | O | A51010 | 석고보드 천정공사 [석고보드시공] | 1CA51010 | 1층 - 코어 - 석고보드 천정공사 [석고보드시공] | 1 | 6 | 6 | P.N.1.O | A510
1층 | 1 | 코어 | O | A52010 | 그릴설치 [설치] | 1CA52010 | 1층 - 코어 - 그릴설치 [설치] | 1 | 6 | 6 | P.N.1.O | A520
1층 | 1 | 코어 | O | A52510 | 공용부창호설치 [창틀설치] | 1CA52510 | 1층 - 코어 - 공용부창호설치 [창틀설치] | 1 | 6 | 6 | P.N.1.O | A525
1층 | 1 | 코어 | O | A52520 | 공용부창호설치 [우레탄충진] | 1CA52520 | 1층 - 코어 - 공용부창호설치 [우레탄충진] | 1 | 6 | 6 | P.N.1.O | A525
1층 | 1 | 코어 | O | A52530 | 공용부창호설치 [창설치] | 1CA52530 | 1층 - 코어 - 공용부창호설치 [창설치] | 1 | 6 | 6 | P.N.1.O | A525
1층 | 1 | 코어 | O | A53010 | 공용부문설치 [문틀설치] | 1CA53010 | 1층 - 코어 - 공용부문설치 [문틀설치] | 1 | 6 | 6 | P.N.1.O | A530
1층 | 1 | 코어 | O | A53020 | 공용부문설치 [문짝설치] | 1CA53020 | 1층 - 코어 - 공용부문설치 [문짝설치] | 1 | 6 | 6 | P.N.1.O | A530
1층 | 1 | 코어 | O | A55010 | 석재시공 | 1CA55010 | 1층 - 코어 - 석재시공 | 1 | 6 | 6 | P.N.1.O | A550
1층 | 1 | 코어 | O | A57510 | 실내벽도장 [바탕면처리] | 1CA57510 | 1층 - 코어 - 실내벽도장 [바탕면처리] | 2 | 6 | 3 | P.N.1.O | A575
1층 | 1 | 코어 | O | A57520 | 실내벽도장 [도장] | 1CA57520 | 1층 - 코어 - 실내벽도장 [도장] | 1 | 6 | 6 | P.N.1.O | A575
1층 | 1 | 코어 | O | A57530 | 실내벽도장 [마감도장] | 1CA57530 | 1층 - 코어 - 실내벽도장 [마감도장] | 1 | 6 | 6 | P.N.1.O | A575
1층 | 1 | 코어 | O | A58010 | 유리설치 [설치] | 1CA58010 | 1층 - 코어 - 유리설치 [설치] | 1 | 6 | 6 | P.N.1.O | A580
1층 | 1 | 코어 | O | A59010 | 실내천정도장 [바탕면처리] | 1CA59010 | 1층 - 코어 - 실내천정도장 [바탕면처리] | 1 | 6 | 6 | P.N.1.O | A590
1층 | 1 | 코어 | O | A59020 | 실내천정도장 [도장] | 1CA59020 | 1층 - 코어 - 실내천정도장 [도장] | 1 | 6 | 6 | P.N.1.O | A590
1층 | 1 | 코어 | O | A59030 | 실내천정도장 [마감도장] | 1CA59030 | 1층 - 코어 - 실내천정도장 [마감도장] | 1 | 6 | 6 | P.N.1.O | A590
1층 | 1 | 코어 | O | A59510 | 계단실 텍스 천정공사 [천정설치] | 1CA59510 | 1층 - 코어 - 계단실 텍스 천정공사 [천정설치] | 1 | 6 | 6 | P.N.1.O | A595
1층 | 1 | 코어 | O | A60510 | 실내바닥도장(에폭시) [바탕면처리] | 1CA60510 | 1층 - 코어 - 실내바닥도장(에폭시) [바탕면처리] | 1 | 6 | 6 | P.N.1.O | A605
1층 | 1 | 코어 | O | A60520 | 실내바닥도장(에폭시) [도장] | 1CA60520 | 1층 - 코어 - 실내바닥도장(에폭시) [도장] | 1 | 6 | 6 | P.N.1.O | A605
1층 | 1 | 코어 | O | A60530 | 실내바닥도장 [마감도장] | 1CA60530 | 1층 - 코어 - 실내바닥도장 [마감도장] | 1 | 6 | 6 | P.N.1.O | A605
1층 | 1 | 코어 | O | A61010 | 계단실 비닐타일 [바탕면처리] | 1CA61010 | 1층 - 코어 - 계단실 비닐타일 [바탕면처리] | 1 | 6 | 6 | P.N.1.O | A610
1층 | 1 | 코어 | O | A61020 | 계단실 비닐타일 [타일시공] | 1CA61020 | 1층 - 코어 - 계단실 비닐타일 [타일시공] | 1 | 6 | 6 | P.N.1.O | A610
1층 | 1 | 코어 | O | A62510 | 걸레받이시공 [걸레받이설치] | 1CA62510 | 1층 - 코어 - 걸레받이시공 [걸레받이설치] | 2 | 6 | 3 | P.N.1.O | A625
1층 | 1 | 코어 | O | A64010 | 계단잡철물공사 [설치] | 1CA64010 | 1층 - 코어 - 계단잡철물공사 [설치] | 1 | 6 | 6 | P.N.1.O | A640
1층 | 1 | 코어 | O | A68010 | 사인공사 | 1CA68010 | 1층 - 코어 - 사인공사 | 2 | 6 | 3 | P.N.1.O | A680
1층 | 1 | 로비 | O | A41510 | 기준먹메김 | 1LA41510 | 1층 - 로비 - 기준먹메김 | 2 | 6 | 3 | P.N.1.O | A415
1층 | 1 | 로비 | O | A48510 | 석고보드 벽공사 [먹놓기] | 1LA48510 | 1층 - 로비 - 석고보드 벽공사 [먹놓기] | 2 | 6 | 3 | P.N.1.O | A485
1층 | 1 | 로비 | O | A48520 | 석고보드 벽공사 [스터드] | 1LA48520 | 1층 - 로비 - 석고보드 벽공사 [스터드] | 1 | 6 | 6 | P.N.1.O | A485
1층 | 1 | 로비 | O | A48530 | 석고보드 벽공사 [석고보드시공] | 1LA48530 | 1층 - 로비 - 석고보드 벽공사 [석고보드시공] | 1 | 6 | 6 | P.N.1.O | A485
1층 | 1 | 로비 | T | A50510 | 천정틀시공 [행거설치] | 1LA50510 | 1층 - 로비 - 천정틀시공 [행거설치] | 1 |  | 1 | P.N.1.T | A505
1층 | 1 | 로비 | T | A50520 | 천정틀시공 [틀설치] | 1LA50520 | 1층 - 로비 - 천정틀시공 [틀설치] | 1 |  | 1 | P.N.1.T | A505
1층 | 1 | 로비 | T | A52510 | 공용부창호설치 [창틀설치] | 1LA52510 | 1층 - 로비 - 공용부창호설치 [창틀설치] | 1 |  | 1 | P.N.1.T | A525
1층 | 1 | 로비 | T | A52520 | 공용부창호설치 [우레탄충진] | 1LA52520 | 1층 - 로비 - 공용부창호설치 [우레탄충진] | 1 |  | 1 | P.N.1.T | A525
1층 | 1 | 로비 | T | A52530 | 공용부창호설치 [창설치] | 1LA52530 | 1층 - 로비 - 공용부창호설치 [창설치] | 1 |  | 1 | P.N.1.T | A525
1층 | 1 | 로비 | T | A54010 | 유리문설치 [바탕면정리] | 1LA54010 | 1층 - 로비 - 유리문설치 [바탕면정리] | 1 |  | 1 | P.N.1.T | A540
1층 | 1 | 로비 | T | A54020 | 유리문설치 [하드웨어설치] | 1LA54020 | 1층 - 로비 - 유리문설치 [하드웨어설치] | 1 |  | 1 | P.N.1.T | A540
1층 | 1 | 로비 | T | A54030 | 유리문설치 [문설치] | 1LA54030 | 1층 - 로비 - 유리문설치 [문설치] | 1 |  | 1 | P.N.1.T | A540
1층 | 1 | 로비 | T | A55010 | 석재시공 | 1LA55010 | 1층 - 로비 - 석재시공 | 1 |  | 1 | P.N.1.T | A550
1층 | 1 | 로비 | T | A57510 | 실내벽도장 [바탕면처리] | 1LA57510 | 1층 - 로비 - 실내벽도장 [바탕면처리] | 2 |  | 1 | P.N.1.T | A575
1층 | 1 | 로비 | T | A57520 | 실내벽도장 [도장] | 1LA57520 | 1층 - 로비 - 실내벽도장 [도장] | 1 |  | 1 | P.N.1.T | A575
1층 | 1 | 로비 | T | A57530 | 실내벽도장 [마감도장] | 1LA57530 | 1층 - 로비 - 실내벽도장 [마감도장] | 1 |  | 1 | P.N.1.T | A575
1층 | 1 | 로비 | T | A58010 | 유리설치 [설치] | 1LA58010 | 1층 - 로비 - 유리설치 [설치] | 1 |  | 1 | P.N.1.T | A580
1층 | 1 | 로비 | T | A60020 | 바리솔, 루버 천장시공 [천정설치] | 1LA60020 | 1층 - 로비 - 바리솔, 루버 천장시공 [천정설치] | 1 |  | 1 | P.N.1.T | A600
1층 | 1 | 로비 | T | A62510 | 걸레받이시공 [걸레받이설치] | 1LA62510 | 1층 - 로비 - 걸레받이시공 [걸레받이설치] | 2 |  | 1 | P.N.1.T | A625
1층 | 1 | 로비 | T | A67010 | 가구공사 | 1LA67010 | 1층 - 로비 - 가구공사 | 1 |  | 1 | P.N.1.T | A670
1층 | 1 | 로비 | T | A68010 | 사인공사 | 1LA68010 | 1층 - 로비 - 사인공사 | 2 |  | 1 | P.N.1.T | A680
1층 | 1 | 오피스 | T | A41510 | 기준먹메김 | 1OA41510 | 1층 - 오피스 - 기준먹메김 | 2 |  | 1 | P.N.1.T | A415
1층 | 1 | 오피스 | T | A41810 | 비닐타일 [타일시공] | 1OA41810 | 1층 - 오피스 - 비닐타일 [타일시공] | 1 |  | 1 | P.N.1.T | A418
1층 | 1 | 오피스 | T | A43010 | 무근타설 [레벨작업] | 1OA43010 | 1층 - 오피스 - 무근타설 [레벨작업] | 2 |  | 1 | P.N.1.T | A430
1층 | 1 | 오피스 | T | A43020 | 무근타설 [무근타설] | 1OA43020 | 1층 - 오피스 - 무근타설 [무근타설] | 2 |  | 1 | P.N.1.T | A430
1층 | 1 | 오피스 | T | A43021 | 무근타설 [바닥미장, 양생] | 1OA43021 | 1층 - 오피스 - 무근타설 [바닥미장, 양생] | 2 |  | 1 | P.N.1.T | A430
1층 | 1 | 오피스 | T | A43022 | 무근타설 [양생] | 1OA43022 | 1층 - 오피스 - 무근타설 [양생] | 2 |  | 1 | P.N.1.T | A430
1층 | 1 | 오피스 | T | A45510 | 단열벽공사 [바탕면처리] | 1OA45510 | 1층 - 오피스 - 단열벽공사 [바탕면처리] | 2 |  | 1 | P.N.1.T | A455
1층 | 1 | 오피스 | T | A45520 | 단열벽공사 [단열재설치] | 1OA45520 | 1층 - 오피스 - 단열벽공사 [단열재설치] | 1 |  | 1 | P.N.1.T | A455
1층 | 1 | 오피스 | T | A47510 | 외부 벽공사 [기준선작업] | 1OA47510 | 1층 - 오피스 - 외부 벽공사 [기준선작업] | 2 |  | 1 | P.N.1.T | A475
1층 | 1 | 오피스 | C | A47520 | 외부 벽공사 [하지철물] | 1OA47520 | 1층 - 오피스 - 외부 벽공사 [하지철물] | 1 |  | 1 | P.N.1.C | A475
1층 | 1 | 오피스 | C | A47530 | 외부 벽공사 [외부시공] | 1OA47530 | 1층 - 오피스 - 외부 벽공사 [외부시공] | 1 |  | 1 | P.N.1.C | A475
1층 | 1 | 오피스 | C | A48510 | 석고보드 벽공사 [먹놓기] | 1OA48510 | 1층 - 오피스 - 석고보드 벽공사 [먹놓기] | 2 |  | 1 | P.N.1.C | A485
1층 | 1 | 오피스 | C | A48520 | 석고보드 벽공사 [스터드] | 1OA48520 | 1층 - 오피스 - 석고보드 벽공사 [스터드] | 1 |  | 1 | P.N.1.C | A485
1층 | 1 | 오피스 | C | A48530 | 석고보드 벽공사 [석고보드시공] | 1OA48530 | 1층 - 오피스 - 석고보드 벽공사 [석고보드시공] | 1 |  | 1 | P.N.1.C | A485
1층 | 1 | 오피스 | C | A50510 | 천정틀시공 [행거설치] | 1OA50510 | 1층 - 오피스 - 천정틀시공 [행거설치] | 1 |  | 1 | P.N.1.C | A505
1층 | 1 | 오피스 | C | A50520 | 천정틀시공 [틀설치] | 1OA50520 | 1층 - 오피스 - 천정틀시공 [틀설치] | 1 |  | 1 | P.N.1.C | A505
1층 | 1 | 오피스 | C | A51010 | 석고보드 천정공사 [석고보드시공] | 1OA51010 | 1층 - 오피스 - 석고보드 천정공사 [석고보드시공] | 1 |  | 1 | P.N.1.C | A510
1층 | 1 | 오피스 | C | A52510 | 공용부창호설치 [창틀설치] | 1OA52510 | 1층 - 오피스 - 공용부창호설치 [창틀설치] | 1 |  | 1 | P.N.1.C | A525
1층 | 1 | 오피스 | C | A52520 | 공용부창호설치 [우레탄충진] | 1OA52520 | 1층 - 오피스 - 공용부창호설치 [우레탄충진] | 1 |  | 1 | P.N.1.C | A525
1층 | 1 | 오피스 | C | A52530 | 공용부창호설치 [창설치] | 1OA52530 | 1층 - 오피스 - 공용부창호설치 [창설치] | 1 |  | 1 | P.N.1.C | A525
1층 | 1 | 오피스 | C | A53010 | 공용부문설치 [문틀설치] | 1OA53010 | 1층 - 오피스 - 공용부문설치 [문틀설치] | 1 |  | 1 | P.N.1.C | A530
1층 | 1 | 오피스 | C | A53020 | 공용부문설치 [문짝설치] | 1OA53020 | 1층 - 오피스 - 공용부문설치 [문짝설치] | 1 |  | 1 | P.N.1.C | A530
1층 | 1 | 오피스 | C | A57510 | 실내벽도장 [바탕면처리] | 1OA57510 | 1층 - 오피스 - 실내벽도장 [바탕면처리] | 2 |  | 1 | P.N.1.C | A575
1층 | 1 | 오피스 | C | A57520 | 실내벽도장 [도장] | 1OA57520 | 1층 - 오피스 - 실내벽도장 [도장] | 1 |  | 1 | P.N.1.C | A575
1층 | 1 | 오피스 | C | A57530 | 실내벽도장 [마감도장] | 1OA57530 | 1층 - 오피스 - 실내벽도장 [마감도장] | 1 |  | 1 | P.N.1.C | A575
1층 | 1 | 오피스 | C | A58010 | 유리설치 [설치] | 1OA58010 | 1층 - 오피스 - 유리설치 [설치] | 1 |  | 1 | P.N.1.C | A580
1층 | 1 | 오피스 | C | A59010 | 실내천정도장 [바탕면처리] | 1OA59010 | 1층 - 오피스 - 실내천정도장 [바탕면처리] | 1 |  | 1 | P.N.1.C | A590
1층 | 1 | 오피스 | C | A59020 | 실내천정도장 [도장] | 1OA59020 | 1층 - 오피스 - 실내천정도장 [도장] | 1 |  | 1 | P.N.1.C | A590
1층 | 1 | 오피스 | C | A59030 | 실내천정도장 [마감도장] | 1OA59030 | 1층 - 오피스 - 실내천정도장 [마감도장] | 1 |  | 1 | P.N.1.C | A590
1층 | 1 | 오피스 | C | A61510 | Access Floor시공 [분진방지도장) | 1OA61510 | 1층 - 오피스 - Access Floor시공 [분진방지도장) | 1 |  | 1 | P.N.1.C | A615
1층 | 1 | 오피스 | C | A61520 | Access Floor시공 [먹메김] | 1OA61520 | 1층 - 오피스 - Access Floor시공 [먹메김] | 2 |  | 1 | P.N.1.C | A615
1층 | 1 | 오피스 | C | A61530 | Access Floor시공 [하지작업] | 1OA61530 | 1층 - 오피스 - Access Floor시공 [하지작업] | 1 |  | 1 | P.N.1.C | A615
1층 | 1 | 오피스 | C | A61540 | Access Floor시공 [바닥판설치] | 1OA61540 | 1층 - 오피스 - Access Floor시공 [바닥판설치] | 1 |  | 1 | P.N.1.C | A615
1층 | 1 | 오피스 | C | A62510 | 걸레받이시공 [걸레받이설치] | 1OA62510 | 1층 - 오피스 - 걸레받이시공 [걸레받이설치] | 2 |  | 1 | P.N.1.C | A625
1층 | 1 | 오피스 | C | A66510 | 가전공사 | 1OA66510 | 1층 - 오피스 - 가전공사 | 1 |  | 1 | P.N.1.C | A665
1층 | 1 | 오피스 | C | A67010 | 가구공사 | 1OA67010 | 1층 - 오피스 - 가구공사 | 1 |  | 1 | P.N.1.C | A670
1층 | 1 | 오피스 | C | A68010 | 사인공사 | 1OA68010 | 1층 - 오피스 - 사인공사 | 2 |  | 1 | P.N.1.C | A680
1층 | 1 | 휴게실 | C | A41510 | 기준먹메김 | 1RA41510 | 1층 - 휴게실 - 기준먹메김 | 2 |  | 1 | P.N.1.C | A415
1층 | 1 | 휴게실 | C | A45510 | 단열벽공사 [바탕면처리] | 1RA45510 | 1층 - 휴게실 - 단열벽공사 [바탕면처리] | 2 |  | 1 | P.N.1.C | A455
1층 | 1 | 휴게실 | C | A45520 | 단열벽공사 [단열재설치] | 1RA45520 | 1층 - 휴게실 - 단열벽공사 [단열재설치] | 1 |  | 1 | P.N.1.C | A455
1층 | 1 | 휴게실 | C | A46010 | 단열천정공사 [바탕면처리] | 1RA46010 | 1층 - 휴게실 - 단열천정공사 [바탕면처리] | 2 |  | 1 | P.N.1.C | A460
1층 | 1 | 휴게실 | C | A46020 | 단열천정공사 [단열재설치] | 1RA46020 | 1층 - 휴게실 - 단열천정공사 [단열재설치] | 1 |  | 1 | P.N.1.C | A460
1층 | 1 | 휴게실 | C | A47510 | 외부 벽공사 [기준선작업] | 1RA47510 | 1층 - 휴게실 - 외부 벽공사 [기준선작업] | 2 |  | 1 | P.N.1.C | A475
1층 | 1 | 휴게실 | L | A47520 | 외부 벽공사 [하지철물] | 1RA47520 | 1층 - 휴게실 - 외부 벽공사 [하지철물] | 1 |  | 1 | P.N.1.L | A475
1층 | 1 | 휴게실 | L | A47530 | 외부 벽공사 [외부시공] | 1RA47530 | 1층 - 휴게실 - 외부 벽공사 [외부시공] | 1 |  | 1 | P.N.1.L | A475
1층 | 1 | 휴게실 | L | A48510 | 석고보드 벽공사 [먹놓기] | 1RA48510 | 1층 - 휴게실 - 석고보드 벽공사 [먹놓기] | 2 |  | 1 | P.N.1.L | A485
1층 | 1 | 휴게실 | L | A48520 | 석고보드 벽공사 [스터드] | 1RA48520 | 1층 - 휴게실 - 석고보드 벽공사 [스터드] | 1 |  | 1 | P.N.1.L | A485
1층 | 1 | 휴게실 | L | A48530 | 석고보드 벽공사 [석고보드시공] | 1RA48530 | 1층 - 휴게실 - 석고보드 벽공사 [석고보드시공] | 1 |  | 1 | P.N.1.L | A485
1층 | 1 | 휴게실 | L | A50510 | 천정틀시공 [행거설치] | 1RA50510 | 1층 - 휴게실 - 천정틀시공 [행거설치] | 1 |  | 1 | P.N.1.L | A505
1층 | 1 | 휴게실 | L | A50520 | 천정틀시공 [틀설치] | 1RA50520 | 1층 - 휴게실 - 천정틀시공 [틀설치] | 1 |  | 1 | P.N.1.L | A505
1층 | 1 | 휴게실 | L | A51010 | 석고보드 천정공사 [석고보드시공] | 1RA51010 | 1층 - 휴게실 - 석고보드 천정공사 [석고보드시공] | 1 |  | 1 | P.N.1.L | A510
1층 | 1 | 휴게실 | L | A51510 | 세대창호설치 [창틀설치] | 1RA51510 | 1층 - 휴게실 - 세대창호설치 [창틀설치] | 1 |  | 1 | P.N.1.L | A515
1층 | 1 | 휴게실 | L | A51520 | 세대창호설치 [우레탄충진] | 1RA51520 | 1층 - 휴게실 - 세대창호설치 [우레탄충진] | 1 |  | 1 | P.N.1.L | A515
1층 | 1 | 휴게실 | L | A51530 | 세대창호설치 [창설치] | 1RA51530 | 1층 - 휴게실 - 세대창호설치 [창설치] | 1 |  | 1 | P.N.1.L | A515
1층 | 1 | 휴게실 | L | A53510 | 세대 문설치 [문틀설치] | 1RA53510 | 1층 - 휴게실 - 세대 문설치 [문틀설치] | 2 |  | 1 | P.N.1.L | A535
1층 | 1 | 휴게실 | L | A53520 | 세대 문설치 [문짝설치] | 1RA53520 | 1층 - 휴게실 - 세대 문설치 [문짝설치] | 2 |  | 1 | P.N.1.L | A535
1층 | 1 | 휴게실 | L | A54510 | 바닥난방시스템시공 [바탕면정리] | 1RA54510 | 1층 - 휴게실 - 바닥난방시스템시공 [바탕면정리] | 1 |  | 1 | P.N.1.L | A545
1층 | 1 | 휴게실 | L | A54520 | 바닥난방시스템시공 [기포타설] | 1RA54520 | 1층 - 휴게실 - 바닥난방시스템시공 [기포타설] | 2 |  | 1 | P.N.1.L | A545
1층 | 1 | 휴게실 | L | A54530 | 바닥난방시스템시공 [방통타설/양생] | 1RA54530 | 1층 - 휴게실 - 바닥난방시스템시공 [방통타설/양생] | 2 |  | 1 | P.N.1.L | A545
1층 | 1 | 휴게실 | L | A58010 | 유리설치 [설치] | 1RA58010 | 1층 - 휴게실 - 유리설치 [설치] | 1 |  | 1 | P.N.1.L | A580
1층 | 1 | 휴게실 | L | A59010 | 실내천정도장 [바탕면처리] | 1RA59010 | 1층 - 휴게실 - 실내천정도장 [바탕면처리] | 1 |  | 1 | P.N.1.L | A590
1층 | 1 | 휴게실 | L | A59020 | 실내천정도장 [도장] | 1RA59020 | 1층 - 휴게실 - 실내천정도장 [도장] | 1 |  | 1 | P.N.1.L | A590
1층 | 1 | 휴게실 | L | A59030 | 실내천정도장 [마감도장] | 1RA59030 | 1층 - 휴게실 - 실내천정도장 [마감도장] | 1 |  | 1 | P.N.1.L | A590
1층 | 1 | 휴게실 | L | A62010 | 마루시공 [바탕면처리] | 1RA62010 | 1층 - 휴게실 - 마루시공 [바탕면처리] | 1 |  | 1 | P.N.1.L | A620
1층 | 1 | 휴게실 | L | A62020 | 마루시공 [먹메김] | 1RA62020 | 1층 - 휴게실 - 마루시공 [먹메김] | 2 |  | 1 | P.N.1.L | A620
1층 | 1 | 휴게실 | R | A62030 | 마루시공 [하지작업] | 1RA62030 | 1층 - 휴게실 - 마루시공 [하지작업] | 1 |  | 1 | P.N.1.R | A620
1층 | 1 | 휴게실 | R | A62040 | 마루시공 [마루설치] | 1RA62040 | 1층 - 휴게실 - 마루시공 [마루설치] | 1 |  | 1 | P.N.1.R | A620
1층 | 1 | 휴게실 | R | A62050 | 마루시공 [마감처리] | 1RA62050 | 1층 - 휴게실 - 마루시공 [마감처리] | 1 |  | 1 | P.N.1.R | A620
1층 | 1 | 휴게실 | R | A62510 | 걸레받이시공 [걸레받이설치] | 1RA62510 | 1층 - 휴게실 - 걸레받이시공 [걸레받이설치] | 2 |  | 1 | P.N.1.R | A625
1층 | 1 | 휴게실 | R | A63010 | 도배공사 [천정도배] | 1RA63010 | 1층 - 휴게실 - 도배공사 [천정도배] | 1 |  | 1 | P.N.1.R | A630
1층 | 1 | 휴게실 | R | A63020 | 도배공사 [벽도배] | 1RA63020 | 1층 - 휴게실 - 도배공사 [벽도배] | 1 |  | 1 | P.N.1.R | A630
1층 | 1 | 휴게실 | R | A66510 | 가전공사 | 1RA66510 | 1층 - 휴게실 - 가전공사 | 1 |  | 1 | P.N.1.R | A665
1층 | 1 | 휴게실 | R | A67010 | 가구공사 | 1RA67010 | 1층 - 휴게실 - 가구공사 | 1 |  | 1 | P.N.1.R | A670
1층 | 1 | 휴게실 | R | A68010 | 사인공사 | 1RA68010 | 1층 - 휴게실 - 사인공사 | 2 |  | 1 | P.N.1.R | A680
1층 | 1 | 화장실 | R | A41510 | 기준먹메김 | 1TA41510 | 1층 - 화장실 - 기준먹메김 | 2 |  | 1 | P.N.1.R | A415
1층 | 1 | 화장실 | R | A44510 | 조적시공 [운반작업] | 1TA44510 | 1층 - 화장실 - 조적시공 [운반작업] | 2 |  | 1 | P.N.1.R | A445
1층 | 1 | 화장실 | R | A44520 | 조적시공 [조적1차] | 1TA44520 | 1층 - 화장실 - 조적시공 [조적1차] | 1 |  | 1 | P.N.1.R | A445
1층 | 1 | 화장실 | R | A44521 | 조적시공 [조적2차] | 1TA44521 | 1층 - 화장실 - 조적시공 [조적2차] | 1 |  | 1 | P.N.1.R | A445
1층 | 1 | 화장실 | R | A45010 | 미장공사 [바탕면처리] | 1TA45010 | 1층 - 화장실 - 미장공사 [바탕면처리] | 2 |  | 1 | P.N.1.R | A450
1층 | 1 | 화장실 | R | A45011 | 미장공사 [미장 초벌] | 1TA45011 | 1층 - 화장실 - 미장공사 [미장 초벌] | 1 |  | 1 | P.N.1.R | A450
1층 | 1 | 화장실 | R | A45012 | 미장공사 [미장 정벌] | 1TA45012 | 1층 - 화장실 - 미장공사 [미장 정벌] | 1 |  | 1 | P.N.1.R | A450
1층 | 1 | 화장실 | R | A45510 | 단열벽공사 [바탕면처리] | 1TA45510 | 1층 - 화장실 - 단열벽공사 [바탕면처리] | 2 |  | 1 | P.N.1.R | A455
1층 | 1 | 화장실 | R | A45520 | 단열벽공사 [단열재설치] | 1TA45520 | 1층 - 화장실 - 단열벽공사 [단열재설치] | 1 |  | 1 | P.N.1.R | A455
1층 | 1 | 화장실 | R | A48510 | 석고보드 벽공사 [먹놓기] | 1TA48510 | 1층 - 화장실 - 석고보드 벽공사 [먹놓기] | 2 |  | 1 | P.N.1.R | A485
1층 | 1 | 화장실 | R | A48520 | 석고보드 벽공사 [스터드] | 1TA48520 | 1층 - 화장실 - 석고보드 벽공사 [스터드] | 1 |  | 1 | P.N.1.R | A485
1층 | 1 | 화장실 | R | A48530 | 석고보드 벽공사 [석고보드시공] | 1TA48530 | 1층 - 화장실 - 석고보드 벽공사 [석고보드시공] | 1 |  | 1 | P.N.1.R | A485
1층 | 1 | 화장실 | R | A49510 | 실내방수시공 [바탕면처리] | 1TA49510 | 1층 - 화장실 - 실내방수시공 [바탕면처리] | 1 |  | 1 | P.N.1.R | A495
1층 | 1 | 화장실 | R | A49520 | 실내방수시공 [방수시공] | 1TA49520 | 1층 - 화장실 - 실내방수시공 [방수시공] | 1 |  | 1 | P.N.1.R | A495
1층 | 1 | 화장실 | R | A49530 | 실내방수시공 [방수테스트] | 1TA49530 | 1층 - 화장실 - 실내방수시공 [방수테스트] | 1 |  | 1 | P.N.1.R | A495
1층 | 1 | 화장실 | R | A49540 | 실내방수시공 [보호몰탈] | 1TA49540 | 1층 - 화장실 - 실내방수시공 [보호몰탈] | 1 |  | 1 | P.N.1.R | A495
1층 | 1 | 화장실 | R | A50510 | 천정틀시공 [행거설치] | 1TA50510 | 1층 - 화장실 - 천정틀시공 [행거설치] | 1 |  | 1 | P.N.1.R | A505
1층 | 1 | 화장실 | R | A50520 | 천정틀시공 [틀설치] | 1TA50520 | 1층 - 화장실 - 천정틀시공 [틀설치] | 1 |  | 1 | P.N.1.R | A505
1층 | 1 | 화장실 | R | A53010 | 공용부문설치 [문틀설치] | 1TA53010 | 1층 - 화장실 - 공용부문설치 [문틀설치] | 1 |  | 1 | P.N.1.R | A530
1층 | 1 | 화장실 | R | A53020 | 공용부문설치 [문짝설치] | 1TA53020 | 1층 - 화장실 - 공용부문설치 [문짝설치] | 1 |  | 1 | P.N.1.R | A530
1층 | 1 | 화장실 | R | A56510 | 화장실바닥타일시공 [바탕면처리] | 1TA56510 | 1층 - 화장실 - 화장실바닥타일시공 [바탕면처리] | 1 |  | 1 | P.N.1.R | A565
1층 | 1 | 화장실 | R | A56520 | 화장실바닥타일시공 [타일시공] | 1TA56520 | 1층 - 화장실 - 화장실바닥타일시공 [타일시공] | 1 |  | 1 | P.N.1.R | A565
1층 | 1 | 화장실 | R | A57010 | 벽타일시공 [타일시공] | 1TA57010 | 1층 - 화장실 - 벽타일시공 [타일시공] | 1 |  | 1 | P.N.1.R | A570
1층 | 1 | 화장실 | R | A60010 | SMC 천장시공 [천정설치] | 1TA60010 | 1층 - 화장실 - SMC 천장시공 [천정설치] | 1 |  | 1 | P.N.1.R | A600
1층 | 1 | 화장실 | R | A60710 | 세면대설치 [하지작업] | 1TA60710 | 1층 - 화장실 - 세면대설치 [하지작업] | 1 |  | 1 | P.N.1.R | A607
1층 | 1 | 화장실 | R | A60720 | 세면대설치 [세면대설치] | 1TA60720 | 1층 - 화장실 - 세면대설치 [세면대설치] | 1 |  | 1 | P.N.1.R | A607
1층 | 1 | 화장실 | R | A66010 | 화장실기구설치(거울, 큐비클) | 1TA66010 | 1층 - 화장실 - 화장실기구설치(거울, 큐비클) | 1 |  | 1 | P.N.1.R | A660
1층 | 1 | 화장실 | R | A68010 | 사인공사 | 1TA68010 | 1층 - 화장실 - 사인공사 | 2 |  | 1 | P.N.1.R | A680

## 작업생산성
ID | 작업 | 생산성 | 최소작업기간
A41510 | 기준먹메김 | 2 |  | A415 | 기준먹메김 | A41510
A41810 | 비닐타일 [타일시공] | 1 |  | A418 | 비닐타일 [타일시공] | A41810
A43010 | 무근타설 [레벨작업] | 2 |  | A430 | 무근타설 [레벨작업] | A43010
A43020 | 무근타설 [무근타설] | 2 |  | A430 | 무근타설 [무근타설] | A43020
A43021 | 무근타설 [바닥미장, 양생] | 2 |  | A430 | 무근타설 [바닥미장, 양생] | A43021
A43022 | 무근타설 [양생] | 2 |  | A430 | 무근타설 [양생] | A43022
A44510 | 조적시공 [운반작업] | 2 |  | A445 | 조적시공 [운반작업] | A44510
A44520 | 조적시공 [조적1차] | 1 |  | A445 | 조적시공 [조적1차] | A44520
A44521 | 조적시공 [조적2차] | 1 |  | A445 | 조적시공 [조적2차] | A44521
A45010 | 미장공사 [바탕면처리] | 2 |  | A450 | 미장공사 [바탕면처리] | A45010
A45011 | 미장공사 [미장 초벌] | 1 |  | A450 | 미장공사 [미장 초벌] | A45011
A45012 | 미장공사 [미장 정벌] | 1 |  | A450 | 미장공사 [미장 정벌] | A45012
A45510 | 단열벽공사 [바탕면처리] | 2 |  | A455 | 단열벽공사 [바탕면처리] | A45510
A45520 | 단열벽공사 [단열재설치] | 1 |  | A455 | 단열벽공사 [단열재설치] | A45520
A46010 | 단열천정공사 [바탕면처리] | 2 |  | A460 | 단열천정공사 [바탕면처리] | A46010
A46020 | 단열천정공사 [단열재설치] | 1 |  | A460 | 단열천정공사 [단열재설치] | A46020
A47510 | 외부 벽공사 [기준선작업] | 2 |  | A475 | 외부 벽공사 [기준선작업] | A47510
A47520 | 외부 벽공사 [하지철물] | 1 |  | A475 | 외부 벽공사 [하지철물] | A47520
A47530 | 외부 벽공사 [외부시공] | 1 |  | A475 | 외부 벽공사 [외부시공] | A47530
A48510 | 석고보드 벽공사 [먹놓기] | 2 |  | A485 | 석고보드 벽공사 [먹놓기] | A48510
A48520 | 석고보드 벽공사 [스터드] | 1 |  | A485 | 석고보드 벽공사 [스터드] | A48520
A48530 | 석고보드 벽공사 [석고보드시공] | 1 |  | A485 | 석고보드 벽공사 [석고보드시공] | A48530
A49510 | 실내방수시공 [바탕면처리] | 1 |  | A495 | 실내방수시공 [바탕면처리] | A49510
A49520 | 실내방수시공 [방수시공] | 1 |  | A495 | 실내방수시공 [방수시공] | A49520
A49530 | 실내방수시공 [방수테스트] | 1 |  | A495 | 실내방수시공 [방수테스트] | A49530
A49540 | 실내방수시공 [보호몰탈] | 1 |  | A495 | 실내방수시공 [보호몰탈] | A49540
A50510 | 천정틀시공 [행거설치] | 1 |  | A505 | 천정틀시공 [행거설치] | A50510
A50520 | 천정틀시공 [틀설치] | 1 |  | A505 | 천정틀시공 [틀설치] | A50520
A51010 | 석고보드 천정공사 [석고보드시공] | 1 |  | A510 | 석고보드 천정공사 [석고보드시공] | A51010
A51510 | 세대창호설치 [창틀설치] | 1 |  | A515 | 세대창호설치 [창틀설치] | A51510
A51520 | 세대창호설치 [우레탄충진] | 1 |  | A515 | 세대창호설치 [우레탄충진] | A51520
A51530 | 세대창호설치 [창설치] | 1 |  | A515 | 세대창호설치 [창설치] | A51530
A52010 | 그릴설치 [설치] | 1 |  | A520 | 그릴설치 [설치] | A52010
A52510 | 공용부창호설치 [창틀설치] | 1 |  | A525 | 공용부창호설치 [창틀설치] | A52510
A52520 | 공용부창호설치 [우레탄충진] | 1 |  | A525 | 공용부창호설치 [우레탄충진] | A52520
A52530 | 공용부창호설치 [창설치] | 1 |  | A525 | 공용부창호설치 [창설치] | A52530
A53010 | 공용부문설치 [문틀설치] | 1 |  | A530 | 공용부문설치 [문틀설치] | A53010
A53020 | 공용부문설치 [문짝설치] | 1 |  | A530 | 공용부문설치 [문짝설치] | A53020
A53510 | 세대 문설치 [문틀설치] | 2 |  | A535 | 세대 문설치 [문틀설치] | A53510
A53520 | 세대 문설치 [문짝설치] | 2 |  | A535 | 세대 문설치 [문짝설치] | A53520
A54010 | 유리문설치 [바탕면정리] | 1 |  | A540 | 유리문설치 [바탕면정리] | A54010
A54020 | 유리문설치 [하드웨어설치] | 1 |  | A540 | 유리문설치 [하드웨어설치] | A54020
A54030 | 유리문설치 [문설치] | 1 |  | A540 | 유리문설치 [문설치] | A54030
A54510 | 바닥난방시스템시공 [바탕면정리] | 1 |  | A545 | 바닥난방시스템시공 [바탕면정리] | A54510
A54520 | 바닥난방시스템시공 [기포타설] | 2 |  | A545 | 바닥난방시스템시공 [기포타설] | A54520
A54530 | 바닥난방시스템시공 [방통타설/양생] | 2 |  | A545 | 바닥난방시스템시공 [방통타설/양생] | A54530
A55010 | 석재시공 | 1 |  | A550 | 석재시공 | A55010
A56510 | 화장실바닥타일시공 [바탕면처리] | 1 |  | A565 | 화장실바닥타일시공 [바탕면처리] | A56510
A56520 | 화장실바닥타일시공 [타일시공] | 1 |  | A565 | 화장실바닥타일시공 [타일시공] | A56520
A57010 | 벽타일시공 [타일시공] | 1 |  | A570 | 벽타일시공 [타일시공] | A57010
A57510 | 실내벽도장 [바탕면처리] | 2 |  | A575 | 실내벽도장 [바탕면처리] | A57510
A57520 | 실내벽도장 [도장] | 1 |  | A575 | 실내벽도장 [도장] | A57520
A57530 | 실내벽도장 [마감도장] | 1 |  | A575 | 실내벽도장 [마감도장] | A57530
A58010 | 유리설치 [설치] | 1 |  | A580 | 유리설치 [설치] | A58010
A59010 | 실내천정도장 [바탕면처리] | 1 |  | A590 | 실내천정도장 [바탕면처리] | A59010
A59020 | 실내천정도장 [도장] | 1 |  | A590 | 실내천정도장 [도장] | A59020
A59030 | 실내천정도장 [마감도장] | 1 |  | A590 | 실내천정도장 [마감도장] | A59030
A59510 | 계단실 텍스 천정공사 [천정설치] | 1 |  | A595 | 계단실 텍스 천정공사 [천정설치] | A59510
A60010 | SMC 천장시공 [천정설치] | 1 |  | A600 | SMC 천장시공 [천정설치] | A60010
A60020 | 바리솔, 루버 천장시공 [천정설치] | 1 |  | A600 | 바리솔, 루버 천장시공 [천정설치] | A60020
A60510 | 실내바닥도장(에폭시) [바탕면처리] | 1 |  | A605 | 실내바닥도장(에폭시) [바탕면처리] | A60510
A60520 | 실내바닥도장(에폭시) [도장] | 1 |  | A605 | 실내바닥도장(에폭시) [도장] | A60520
A60530 | 실내바닥도장 [마감도장] | 1 |  | A605 | 실내바닥도장 [마감도장] | A60530
A60710 | 세면대설치 [하지작업] | 1 |  | A607 | 세면대설치 [하지작업] | A60710
A60720 | 세면대설치 [세면대설치] | 1 |  | A607 | 세면대설치 [세면대설치] | A60720
A61010 | 계단실 비닐타일 [바탕면처리] | 1 |  | A610 | 계단실 비닐타일 [바탕면처리] | A61010
A61020 | 계단실 비닐타일 [타일시공] | 1 |  | A610 | 계단실 비닐타일 [타일시공] | A61020
A61510 | Access Floor시공 [분진방지도장) | 1 |  | A615 | Access Floor시공 [분진방지도장) | A61510
A61520 | Access Floor시공 [먹메김] | 2 |  | A615 | Access Floor시공 [먹메김] | A61520
A61530 | Access Floor시공 [하지작업] | 1 |  | A615 | Access Floor시공 [하지작업] | A61530
A61540 | Access Floor시공 [바닥판설치] | 1 |  | A615 | Access Floor시공 [바닥판설치] | A61540
A62010 | 마루시공 [바탕면처리] | 1 |  | A620 | 마루시공 [바탕면처리] | A62010
A62020 | 마루시공 [먹메김] | 2 |  | A620 | 마루시공 [먹메김] | A62020
A62030 | 마루시공 [하지작업] | 1 |  | A620 | 마루시공 [하지작업] | A62030
A62040 | 마루시공 [마루설치] | 1 |  | A620 | 마루시공 [마루설치] | A62040
A62050 | 마루시공 [마감처리] | 1 |  | A620 | 마루시공 [마감처리] | A62050
A62510 | 걸레받이시공 [걸레받이설치] | 2 |  | A625 | 걸레받이시공 [걸레받이설치] | A62510
A63010 | 도배공사 [천정도배] | 1 |  | A630 | 도배공사 [천정도배] | A63010
A63020 | 도배공사 [벽도배] | 1 |  | A630 | 도배공사 [벽도배] | A63020
A64010 | 계단잡철물공사 [설치] | 1 |  | A640 | 계단잡철물공사 [설치] | A64010
A66010 | 화장실기구설치(거울, 큐비클) | 1 |  | A660 | 화장실기구설치(거울, 큐비클) | A66010
A66510 | 가전공사 | 1 |  | A665 | 가전공사 | A66510
A67010 | 가구공사 | 1 |  | A670 | 가구공사 | A67010
A68010 | 사인공사 | 2 |  | A680 | 사인공사 | #N/A

## 선후관계
선행 | 후행 | 관계 |  | Lag | 선행 | 후행
A43022 | A41810 | FS | A43022 | 0 | 무근타설 [양생] | 비닐타일 [타일시공] | A43022 | A41810
A51010 | A41810 | FS | A51010 | 0 | 석고보드 천정공사 [석고보드시공] | 비닐타일 [타일시공] | A51010 | A41810
A52010 | A41810 | FS | A52010 | 0 | 그릴설치 [설치] | 비닐타일 [타일시공] | A52010 | A41810
A43022 | A41810 | FS | A43022 | 0 | 무근타설 [양생] | 비닐타일 [타일시공] | A43022 | A41810
A48530 | A43010 | FS | A48530 | 0 | 석고보드 벽공사 [석고보드시공] | 무근타설 [레벨작업] | A48530 | A43010
A43010 | A43020 | FS | A43010 | 0 | 무근타설 [레벨작업] | 무근타설 [무근타설] | A43010 | A43020
A43020 | A43021 | FS | A43020 | 0 | 무근타설 [무근타설] | 무근타설 [바닥미장, 양생] | A43020 | A43021
A43021 | A43022 | FS | A43021 | 0 | 무근타설 [바닥미장, 양생] | 무근타설 [양생] | A43021 | A43022
A44510 | A44520 | FS | A44510 | 0 | 조적시공 [운반작업] | 조적시공 [조적1차] | A44510 | A44520
A44520 | A44521 | FS | A44520 | 0 | 조적시공 [조적1차] | 조적시공 [조적2차] | A44520 | A44521
A44521 | A45010 | FS | A44521 | 0 | 조적시공 [조적2차] | 미장공사 [바탕면처리] | A44521 | A45010
A45010 | A45011 | FS | A45010 | 0 | 미장공사 [바탕면처리] | 미장공사 [미장 초벌] | A45010 | A45011
A45011 | A45012 | FS | A45011 | 0 | 미장공사 [미장 초벌] | 미장공사 [미장 정벌] | A45011 | A45012
A41510 | A45510 | FS | A41510 | 0 | 기준먹메김 | 단열벽공사 [바탕면처리] | A41510 | A45510
A45510 | A45520 | FS | A45510 | 0 | 단열벽공사 [바탕면처리] | 단열벽공사 [단열재설치] | A45510 | A45520
A51510 | A45520 | FS | A51510 | 0 | 세대창호설치 [창틀설치] | 단열벽공사 [단열재설치] | A51510 | A45520
A41510 | A46010 | FS | A41510 | 0 | 기준먹메김 | 단열천정공사 [바탕면처리] | A41510 | A46010
A46010 | A46020 | FS | A46010 | 0 | 단열천정공사 [바탕면처리] | 단열천정공사 [단열재설치] | A46010 | A46020
A45520 | A46020 | FS | A45520 | 0 | 단열벽공사 [단열재설치] | 단열천정공사 [단열재설치] | A45520 | A46020
A41510 | A47510 | FS | A41510 | 0 | 기준먹메김 | 외부 벽공사 [기준선작업] | A41510 | A47510
A47510 | A47520 | FS | A47510 | 0 | 외부 벽공사 [기준선작업] | 외부 벽공사 [하지철물] | A47510 | A47520
A47520 | A47530 | FS | A47520 | 0 | 외부 벽공사 [하지철물] | 외부 벽공사 [외부시공] | A47520 | A47530
A41510 | A48510 | FS | A41510 | 0 | 기준먹메김 | 석고보드 벽공사 [먹놓기] | A41510 | A48510
A48510 | A48520 | FS | A48510 | 0 | 석고보드 벽공사 [먹놓기] | 석고보드 벽공사 [스터드] | A48510 | A48520
A45520 | A48520 | FS | A45520 | 0 | 단열벽공사 [단열재설치] | 석고보드 벽공사 [스터드] | A45520 | A48520
A46020 | A48520 | FS | A46020 | 0 | 단열천정공사 [단열재설치] | 석고보드 벽공사 [스터드] | A46020 | A48520
A48520 | A48530 | FS | A48520 | 0 | 석고보드 벽공사 [스터드] | 석고보드 벽공사 [석고보드시공] | A48520 | A48530
A47530 | A48530 | FS | A47530 | 0 | 외부 벽공사 [외부시공] | 석고보드 벽공사 [석고보드시공] | A47530 | A48530
A45012 | A49510 | FS | A45012 | 0 | 미장공사 [미장 정벌] | 실내방수시공 [바탕면처리] | A45012 | A49510
A48530 | A49510 | FS | A48530 | 0 | 석고보드 벽공사 [석고보드시공] | 실내방수시공 [바탕면처리] | A48530 | A49510
A49510 | A49520 | FS | A49510 | 0 | 실내방수시공 [바탕면처리] | 실내방수시공 [방수시공] | A49510 | A49520
A49520 | A49530 | FS | A49520 | 0 | 실내방수시공 [방수시공] | 실내방수시공 [방수테스트] | A49520 | A49530
A49530 | A49540 | FS | A49530 | 0 | 실내방수시공 [방수테스트] | 실내방수시공 [보호몰탈] | A49530 | A49540
A48530 | A50510 | FS | A48530 | 0 | 석고보드 벽공사 [석고보드시공] | 천정틀시공 [행거설치] | A48530 | A50510
A46020 | A50510 | FS | A46020 | 0 | 단열천정공사 [단열재설치] | 천정틀시공 [행거설치] | A46020 | A50510
A50510 | A50520 | FS | A50510 | 0 | 천정틀시공 [행거설치] | 천정틀시공 [틀설치] | A50510 | A50520
A50520 | A51010 | FS | A50520 | 0 | 천정틀시공 [틀설치] | 석고보드 천정공사 [석고보드시공] | A50520 | A51010
A54530 | A51010 | FS | A54530 | 0 | 바닥난방시스템시공 [방통타설/양생] | 석고보드 천정공사 [석고보드시공] | A54530 | A51010
A47520 | A51510 | FS | A47520 | 0 | 외부 벽공사 [하지철물] | 세대창호설치 [창틀설치] | A47520 | A51510
A41510 | A51510 | FS | A41510 | 0 | 기준먹메김 | 세대창호설치 [창틀설치] | A41510 | A51510
A51510 | A51520 | FS | A51510 | 0 | 세대창호설치 [창틀설치] | 세대창호설치 [우레탄충진] | A51510 | A51520
A51510 | A51530 | FS | A51510 | 0 | 세대창호설치 [창틀설치] | 세대창호설치 [창설치] | A51510 | A51530
A51520 | A51530 | FS | A51520 | 0 | 세대창호설치 [우레탄충진] | 세대창호설치 [창설치] | A51520 | A51530
A52510 | A52010 | FS | A52510 | 0 | 공용부창호설치 [창틀설치] | 그릴설치 [설치] | A52510 | A52010
A41510 | A52510 | FS | A41510 | 0 | 기준먹메김 | 공용부창호설치 [창틀설치] | A41510 | A52510
A47520 | A52510 | FS | A47520 | 0 | 외부 벽공사 [하지철물] | 공용부창호설치 [창틀설치] | A47520 | A52510
A52510 | A52520 | FS | A52510 | 0 | 공용부창호설치 [창틀설치] | 공용부창호설치 [우레탄충진] | A52510 | A52520
A52510 | A52530 | FS | A52510 | 0 | 공용부창호설치 [창틀설치] | 공용부창호설치 [창설치] | A52510 | A52530
A52520 | A52530 | FS | A52520 | 0 | 공용부창호설치 [우레탄충진] | 공용부창호설치 [창설치] | A52520 | A52530
A48520 | A53010 | FS | A48520 | 0 | 석고보드 벽공사 [스터드] | 공용부문설치 [문틀설치] | A48520 | A53010
A53010 | A53020 | FS | A53010 | 0 | 공용부문설치 [문틀설치] | 공용부문설치 [문짝설치] | A53010 | A53020
A41810 | A53020 | FS | A41810 | 0 | 비닐타일 [타일시공] | 공용부문설치 [문짝설치] | A41810 | A53020
A61540 | A53020 | FS | A61540 | 0 | Access Floor시공 [바닥판설치] | 공용부문설치 [문짝설치] | A61540 | A53020
A62510 | A53020 | FS | A62510 | 0 | 걸레받이시공 [걸레받이설치] | 공용부문설치 [문짝설치] | A62510 | A53020
A56520 | A53020 | FS | A56520 | 0 | 화장실바닥타일시공 [타일시공] | 공용부문설치 [문짝설치] | A56520 | A53020
A60720 | A53020 | FS | A60720 | 0 | 세면대설치 [세면대설치] | 공용부문설치 [문짝설치] | A60720 | A53020
A55010 | A53020 | FS | A55010 | 0 | 석재시공 | 공용부문설치 [문짝설치] | A55010 | A53020
A61020 | A53020 | FS | A61020 | 0 | 계단실 비닐타일 [타일시공] | 공용부문설치 [문짝설치] | A61020 | A53020
A48520 | A53510 | FS | A48520 | 0 | 석고보드 벽공사 [스터드] | 세대 문설치 [문틀설치] | A48520 | A53510
A53510 | A53520 | FS | A53510 | 0 | 세대 문설치 [문틀설치] | 세대 문설치 [문짝설치] | A53510 | A53520
A67010 | A53520 | FS | A67010 | 0 | 가구공사 | 세대 문설치 [문짝설치] | A67010 | A53520
A62510 | A53520 | FS | A62510 | 0 | 걸레받이시공 [걸레받이설치] | 세대 문설치 [문짝설치] | A62510 | A53520
A55010 | A54010 | FS | A55010 | 0 | 석재시공 | 유리문설치 [바탕면정리] | A55010 | A54010
A54010 | A54020 | FS | A54010 | 0 | 유리문설치 [바탕면정리] | 유리문설치 [하드웨어설치] | A54010 | A54020
A54020 | A54030 | FS | A54020 | 0 | 유리문설치 [하드웨어설치] | 유리문설치 [문설치] | A54020 | A54030
A48530 | A54510 | FS | A48530 | 0 | 석고보드 벽공사 [석고보드시공] | 바닥난방시스템시공 [바탕면정리] | A48530 | A54510
A53510 | A54510 | FS | A53510 | 0 | 세대 문설치 [문틀설치] | 바닥난방시스템시공 [바탕면정리] | A53510 | A54510
A54510 | A54520 | FS | A54510 | 0 | 바닥난방시스템시공 [바탕면정리] | 바닥난방시스템시공 [기포타설] | A54510 | A54520
A54520 | A54530 | FS | A54520 | 0 | 바닥난방시스템시공 [기포타설] | 바닥난방시스템시공 [방통타설/양생] | A54520 | A54530
A48530 | A55010 | FS | A48530 | 0 | 석고보드 벽공사 [석고보드시공] | 석재시공 | A48530 | A55010
A53010 | A55010 | FS | A53010 | 0 | 공용부문설치 [문틀설치] | 석재시공 | A53010 | A55010
A57010 | A56510 | FS | A57010 | 0 | 벽타일시공 [타일시공] | 화장실바닥타일시공 [바탕면처리] | A57010 | A56510
A56510 | A56520 | FS | A56510 | 0 | 화장실바닥타일시공 [바탕면처리] | 화장실바닥타일시공 [타일시공] | A56510 | A56520
A49540 | A57010 | FS | A49540 | 0 | 실내방수시공 [보호몰탈] | 벽타일시공 [타일시공] | A49540 | A57010
A48530 | A57510 | FS | A48530 | 0 | 석고보드 벽공사 [석고보드시공] | 실내벽도장 [바탕면처리] | A48530 | A57510
A45012 | A57510 | FS | A45012 | 0 | 미장공사 [미장 정벌] | 실내벽도장 [바탕면처리] | A45012 | A57510
A43022 | A57510 | FS | A43022 | 0 | 무근타설 [양생] | 실내벽도장 [바탕면처리] | A43022 | A57510
A57510 | A57520 | FS | A57510 | 0 | 실내벽도장 [바탕면처리] | 실내벽도장 [도장] | A57510 | A57520
A57520 | A57530 | FS | A57520 | 0 | 실내벽도장 [도장] | 실내벽도장 [마감도장] | A57520 | A57530
A52530 | A58010 | FS | A52530 | 0 | 공용부창호설치 [창설치] | 유리설치 [설치] | A52530 | A58010
A51530 | A58010 | FS | A51530 | 0 | 세대창호설치 [창설치] | 유리설치 [설치] | A51530 | A58010
A51010 | A59010 | FS | A51010 | 0 | 석고보드 천정공사 [석고보드시공] | 실내천정도장 [바탕면처리] | A51010 | A59010
A59010 | A59020 | FS | A59010 | 0 | 실내천정도장 [바탕면처리] | 실내천정도장 [도장] | A59010 | A59020
A59020 | A59030 | FS | A59020 | 0 | 실내천정도장 [도장] | 실내천정도장 [마감도장] | A59020 | A59030
A57520 | A59510 | FS | A57520 | 0 | 실내벽도장 [도장] | 계단실 텍스 천정공사 [천정설치] | A57520 | A59510
A50520 | A59510 | FS | A50520 | 0 | 천정틀시공 [틀설치] | 계단실 텍스 천정공사 [천정설치] | A50520 | A59510
A50520 | A60010 | FS | A50520 | 0 | 천정틀시공 [틀설치] | SMC 천장시공 [천정설치] | A50520 | A60010
A56520 | A60010 | FS | A56520 | 0 | 화장실바닥타일시공 [타일시공] | SMC 천장시공 [천정설치] | A56520 | A60010
A50520 | A60020 | FS | A50520 | 0 | 천정틀시공 [틀설치] | 바리솔, 루버 천장시공 [천정설치] | A50520 | A60020
A59020 | A60510 | FS | A59020 | 0 | 실내천정도장 [도장] | 실내바닥도장(에폭시) [바탕면처리] | A59020 | A60510
A52010 | A60510 | FS | A52010 | 0 | 그릴설치 [설치] | 실내바닥도장(에폭시) [바탕면처리] | A52010 | A60510
A60510 | A60520 | FS | A60510 | 0 | 실내바닥도장(에폭시) [바탕면처리] | 실내바닥도장(에폭시) [도장] | A60510 | A60520
A60520 | A60530 | FS | A60520 | 0 | 실내바닥도장(에폭시) [도장] | 실내바닥도장 [마감도장] | A60520 | A60530
A56520 | A60710 | FS | A56520 | 0 | 화장실바닥타일시공 [타일시공] | 세면대설치 [하지작업] | A56520 | A60710
A60010 | A60720 | FS | A60010 | 0 | SMC 천장시공 [천정설치] | 세면대설치 [세면대설치] | A60010 | A60720
A60710 | A60720 | FS | A60710 | 0 | 세면대설치 [하지작업] | 세면대설치 [세면대설치] | A60710 | A60720
A64010 | A61010 | FS | A64010 | 0 | 계단잡철물공사 [설치] | 계단실 비닐타일 [바탕면처리] | A64010 | A61010
A57520 | A61010 | FS | A57520 | 0 | 실내벽도장 [도장] | 계단실 비닐타일 [바탕면처리] | A57520 | A61010
A59030 | A61020 | FS | A59030 | 0 | 실내천정도장 [마감도장] | 계단실 비닐타일 [타일시공] | A59030 | A61020
A61010 | A61020 | FS | A61010 | 0 | 계단실 비닐타일 [바탕면처리] | 계단실 비닐타일 [타일시공] | A61010 | A61020
A59510 | A61020 | FS | A59510 | 0 | 계단실 텍스 천정공사 [천정설치] | 계단실 비닐타일 [타일시공] | A59510 | A61020
A57520 | A61510 | FS | A57520 | 0 | 실내벽도장 [도장] | Access Floor시공 [분진방지도장) | A57520 | A61510
A43022 | A61510 | FS | A43022 | 0 | 무근타설 [양생] | Access Floor시공 [분진방지도장) | A43022 | A61510
A61510 | A61520 | FS | A61510 | 0 | Access Floor시공 [분진방지도장) | Access Floor시공 [먹메김] | A61510 | A61520
A61520 | A61530 | FS | A61520 | 0 | Access Floor시공 [먹메김] | Access Floor시공 [하지작업] | A61520 | A61530
A61530 | A61540 | FS | A61530 | 0 | Access Floor시공 [하지작업] | Access Floor시공 [바닥판설치] | A61530 | A61540
A54530 | A62010 | FS | A54530 | 0 | 바닥난방시스템시공 [방통타설/양생] | 마루시공 [바탕면처리] | A54530 | A62010
A62010 | A62020 | FS | A62010 | 0 | 마루시공 [바탕면처리] | 마루시공 [먹메김] | A62010 | A62020
A62020 | A62030 | FS | A62020 | 0 | 마루시공 [먹메김] | 마루시공 [하지작업] | A62020 | A62030
A62030 | A62040 | FS | A62030 | 0 | 마루시공 [하지작업] | 마루시공 [마루설치] | A62030 | A62040
A58010 | A62040 | FS | A58010 | 0 | 유리설치 [설치] | 마루시공 [마루설치] | A58010 | A62040
A62040 | A62050 | FS | A62040 | 0 | 마루시공 [마루설치] | 마루시공 [마감처리] | A62040 | A62050
A51010 | A62510 | FS | A51010 | 0 | 석고보드 천정공사 [석고보드시공] | 걸레받이시공 [걸레받이설치] | A51010 | A62510
A51010 | A63010 | FS | A51010 | 0 | 석고보드 천정공사 [석고보드시공] | 도배공사 [천정도배] | A51010 | A63010
A58010 | A63010 | FS | A58010 | 0 | 유리설치 [설치] | 도배공사 [천정도배] | A58010 | A63010
A43022 | A63010 | FS | A43022 | 0 | 무근타설 [양생] | 도배공사 [천정도배] | A43022 | A63010
A63010 | A63020 | FS | A63010 | 0 | 도배공사 [천정도배] | 도배공사 [벽도배] | A63010 | A63020
A58010 | A63020 | FS | A58010 | 0 | 유리설치 [설치] | 도배공사 [벽도배] | A58010 | A63020
A43022 | A63020 | FS | A43022 | 0 | 무근타설 [양생] | 도배공사 [벽도배] | A43022 | A63020
A60720 | A66010 | FS | A60720 | 0 | 세면대설치 [세면대설치] | 화장실기구설치(거울, 큐비클) | A60720 | A66010
A67010 | A66510 | FS | A67010 | 0 | 가구공사 | 가전공사 | A67010 | A66510
A62050 | A66510 | FS | A62050 | 0 | 마루시공 [마감처리] | 가전공사 | A62050 | A66510
A53520 | A66510 | FS | A53520 | 0 | 세대 문설치 [문짝설치] | 가전공사 | A53520 | A66510
A53020 | A67010 | FS | A53020 | 0 | 공용부문설치 [문짝설치] | 가구공사 | A53020 | A67010
A57530 | A67010 | FS | A57530 | 0 | 실내벽도장 [마감도장] | 가구공사 | A57530 | A67010
A59030 | A67010 | FS | A59030 | 0 | 실내천정도장 [마감도장] | 가구공사 | A59030 | A67010
A41810 | A67010 | FS | A41810 | 0 | 비닐타일 [타일시공] | 가구공사 | A41810 | A67010
A63010 | A67010 | FS | A63010 | 0 | 도배공사 [천정도배] | 가구공사 | A63010 | A67010
A63020 | A67010 | FS | A63020 | 0 | 도배공사 [벽도배] | 가구공사 | A63020 | A67010
A62050 | A67010 | FS | A62050 | 0 | 마루시공 [마감처리] | 가구공사 | A62050 | A67010
A60530 | A67010 | FS | A60530 | 0 | 실내바닥도장 [마감도장] | 가구공사 | A60530 | A67010
A60020 | A67010 | FS | A60020 | 0 | 바리솔, 루버 천장시공 [천정설치] | 가구공사 | A60020 | A67010
A54030 | A67010 | FS | A54030 | 0 | 유리문설치 [문설치] | 가구공사 | A54030 | A67010
A53020 | A68010 | FS | A53020 | 0 | 공용부문설치 [문짝설치] | 사인공사 | A53020 | A68010
A57530 | A68010 | FS | A57530 | 0 | 실내벽도장 [마감도장] | 사인공사 | A57530 | A68010
A59030 | A68010 | FS | A59030 | 0 | 실내천정도장 [마감도장] | 사인공사 | A59030 | A68010
A41810 | A68010 | FS | A41810 | 0 | 비닐타일 [타일시공] | 사인공사 | A41810 | A68010
A66010 | A68010 | FS | A66010 | 0 | 화장실기구설치(거울, 큐비클) | 사인공사 | A66010 | A68010
A66510 | A68010 | FS | A66510 | 0 | 가전공사 | 사인공사 | A66510 | A68010
A53520 | A68010 | FS | A53520 | 0 | 세대 문설치 [문짝설치] | 사인공사 | A53520 | A68010
A48530 | A62510 | FS | A48530 | 0 | 석고보드 벽공사 [석고보드시공] | 걸레받이시공 [걸레받이설치] | A48530 | A62510
A41510 | A64010 | FS | A41510 | 0 | 기준먹메김 | 계단잡철물공사 [설치] | A41510 | A64010
A41510 | A44510 | FS | A41510 | 0 | 기준먹메김 | 조적시공 [운반작업] | A41510 | A44510
T10010 | T10020 |  |  |  | 가설휀스A [기준선측량, 마킹] | 가설휀스A [굴착]
T10020 | T10030 |  |  |  | 가설휀스A [굴착] | 가설휀스A [다짐]
T10030 | T10040 |  |  |  | 가설휀스A [다짐] | 가설휀스A [기초설치]
T10040 | T10050 |  |  |  | 가설휀스A [기초설치] | 가설휀스A [되메우기]
T10050 | T10060 |  |  |  | 가설휀스A [되메우기] | 가설휀스A [철골설치]
T10060 | T10070 |  |  |  | 가설휀스A [철골설치] | 가설휀스A [판넬설치]
T10070 | T10080 |  |  |  | 가설휀스A [판넬설치] | 가설휀스A [이미지 랩핑]
T10080 | T10090 |  |  |  | 가설휀스A [이미지 랩핑] | 가설휀스A [검사]
T10090 |  |  |  |  | 가설휀스A [검사] | #N/A
T11010 | T11020 |  |  |  | 가설휀스B [기준선측량, 마킹] | 가설휀스B [굴착]
T11020 | T11030 |  |  |  | 가설휀스B [굴착] | 가설휀스B [다짐]
T11030 | T11040 |  |  |  | 가설휀스B [다짐] | 가설휀스B [기초설치]
T11040 | T11050 |  |  |  | 가설휀스B [기초설치] | 가설휀스B [되메우기]
T11050 | T11060 |  |  |  | 가설휀스B [되메우기] | 가설휀스B [철골설치]
T11060 | T11070 |  |  |  | 가설휀스B [철골설치] | 가설휀스B [판넬설치]
T11070 | T11080 |  |  |  | 가설휀스B [판넬설치] | 가설휀스B [검사]
T11080 |  |  |  |  | 가설휀스B [검사] | #N/A
T12010 | T12020 |  |  |  | 가설휀스C [기준선측량, 마킹] | 가설휀스C [굴착]
T12020 | T12030 |  |  |  | 가설휀스C [굴착] | 가설휀스C [다짐]
T12030 | T12040 |  |  |  | 가설휀스C [다짐] | 가설휀스C [철골설치]
T12040 | T12050 |  |  |  | 가설휀스C [철골설치] | 가설휀스C [판넬설치]
T12050 | T12060 |  |  |  | 가설휀스C [판넬설치] | 가설휀스C [검사]
T12060 | T20010 |  |  |  | 가설휀스C [검사] | 매직판넬 [지반보강]
T20010 | T20020 |  |  |  | 매직판넬 [지반보강] | 매직판넬 [기준선측량, 마킹]
T20020 | T20030 |  |  |  | 매직판넬 [기준선측량, 마킹] | 매직판넬 [프레임설치]
T20030 | T20040 |  |  |  | 매직판넬 [프레임설치] | 매직판넬 [판넬설치]
T20040 | T20050 |  |  |  | 매직판넬 [판넬설치] | 매직판넬 [이미지 랩핑]
T20050 | T20060 |  |  |  | 매직판넬 [이미지 랩핑] | 매직판넬 [검사]
T20060 | W10010 |  |  |  | 매직판넬 [검사] | #N/A
W10010 | W10020 |  |  |  | #N/A | #N/A
W10020 | W10030 |  |  |  | #N/A | #N/A
W10030 | W10040 |  |  |  | #N/A | #N/A
W10040 | W10050 |  |  |  | #N/A | #N/A
W10050 | W10060 |  |  |  | #N/A | #N/A
W10060 | W10070 |  |  |  | #N/A | #N/A
W10070 | W11010 |  |  |  | #N/A | #N/A
W11010 | W11020 |  |  |  | #N/A | #N/A
W11020 | W11030 |  |  |  | #N/A | #N/A
W11030 | W11040 |  |  |  | #N/A | #N/A
W11040 | D10010 |  |  |  | #N/A | #N/A
D10010 | D10020 |  |  |  | #N/A | #N/A
D10020 | D10030 |  |  |  | #N/A | #N/A
D10030 | D11010 |  |  |  | #N/A | #N/A
D11010 | D12010 |  |  |  | #N/A | #N/A
D12010 | D12020 |  |  |  | #N/A | #N/A
D12020 | D12030 |  |  |  | #N/A | #N/A
D12030 | D12040 |  |  |  | #N/A | #N/A
D12040 | D13010 |  |  |  | #N/A | #N/A
D13010 | D14010 |  |  |  | #N/A | #N/A
D14010 | R10010 |  |  |  | #N/A | #N/A
R10010 | R10020 |  |  |  | #N/A | #N/A
R10020 | R11010 |  |  |  | #N/A | #N/A
R11010 | R11020 |  |  |  | #N/A | #N/A
R11020 | R11030 |  |  |  | #N/A | #N/A
R11030 | R12010 |  |  |  | #N/A | #N/A
R12010 | R12020 |  |  |  | #N/A | #N/A
R12020 | R12030 |  |  |  | #N/A | #N/A
R12030 | R13010 |  |  |  | #N/A | #N/A
R13010 | R13020 |  |  |  | #N/A | #N/A
R13020 | R13030 |  |  |  | #N/A | #N/A
R13030 | R14010 |  |  |  | #N/A | #N/A
R14010 | R14020 |  |  |  | #N/A | #N/A
R14020 | R14030 |  |  |  | #N/A | #N/A
R14030 | R15010 |  |  |  | #N/A | #N/A
R15010 | R15020 |  |  |  | #N/A | #N/A
R15020 | R15030 |  |  |  | #N/A | #N/A
R15030 | R16010 |  |  |  | #N/A | #N/A
R16010 | R16020 |  |  |  | #N/A | #N/A
R16020 | R16030 |  |  |  | #N/A | #N/A
R16030 | R17010 |  |  |  | #N/A | #N/A
R17010 | R17020 |  |  |  | #N/A | #N/A
R17020 |  |  |  |  | #N/A | #N/A

## 평면
| 1 | 2 | 3
A |  |  |  | 오피스 | A1 | A3 | B1 | C1 | C2 | D2
|  |  |  | 코어 | B2
|  |  |  | 로비 | A2
B |  |  |  | 화장실 | B3
|  |  |  | 휴게실 | D1
C
D
오피스
오피스
코어
화장실
휴게실
로비
오피스

## Work
A415 | 기준먹메김
A418 | 비닐타일
A430 | 무근타설
A445 | 조적시공
A450 | 미장공사
A455 | 단열벽공사
A460 | 단열천정공사
A475 | 시멘트보드 벽공사
A485 | 석고보드 벽공사
A490 | 단열바닥공사
A495 | 실내방수시공
A505 | 천정틀시공
A510 | 석고보드 천정공사
A515 | 세대창호설치
A520 | 그릴설치
A525 | 공용부창호설치
A530 | 공용부문설치
A535 | 세대 문설치
A540 | 유리문설치
A545 | 바닥난방시스템시공
A550 | 석재시공
A565 | 화장실바닥타일시공
A570 | 벽타일시공
A575 | 실내벽도장
A580 | 유리설치
A590 | 실내천정도장
A595 | 계단실 텍스 천정공사
A600 | SMC 천장시공
A605 | 실내바닥도장(에폭시)
A607 | 세면대설치
A610 | 계단실 비닐타일
A615 | Access Floor시공
A620 | 마루시공
A625 | 걸레받이시공
A630 | 도배공사
A640 | 계단잡철물공사
A660 | 화장실기구설치
A665 | 가전공사
A670 | 가구공사
A675 | 기타공사
A680 | 사인공사

## temp
act_id | category | act_name | productivity | wp_code | id | wp_name_ko | wp_name_en | step | act_name_en | logic_check
T10010 | 가설공사 | 가설휀스A [기준선측량, 마킹] | 5 | T100 | 10 | 가설휀스A | fence | line_marking | fence-line_marking | T10010
T10020 | 가설공사 | 가설휀스A [굴착] | 3 | T100 | 20 | 가설휀스A | fence | excavation | fence-excavation | T10020
T10030 | 가설공사 | 가설휀스A [다짐] | 3 | T100 | 30 | 가설휀스A | fence | compaction | fence-compaction | T10030
T10040 | 가설공사 | 가설휀스A [기초설치] | 3 | T100 | 40 | 가설휀스A | fence | foundation | fence-foundation | T10040
T10050 | 가설공사 | 가설휀스A [되메우기] | 3 | T100 | 50 | 가설휀스A | fence | backfilling | fence-backfilling | T10050
T10060 | 가설공사 | 가설휀스A [철골설치] | 3 | T100 | 60 | 가설휀스A | fence | steel | fence-steel | T10060
T10070 | 가설공사 | 가설휀스A [판넬설치] | 5 | T100 | 70 | 가설휀스A | fence | panel | fence-panel | T10070
T10080 | 가설공사 | 가설휀스A [이미지 랩핑] | 10 | T100 | 80 | 가설휀스A | fence | wrapping | fence-wrapping | T10080
T10090 | 가설공사 | 가설휀스A [검사] | 20 | T100 | 90 | 가설휀스A | fence | inspection | fence-inspection | T10090
T30010 | 가설공사 | 타워크레인설치 [기초거푸집] | 1 | T300 | 10 | 타워크레인설치 | t-crane_installation | form | t-crane_installation-form | T30010
T30020 | 가설공사 | 타워크레인설치 [기초철근] | 1 | T300 | 20 | 타워크레인설치 | t-crane_installation | rebar | t-crane_installation-rebar | T30020
T30030 | 가설공사 | 타워크레인설치 [기초타설] | 1 | T300 | 30 | 타워크레인설치 | t-crane_installation | casting | t-crane_installation-casting | T30030
T30031 | 가설공사 | 타워크레인설치 [양생1] | 1 | T300 | 31 | 타워크레인설치 | t-crane_installation | curing1 | t-crane_installation-curing1 | T30031
T30032 | 가설공사 | 타워크레인설치 [양생2] | 1 | T300 | 32 | 타워크레인설치 | t-crane_installation | curing2 | t-crane_installation-curing2 | T30032
T30033 | 가설공사 | 타워크레인설치 [양생3] | 1 | T300 | 33 | 타워크레인설치 | t-crane_installation | curing3 | t-crane_installation-curing3 | T30033
T30034 | 가설공사 | 타워크레인설치 [양생4] | 1 | T300 | 34 | 타워크레인설치 | t-crane_installation | curing4 | t-crane_installation-curing4 | T30034
T30035 | 가설공사 | 타워크레인설치 [양생5] | 1 | T300 | 35 | 타워크레인설치 | t-crane_installation | curing5 | t-crane_installation-curing5 | T30035
T30036 | 가설공사 | 타워크레인설치 [양생6] | 1 | T300 | 36 | 타워크레인설치 | t-crane_installation | curing6 | t-crane_installation-curing6 | T30036
T30040 | 가설공사 | 타워크레인설치 [설치] | 1 | T300 | 40 | 타워크레인설치 | t-crane_installation | installation | t-crane_installation-installation | T30040
T30050 | 가설공사 | 타워크레인설치 [검사] | 1 | T300 | 50 | 타워크레인설치 | t-crane_installation | inspection | t-crane_installation-inspection | T30050
T32010 | 가설공사 | 타워크레인 [해체장비설치] | 1 | T320 | 10 | 타워크레인해체 | t-crane_dismantling | machine | t-crane_dismantling-machine | T32010
T32020 | 가설공사 | 타워크레인 [해체] | 1 | T320 | 20 | 타워크레인해체 | t-crane_dismantling | dismantling | t-crane_dismantling-dismantling | T32020
T35010 | 가설공사 | 리프트카설치 [기초거푸집] | 1 | T350 | 10 | 리프트카설치 | lift_installation | form | lift_installation-form | T35010
T35020 | 가설공사 | 리프트카설치 [기초철근] | 1 | T350 | 20 | 리프트카설치 | lift_installation | rebar | lift_installation-rebar | T35020
T35030 | 가설공사 | 리프트카설치 [기초타설] | 1 | T350 | 30 | 리프트카설치 | lift_installation | casting | lift_installation-casting | T35030
T35031 | 가설공사 | 리프트카설치 [양생1] | 1 | T350 | 31 | 리프트카설치 | lift_installation | curing1 | lift_installation-curing1 | T35031
T35032 | 가설공사 | 리프트카설치 [양생2] | 1 | T350 | 32 | 리프트카설치 | lift_installation | curing2 | lift_installation-curing2 | T35032
T35033 | 가설공사 | 리프트카설치 [양생3] | 1 | T350 | 33 | 리프트카설치 | lift_installation | curing3 | lift_installation-curing3 | T35033
T35034 | 가설공사 | 리프트카설치 [양생4] | 1 | T350 | 34 | 리프트카설치 | lift_installation | curing4 | lift_installation-curing4 | T35034
T35035 | 가설공사 | 리프트카설치 [양생5] | 1 | T350 | 35 | 리프트카설치 | lift_installation | curing5 | lift_installation-curing5 | T35035
T35036 | 가설공사 | 리프트카설치 [양생6] | 1 | T350 | 36 | 리프트카설치 | lift_installation | curing6 | lift_installation-curing6 | T35036
T35040 | 가설공사 | 리프트카설치 [설치] | 1 | T350 | 40 | 리프트카설치 | lift_installation | installation | lift_installation-installation | T35040
T35050 | 가설공사 | 리프트카설치 [검사] | 1 | T350 | 50 | 리프트카설치 | lift_installation | inspection | lift_installation-inspection | T35050
T37010 | 가설공사 | 리프트카 [해체] | 1 | T370 | 10 | 리프트카 | lift_dismantling | dismantling | lift_dismantling-dismantling | T37010
M00009 | milestone | [7 empty] | project_completion
M00001 | milestone | [7 empty] | project_start | M00001
M00007 | milestone | [7 empty] | elevator | M00007

## civil
act_id | category | act_name | productivity | wp_code | id | wp_name_ko | wp_name_en | step | act_name_en | logic_check
W10010 | 흙막이공사 | CIP공사 [기준선측량, 마킹] | 10 | W100 | 10 | CIP공사 | CIP | line_marking | CIP-line_marking | W10010
W10020 | 흙막이공사 | CIP공사 [가이드빔설치] | 5 | W100 | 20 | CIP공사 | CIP | guidebeam | CIP-guidebeam | W10020
W10030 | 흙막이공사 | CIP공사 [지반보강] | 4 | W100 | 30 | CIP공사 | CIP | soil_compaction_for_machine | CIP-soil_compaction_for_machine | W10030
W10040 | 흙막이공사 | CIP공사 [굴착, 철근망, 철골삽입]1 | 3 | W100 | 40 | CIP공사 | CIP | dig&rebar_1 | CIP-dig&rebar_1 | W10040
W10050 | 흙막이공사 | CIP공사 [CIP타설]1 | 3 | W100 | 50 | CIP공사 | CIP | casting_1 | CIP-casting_1 | W10050
W10050 | 흙막이공사 | CIP공사 [굴착, 철근망, 철골삽입]2 | 3 | W100 | 50 | CIP공사 | CIP | dig&rebar_2 | CIP-dig&rebar_2 | W10050
W10050 | 흙막이공사 | CIP공사 [CIP타설]2 | 3 | W100 | 50 | CIP공사 | CIP | casting_2 | CIP-casting_2 | W10050
W10050 | 흙막이공사 | CIP공사 [굴착, 철근망, 철골삽입]3 | 3 | W100 | 50 | CIP공사 | CIP | dig&rebar_3 | CIP-dig&rebar_3 | W10050
W10050 | 흙막이공사 | CIP공사 [CIP타설]3 | 3 | W100 | 50 | CIP공사 | CIP | casting_3 | CIP-casting_3 | W10050
W10060 | 흙막이공사 | CIP공사 [캡빔 배근] | 10 | W100 | 60 | CIP공사 | CIP | capbeam | CIP-capbeam | W10060
W10070 | 흙막이공사 | CIP공사 [캡빔타설] | 10 | W100 | 70 | CIP공사 | CIP | capbeam_casting | CIP-capbeam_casting | W10070
W11010 | 흙막이공사 | 차수공사 [기준선측량, 마킹] | 10 | W110 | 10 | 차수공사 | waterblock | line_marking | waterblock-line_marking | W11010
W11020 | 흙막이공사 | 차수공사 [굴착, 배관삽입] | 5 | W110 | 20 | 차수공사 | waterblock | dig&piping | waterblock-dig&piping | W11020
W11030 | 흙막이공사 | 차수공사 [차수재주입] | 5 | W110 | 30 | 차수공사 | waterblock | injection | waterblock-injection | W11030
W11040 | 흙막이공사 | 차수공사 [정리] | 10 | W110 | 40 | 차수공사 | waterblock | cleaning | waterblock-cleaning | W11040
D10010 | 토공사 | 시험굴착 [계획수립] | 10 | D100 | 10 | 시험굴착 | excavation_test | planning | excavation_test-planning | D10010
D10020 | 토공사 | 시험굴착 [굴착] | 1 | D100 | 20 | 시험굴착 | excavation_test | excavation | excavation_test-excavation | D10020
D10030 | 토공사 | 시험굴착 [검사] | 1 | D100 | 30 | 시험굴착 | excavation_test | inspection | excavation_test-inspection | D10030
D11010 | 토공사 | 굴착공사 [장비굴착] | 5 | D110 | 10 | 굴착공사 | excavation | 0 | excavation-0 | D11010
R10010 | 흙막이지지공사 | 지지말뚝공사 [기준선측량, 마킹] |  | R100 | 10 | 지지말뚝공사 | post_pile | line_marking | post_pile-line_marking | R10010
R10020 | 흙막이지지공사 | 지지말뚝공사 [포스트파일설치] |  | R100 | 20 | 지지말뚝공사 | post_pile | dig&piling | post_pile-dig&piling | R10020
R11010 | 흙막이지지공사 | 스트러트설치 [Wale설치] |  | R110 | 10 | 스트러트설치 | strut_installation | wale | strut_installation-wale | R11010
R11020 | 흙막이지지공사 | 스트러트설치 [스트러트설치] |  | R110 | 20 | 스트러트설치 | strut_installation | strut | strut_installation-strut | R11020
R11030 | 흙막이지지공사 | 스트러트설치 [검사] |  | R110 | 30 | 스트러트설치 | strut_installation | inspection | strut_installation-inspection | R11030
R12010 | 흙막이지지공사 | 스트러트해체 [안전성확인] |  | R120 | 10 | 스트러트해체 | strut_dismatling | check | strut_dismatling-check | R12010
R12020 | 흙막이지지공사 | 스트러트해체 [해체] |  | R120 | 20 | 스트러트해체 | strut_dismatling | remove | strut_dismatling-remove | R12020

## structure
act_id | category | act_name | productivity | wp_code | id | wp_name_ko | wp_name_en | step | act_name_en | logic_check
F20010 | 기초공사 | 기초판 공사 [방습층설치, 버림타설] | 4 | F200 | 10 | 기초판 공사 | foundation | vapor_proof&lean_conc. | foundation-vapor_proof&lean_conc. | F20010
F20020 | 기초공사 | 기초판 공사 [측량, 먹놓기] | 4 | F200 | 20 | 기초판 공사 | foundation | line_marking | foundation-line_marking | F20020
F20030 | 기초공사 | 기초판 공사 [철근설치] | 2 | F200 | 30 | 기초판 공사 | foundation | re-bar | foundation-re-bar | F20030
F20040 | 기초공사 | 기초판 공사 [거푸집설치] | 2 | F200 | 40 | 기초판 공사 | foundation | form | foundation-form | F20040
F20050 | 기초공사 | 기초판 공사 [레미콘타설] | 3 | F200 | 50 | 기초판 공사 | foundation | casting | foundation-casting | F20050
F20051 | 기초공사 | 기초판 공사 [양생] | 3 | F200 | 51 | 기초판 공사 | foundation | curing | foundation-curing | F20051
F20060 | 기초공사 | 기초판 공사 [거푸집해체] | 3 | F200 | 60 | 기초판 공사 | foundation | dismantling | foundation-dismantling | F20060
F20070 | 기초공사 | 기초판 공사 [되메우기] | 5 | F200 | 70 | 기초판 공사 | foundation | backfill | foundation-backfill | F20070
S10010 | 골조공사 | 철콘골조공사(수직) [측량, 먹놓기] | 5 | S100 | 10 | 철콘골조공사(수직) | rc_structure_vertical | line_marking | rc_structure_vertical-line_marking | S10010
S10020 | 골조공사 | 철콘골조공사(수직) [철근설치] | 3 | S100 | 20 | 철콘골조공사(수직) | rc_structure_vertical | re-bar | rc_structure_vertical-re-bar | S10020
S10030 | 골조공사 | 철콘골조공사(수직) [매입물설치] | 3 | S100 | 30 | 철콘골조공사(수직) | rc_structure_vertical | embedding | rc_structure_vertical-embedding | S10030
S10040 | 골조공사 | 철콘골조공사(수직) [거푸집설치] | 3 | S100 | 40 | 철콘골조공사(수직) | rc_structure_vertical | form | rc_structure_vertical-form | S10040
S10050 | 골조공사 | 철콘골조공사(수직) [검측] | 5 | S100 | 50 | 철콘골조공사(수직) | rc_structure_vertical | inspection | rc_structure_vertical-inspection | S10050
S10060 | 골조공사 | 철콘골조공사(수직) [레미콘타설] | 5 | S100 | 60 | 철콘골조공사(수직) | rc_structure_vertical | casting | rc_structure_vertical-casting | S10060
S10061 | 골조공사 | 철콘골조공사(수직) [양생] | 5 | S100 | 61 | 철콘골조공사(수직) | rc_structure_vertical | curing | rc_structure_vertical-curing | S10061
S10070 | 골조공사 | 철콘골조공사(수직) [거푸집해체] | 3 | S100 | 70 | 철콘골조공사(수직) | rc_structure_vertical | dismantling | rc_structure_vertical-dismantling | S10070
S11010 | 골조공사 | 철콘골조공사(수평) [거푸집설치] | 2 | S110 | 10 | 철콘골조공사(수평) | rc_structure_horizontal | form | rc_structure_horizontal-form | S11010
S11020 | 골조공사 | 철콘골조공사(수평) [철근설치] | 3 | S110 | 20 | 철콘골조공사(수평) | rc_structure_horizontal | re-bar | rc_structure_horizontal-re-bar | S11020
S11030 | 골조공사 | 철콘골조공사(수평) [매입물설치] | 3 | S110 | 30 | 철콘골조공사(수평) | rc_structure_horizontal | embedding | rc_structure_horizontal-embedding | S11030
S11040 | 골조공사 | 철콘골조공사(수평) [검측] | 5 | S110 | 40 | 철콘골조공사(수평) | rc_structure_horizontal | inspection | rc_structure_horizontal-inspection | S11040
S11050 | 골조공사 | 철콘골조공사(수평) [레미콘타설] | 5 | S110 | 50 | 철콘골조공사(수평) | rc_structure_horizontal | casting | rc_structure_horizontal-casting | S11050
S11051 | 골조공사 | 철콘골조공사(수평) [양생] | 5 | S110 | 51 | 철콘골조공사(수평) | rc_structure_horizontal | curing | rc_structure_horizontal-curing | S11051
S11060 | 골조공사 | 철콘골조공사(수평) [거푸집해체] | 3 | S110 | 60 | 철콘골조공사(수평) | rc_structure_horizontal | dismantling | rc_structure_horizontal-dismantling | S11060

## finishing
act_id | category | act_name | productivity | wp_code | id | wp_name_ko | wp_name_en | step | act_name_en | logic_check
A41510 | 칸막이벽공사 | 기준먹메김 | 2 | A415 | 10 | 기준먹메김 | benchmark | 0 | benchmark-0 | A41510
A44510 | 칸막이벽공사 | 조적시공 [운반작업] | 2 | A445 | 10 | 조적시공 | masonry | material_delivery | masonry-material_delivery | A44510
A44520 | 칸막이벽공사 | 조적시공 [조적1차] | 1 | A445 | 20 | 조적시공 | masonry | 1st | masonry-1st | A44520
A44521 | 칸막이벽공사 | 조적시공 [조적2차] | 1 | A445 | 21 | 조적시공 | masonry | 2nd | masonry-2nd | A44521
A45010 | 칸막이벽공사 | 미장공사 [바탕면처리] | 2 | A450 | 10 | 미장공사 | plastering | surface | plastering-surface | A45010
A45011 | 칸막이벽공사 | 미장공사 [미장 초벌] | 1 | A450 | 11 | 미장공사 | plastering | 1st | plastering-1st | A45011
A45012 | 칸막이벽공사 | 미장공사 [미장 정벌] | 1 | A450 | 12 | 미장공사 | plastering | final | plastering-final | A45012
A48510 | 칸막이벽공사 | 석고보드 벽공사 [먹놓기] | 2 | A485 | 10 | 석고보드 벽공사 | drywall | line_marking | drywall-line_marking | A48510
A48520 | 칸막이벽공사 | 석고보드 벽공사 [스터드] | 1 | A485 | 20 | 석고보드 벽공사 | drywall | stud | drywall-stud | A48520
A48530 | 칸막이벽공사 | 석고보드 벽공사 [석고보드시공] | 1 | A485 | 30 | 석고보드 벽공사 | drywall | gypsum_board | drywall-gypsum_board | A48530
A50510 | 마감공사 | 천정틀시공 [행거설치] | 1 | A505 | 10 | 천정틀시공 | ceiling_frame | hanger | ceiling_frame-hanger | A50510
A50520 | 마감공사 | 천정틀시공 [틀설치] | 1 | A505 | 20 | 천정틀시공 | ceiling_frame | frame | ceiling_frame-frame | A50520
A51010 | 마감공사 | 석고보드 천정공사 [석고보드시공] | 1 | A510 | 10 | 석고보드 천정공사 | ceiling_board | gypsum_board | ceiling_board-gypsum_board | A51010
A52010 | 마감공사 | 그릴설치 [설치] | 1 | A520 | 10 | 그릴설치 | grill_installation | 0 | grill_installation-0 | A52010
A53010 | 마감공사 | Steel문설치 [문틀설치] | 1 | A530 | 10 | Steel문설치 | steel_door | frame | steel_door-frame | A53010
A53020 | 마감공사 | Steel문설치 [문짝설치] | 1 | A530 | 20 | Steel문설치 | steel_door | door | steel_door-door | A53020
A55010 | 마감공사 | 석재시공 | 1 | A550 | 10 | 석재시공 | finishing stone | 0 | finishing stone-0 | A55010
A57510 | 마감공사 | 실내벽도장 [바탕면처리] | 2 | A575 | 10 | 실내벽도장 | inside_wall_painting | surface | inside_wall_painting-surface | A57510
A57520 | 마감공사 | 실내벽도장 [도장] | 1 | A575 | 20 | 실내벽도장 | inside_wall_painting | 1st | inside_wall_painting-1st | A57520
A57530 | 마감공사 | 실내벽도장 [마감도장] | 1 | A575 | 30 | 실내벽도장 | inside_wall_painting | final | inside_wall_painting-final | A57530
A58010 | 마감공사 | 유리설치 [설치] | 1 | A580 | 10 | 유리설치 | glazing | 0 | glazing-0 | A58010
A59010 | 마감공사 | 실내천정도장 [바탕면처리] | 1 | A590 | 10 | 실내천정도장 | ceiling_painting | surface | ceiling_painting-surface | A59010
A59020 | 마감공사 | 실내천정도장 [도장] | 1 | A590 | 20 | 실내천정도장 | ceiling_painting | 1st | ceiling_painting-1st | A59020
A59030 | 마감공사 | 실내천정도장 [마감도장] | 1 | A590 | 30 | 실내천정도장 | ceiling_painting | final | ceiling_painting-final | A59030
A59510 | 마감공사 | 계단실 텍스 천정공사 [천정설치] | 1 | A595 | 10 | 계단실 텍스 천정공사 | ceiling_tex | 0 | ceiling_tex-0 | A59510
A60510 | 마감공사 | 실내바닥도장(에폭시) [바탕면처리] | 1 | A605 | 10 | 실내바닥도장(에폭시) | inside_floor_painting | surface | inside_floor_painting-surface | A60510
A60520 | 마감공사 | 실내바닥도장(에폭시) [도장] | 1 | A605 | 20 | 실내바닥도장(에폭시) | inside_floor_painting | 1st | inside_floor_painting-1st | A60520
A60530 | 마감공사 | 실내바닥도장 [마감도장] | 1 | A605 | 30 | 실내바닥도장 | inside_floor_painting | final | inside_floor_painting-final | A60530
A61010 | 마감공사 | 계단실 비닐타일 [바탕면처리] | 1 | A610 | 10 | 계단실 비닐타일 | stair_floor_tile | surface | stair_floor_tile-surface | A61010
A61020 | 마감공사 | 계단실 비닐타일 [타일시공] | 1 | A610 | 20 | 계단실 비닐타일 | stair_floor_tile | tile | stair_floor_tile-tile | A61020
A62510 | 마감공사 | 걸레받이시공 [걸레받이설치] | 2 | A625 | 10 | 걸레받이시공 | base_board | 0 | base_board-0 | A62510
A64010 | 마감공사 | 계단잡철물공사 [설치] | 1 | A640 | 10 | 계단잡철물공사 | miscellaneous | 0 | miscellaneous-0 | A64010
A60020 | 마감공사 | 바리솔, 루버 천장시공 [천정설치] | 1 | A600 | 20 | 바리솔, 루버 천장시공 | loover | 0 | loover-0 | A60020
A67010 | 마감공사 | 가구공사 | 1 | A670 | 10 | 가구공사 | furniture | 0 | furniture-0 | A67010
A41810 | 마감공사 | 비닐타일 [타일시공] | 1 | A418 | 10 | 비닐타일 | inside_floor_tile | 0 | inside_floor_tile-0 | A41810
A43010 | 마감공사 | 무근타설 [레벨작업] | 2 | A430 | 10 | 무근타설 | concreting | level_marking | concreting-level_marking | A43010
A43020 | 마감공사 | 무근타설 [무근타설] | 2 | A430 | 20 | 무근타설 | concreting | casting | concreting-casting | A43020
A43021 | 마감공사 | 무근타설 [바닥미장] | 2 | A430 | 21 | 무근타설 | concreting | floor_plastering | concreting-floor_plastering | A43021
A43022 | 마감공사 | 무근타설 [양생] | 2 | A430 | 22 | 무근타설 | concreting | curing | concreting-curing | A43022
A45510 | 마감공사 | 단열벽공사 [바탕면처리] | 2 | A455 | 10 | 단열벽공사 | wall_insulation | surface | wall_insulation-surface | A45510
A45520 | 마감공사 | 단열벽공사 [단열재설치] | 1 | A455 | 20 | 단열벽공사 | wall_insulation | insulation | wall_insulation-insulation | A45520
A61510 | 마감공사 | Access Floor시공 [분진방지도장) | 1 | A615 | 10 | Access Floor시공 | inside_floor_accessfloor | floor_coating | inside_floor_accessfloor-floor_coating | A61510
A61520 | 마감공사 | Access Floor시공 [먹메김] | 2 | A615 | 20 | Access Floor시공 | inside_floor_accessfloor | line_marking | inside_floor_accessfloor-line_marking | A61520
A61530 | 마감공사 | Access Floor시공 [하지작업] | 1 | A615 | 30 | Access Floor시공 | inside_floor_accessfloor | frame | inside_floor_accessfloor-frame | A61530
A61540 | 마감공사 | Access Floor시공 [바닥판설치] | 1 | A615 | 40 | Access Floor시공 | inside_floor_accessfloor | tile | inside_floor_accessfloor-tile | A61540
A66510 | 마감공사 | 가전공사 | 1 | A665 | 10 | 가전공사 | electric_appliances | 0 | electric_appliances-0 | A66510
A46010 | 마감공사 | 단열천정공사 [바탕면처리] | 2 | A460 | 10 | 단열천정공사 | ceiling_insulation | surface | ceiling_insulation-surface | A46010
A46020 | 마감공사 | 단열천정공사 [단열재설치] | 1 | A460 | 20 | 단열천정공사 | ceiling_insulation | insulation | ceiling_insulation-insulation | A46020
A53510 | 마감공사 | 목문설치 [문틀설치] | 2 | A535 | 10 | 목문설치 | wood_door | frame | wood_door-frame | A53510
A53520 | 마감공사 | 목문설치 [문짝설치] | 2 | A535 | 20 | 목문설치 | wood_door | door | wood_door-door | A53520
A54510 | 마감공사 | 바닥난방시스템시공 [바탕면정리] | 1 | A545 | 10 | 바닥난방시스템시공 | floor_heating_finishing | surface | floor_heating_finishing-surface | A54510
A54520 | 마감공사 | 바닥난방시스템시공 [기포타설] | 2 | A545 | 20 | 바닥난방시스템시공 | floor_heating_finishing | mortar_1st | floor_heating_finishing-mortar_1st | A54520
A54530 | 마감공사 | 바닥난방시스템시공 [방통타설/양생] | 2 | A545 | 30 | 바닥난방시스템시공 | floor_heating_finishing | mortar_final | floor_heating_finishing-mortar_final | A54530
A62010 | 마감공사 | 마루시공 [바탕면처리] | 1 | A620 | 10 | 마루시공 | inside_floor_woodtile | surface | inside_floor_woodtile-surface | A62010
A62020 | 마감공사 | 마루시공 [먹메김] | 2 | A620 | 20 | 마루시공 | inside_floor_woodtile | line_marking | inside_floor_woodtile-line_marking | A62020
A62030 | 마감공사 | 마루시공 [하지작업] | 1 | A620 | 30 | 마루시공 | inside_floor_woodtile | frame | inside_floor_woodtile-frame | A62030
A62040 | 마감공사 | 마루시공 [마루설치] | 1 | A620 | 40 | 마루시공 | inside_floor_woodtile | woodtile | inside_floor_woodtile-woodtile | A62040
A62050 | 마감공사 | 마루시공 [마감처리] | 1 | A620 | 50 | 마루시공 | inside_floor_woodtile | finishing | inside_floor_woodtile-finishing | A62050
A63010 | 마감공사 | 도배공사 [천정도배] | 1 | A630 | 10 | 도배공사 | inside_wall_paper | ceiling | inside_wall_paper-ceiling | A63010
A63020 | 마감공사 | 도배공사 [벽도배] | 1 | A630 | 20 | 도배공사 | inside_wall_paper | wall | inside_wall_paper-wall | A63020
A49510 | 마감공사 | 실내방수시공 [바탕면처리] | 1 | A495 | 10 | 실내방수시공 | inside_waterproofing | surface | inside_waterproofing-surface | A49510
A49520 | 마감공사 | 실내방수시공 [방수시공] | 1 | A495 | 20 | 실내방수시공 | inside_waterproofing | waterproofing | inside_waterproofing-waterproofing | A49520
A49530 | 마감공사 | 실내방수시공 [방수테스트] | 1 | A495 | 30 | 실내방수시공 | inside_waterproofing | test | inside_waterproofing-test | A49530
A49540 | 마감공사 | 실내방수시공 [보호몰탈] | 1 | A495 | 40 | 실내방수시공 | inside_waterproofing | protection | inside_waterproofing-protection | A49540
A56510 | 마감공사 | 화장실바닥타일시공 [바탕면처리] | 1 | A565 | 10 | 화장실바닥타일시공 | inside_floor_tile | surface | inside_floor_tile-surface | A56510
A56520 | 마감공사 | 화장실바닥타일시공 [타일시공] | 1 | A565 | 20 | 화장실바닥타일시공 | inside_floor_tile | tile | inside_floor_tile-tile | A56520
A57010 | 마감공사 | 벽타일시공 [타일시공] | 1 | A570 | 10 | 벽타일시공 | inside_wall_tile | 0 | inside_wall_tile-0 | A57010
A60010 | 마감공사 | SMC 천장시공 [천정설치] | 1 | A600 | 10 | SMC 천장시공 | ceiling_tile | 0 | ceiling_tile-0 | A60010
A60710 | 마감공사 | 세면대설치 [하지작업] | 1 | A607 | 10 | 세면대설치 | washbasin_installation | frame | washbasin_installation-frame | A60710
A60720 | 마감공사 | 세면대설치 [세면대설치] | 1 | A607 | 20 | 세면대설치 | washbasin_installation | basin | washbasin_installation-basin | A60720
A66010 | 마감공사 | 화장실기구설치(거울, 큐비클) | 1 | A660 | 10 | 화장실기구설치 | toilet_accessaries_nstallation | 0 | toilet_accessaries_nstallation-0 | A66010
A52510 | 외장공사 | AL창호설치 [창틀설치] | 1 | A525 | 10 | AL창호설치 | al_window | frame | al_window-frame | A52510
A52520 | 외장공사 | AL창호설치 [우레탄충진] | 1 | A525 | 20 | AL창호설치 | al_window | insulation_filling | al_window-insulation_filling | A52520
A52530 | 외장공사 | AL창호설치 [창설치] | 1 | A525 | 30 | AL창호설치 | al_window | window | al_window-window | A52530
A54010 | 외장공사 | 유리문설치 [바탕면정리] | 1 | A540 | 10 | 유리문설치 | window_door | surface | window_door-surface | A54010
A54020 | 외장공사 | 유리문설치 [하드웨어설치] | 1 | A540 | 20 | 유리문설치 | window_door | hardware | window_door-hardware | A54020
A54030 | 외장공사 | 유리문설치 [문설치] | 1 | A540 | 30 | 유리문설치 | window_door | door | window_door-door | A54030
A47510 | 외장공사 | 외부 벽공사 [기준선작업] | 2 | A475 | 10 | 외부 벽공사 | outside_wall_finishing | line_marking | outside_wall_finishing-line_marking | A47510
A47520 | 외장공사 | 외부 벽공사 [하지철물] | 1 | A475 | 20 | 외부 벽공사 | outside_wall_finishing | frame | outside_wall_finishing-frame | A47520
A47530 | 외장공사 | 외부 벽공사 [외부시공] | 1 | A475 | 30 | 외부 벽공사 | outside_wall_finishing | panel | outside_wall_finishing-panel | A47530
A51510 | 외장공사 | PVC창호설치 [창틀설치] | 1 | A515 | 10 | PVC창호설치 | pvc_window | frame | pvc_window-frame | A51510
A51520 | 외장공사 | PVC창호설치 [우레탄충진] | 1 | A515 | 20 | PVC창호설치 | pvc_window | insulation_filling | pvc_window-insulation_filling | A51520
A51530 | 외장공사 | PVC창호설치 [창설치] | 1 | A515 | 30 | PVC창호설치 | pvc_window | window | pvc_window-window | A51530

## logic
pred | succ | 관계 | Lag | 선행 | 후행
A41510 | A44510 | FS
A41510 | A45510 | FS
A41510 | A46010 | FS
A41510 | A47510 | FS
A41510 | A48510 | FS
A41810 | A66510 | FS
A41810 | A67010 | FS
A43010 | A43020 | FS
A43020 | A43021 | FS
A43021 | A43022 | FS
A43022 | A41810 | FS
A43022 | A57510 | FS
A43022 | A61510 | FS
A43022 | A63010 | FS
A43022 | A63020 | FS
A44510 | A44520 | FS
A44520 | A44521 | FS
A44521 | A45010 | FS
A45010 | A45011 | FS
A45011 | A45012 | FS
A45012 | A49510 | FS
A45012 | A57510 | FS
A45510 | A45520 | FS
A45520 | A48530 | FS
A46010 | A46020 | FS
A46020 | A50510 | FS
A47510 | A47520 | FS
A47520 | A47530 | FS
A47520 | A52510 | FS
A47530 | A47540 | FS
A47540 | M00009 | FS
A48510 | A48520 | FS
A48520 | A48530 | FS
A48520 | A51510 | FS
A48520 | A53010 | FS
A48520 | A53510 | FS
A48520 | A60020 | FS
A48530 | A43010 | FS
A48530 | A49510 | FS
A48530 | A50510 | FS
A48530 | A54510 | FS
A48530 | A55010 | FS
A48530 | A57510 | FS
A49510 | A49520 | FS
A49520 | A49530 | FS
A49530 | A49540 | FS
A49540 | A56510 | FS
A49540 | A57010 | FS
A50510 | A50520 | FS
A50520 | A51010 | FS
A50520 | A59510 | FS
A50520 | A60010 | FS
A51010 | A59010 | FS
A51010 | A63010 | FS
A51510 | A51520 | FS
A51520 | A51530 | FS
A51530 | A58010 | FS
A52510 | A52010 | FS
A52510 | A52520 | FS
A52510 | A52530 | FS
A52520 | A52530 | FS
A52530 | A54010 | FS
A52530 | A58010 | FS
A53010 | A53020 | FS
A53010 | A55010 | FS
A53020 | A67010 | FS
A53510 | A53520 | FS
A53510 | A54510 | FS
A53510 | A55010 | FS
A53520 | A66510 | FS
A54010 | A54020 | FS
A54020 | A54030 | FS
A54030 | A67010 | FS
A54510 | A54520 | FS
A54520 | A54530 | FS
A54530 | A51010 | FS
A54530 | A60510 | FS
A54530 | A62010 | FS
A55010 | M00009 | FS
A56510 | A56520 | FS
A56520 | A60010 | FS
A56520 | A60710 | FS
A57010 | A56510 | FS
A57010 | A60010 | FS
A57510 | A57520 | FS
A57520 | A50520 | FS
A57520 | A57530 | FS
A57520 | A61510 | FS
A57530 | A67010 | FS
A58010 | A62040 | FS
A58010 | A63010 | FS
A58010 | A63020 | FS
A59010 | A59020 | FS
A59020 | A59030 | FS
A59030 | A61020 | FS
A59030 | A67010 | FS
A59510 | M00009 | FS
A60010 | A60710 | FS
A60010 | A60720 | FS
A60510 | A60520 | FS
A60520 | A60530 | FS
A60530 | A61010 | FS
A60530 | A67010 | FS
A60710 | A60720 | FS
A60720 | A66010 | FS
A61010 | A61020 | FS
A61020 | A53020 | FS
A61020 | A62510 | FS
A61510 | A61520 | FS
A61520 | A61530 | FS
A61530 | A61540 | FS
A61540 | A66510 | FS
A62010 | A62020 | FS
A62020 | A62030 | FS
A62030 | A62040 | FS
A62040 | A62050 | FS
A62050 | A63010 | FS
A62050 | A66510 | FS
A62050 | A67010 | FS
A62510 | A63020 | FS
A62510 | A64010 | FS
A63010 | A63020 | FS
A63010 | A67010 | FS
A63020 | A66510 | FS
A63020 | A67010 | FS
A64010 | M00009 | FS
A66010 | A52510 | FS
A66510 | M00009 | FS
A67010 | A53520 | FS
A67010 | A66510 | FS
D10010 | D10020 | FS
D10020 | D10030 | FS
D10030 | D11010 | FS
D11010 | R10010 | FS
F20010 | F20020 | FS
F20020 | F20030 | FS
F20030 | F20040 | FS
F20040 | F20050 | FS
F20050 | F20051 | FS
F20051 | F20060 | FS
F20051 | T30010 | FS
F20060 | F20070 | FS
F20060 | T30010 | FS
F20070 | S10010 | FS
F20070 | T30010 | FS
M00001 | T10010 | FS
M00007 | T37010 | FS
R10010 | R10020 | FS
R10020 | R11010 | FS
R11010 | R11020 | FS
R11020 | R11030 | FS
R11030 | R12010 | FS
R12010 | R12020 | FS
R12020 | F20010 | FS
S10010 | S10020 | FS
S10020 | S10030 | FS
S10030 | S10040 | FS
S10040 | S10050 | FS
S10050 | S10060 | FS
S10060 | S10061 | FS
S10061 | S10070 | FS
S10070 | S11010 | FS
S11010 | S11020 | FS
S11020 | S11030 | FS
S11030 | S11040 | FS
S11040 | S11050 | FS
S11050 | S11051 | FS
S11051 | S11060 | FS
S11060 | A41510 | FS
S11060 | A45010 | FS
S11060 | A51510 | FS
S11060 | A60020 | FS
S11060 | M00007 | FS
S11060 | T35010 | FS
T10010 | T10020 | FS
T10020 | T10030 | FS
T10030 | T10040 | FS
T10040 | T10050 | FS
T10050 | T10060 | FS
T10060 | T10070 | FS
T10070 | T10080 | FS
T10080 | T10090 | FS
T10090 | W10010 | FS
T30010 | T30020 | FS
T30020 | T30030 | FS
T30030 | T30031 | FS
T30031 | T30032 | FS
T30032 | T30033 | FS
T30033 | T30034 | FS
T30034 | T30035 | FS
T30035 | T30036 | FS
T30036 | T30040 | FS
T30040 | T30050 | FS
T30050 | T32010 | FS
T32010 | T32020 | FS
T35010 | T35020 | FS
T35020 | T35030 | FS
T35030 | T35031 | FS
T35031 | T35032 | FS
T35032 | T35033 | FS
T35033 | T35034 | FS
T35034 | T35035 | FS
T35035 | T35036 | FS
T35036 | T35040 | FS
T35040 | T35050 | FS
T35050 | T37010 | FS
W10010 | W10020 | FS
W10020 | W10030 | FS
W10030 | W10040 | FS
W10040 | W10050 | FS
W10050 | W10060 | FS
W10060 | W10070 | FS
W10070 | W11010 | FS
W11010 | W11020 | FS
W11020 | W11030 | FS
W11030 | W11040 | FS
W11040 | D10010 | FS
T37010 | M00009 | FS
T32020 | M00009 | FS
A52010 | M00009 | FS
A60020 | M00009 | FS

## p6_relation
pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | delete_record_flag
Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | Delete This Row
T10010 | T10020 | FS | Not Started | Not Started
T10020 | T10030 | FS | Not Started | Not Started
T10030 | T10040 | FS | Not Started | Not Started
T10040 | T10050 | FS | Not Started | Not Started
T10050 | T10060 | FS | Not Started | Not Started
T10060 | T10070 | FS | Not Started | Not Started
T10070 | T10080 | FS | Not Started | Not Started
T10080 | T10090 | FS | Not Started | Not Started
T30010 | T30020 | FS | Not Started | Not Started
T30020 | T30030 | FS | Not Started | Not Started
T30030 | T30031 | FS | Not Started | Not Started
T30031 | T30032 | FS | Not Started | Not Started
T30032 | T30033 | FS | Not Started | Not Started
T30033 | T30034 | FS | Not Started | Not Started
T30034 | T30035 | FS | Not Started | Not Started
T30035 | T30036 | FS | Not Started | Not Started
T30036 | T30040 | FS | Not Started | Not Started
T30040 | T30050 | FS | Not Started | Not Started
T30050 | T32010 | FS | Not Started | Not Started
T32010 | T32020 | FS | Not Started | Not Started
T35010 | T35020 | FS | Not Started | Not Started
T35020 | T35030 | FS | Not Started | Not Started
T35030 | T35031 | FS | Not Started | Not Started
T35031 | T35032 | FS | Not Started | Not Started
T35032 | T35033 | FS | Not Started | Not Started
T35033 | T35034 | FS | Not Started | Not Started
T35034 | T35035 | FS | Not Started | Not Started
T35035 | T35036 | FS | Not Started | Not Started
T35036 | T35040 | FS | Not Started | Not Started
T35040 | T35050 | FS | Not Started | Not Started
T35050 | T37010 | FS | Not Started | Not Started
W10010 | W10020 | FS | Not Started | Not Started
W10020 | W10030 | FS | Not Started | Not Started
W10030 | W10040 | FS | Not Started | Not Started
W10040 | W10050 | FS | Not Started | Not Started
W10050 | W10060 | FS | Not Started | Not Started
W10060 | W10070 | FS | Not Started | Not Started
W10070 | W11010 | FS | Not Started | Not Started
W11010 | W11020 | FS | Not Started | Not Started
W11020 | W11030 | FS | Not Started | Not Started
W11030 | W11040 | FS | Not Started | Not Started
W11040 | D10010 | FS | Not Started | Not Started
D10010 | D10020 | FS | Not Started | Not Started
D10020 | D10030 | FS | Not Started | Not Started
D10030 | D11010 | FS | Not Started | Not Started
D11010 | R10010 | FS | Not Started | Not Started
R10010 | R10020 | FS | Not Started | Not Started
R10020 | R11010 | FS | Not Started | Not Started
R11010 | R11020 | FS | Not Started | Not Started
R11020 | R11030 | FS | Not Started | Not Started
R11030 | R12010 | FS | Not Started | Not Started
R12010 | R12020 | FS | Not Started | Not Started
R12020 | F20010 | FS | Not Started | Not Started
F20010 | F20020 | FS | Not Started | Not Started
F20020 | F20030 | FS | Not Started | Not Started
F20030 | F20040 | FS | Not Started | Not Started
F20040 | F20050 | FS | Not Started | Not Started
F20050 | F20051 | FS | Not Started | Not Started
F20051 | F20060 | FS | Not Started | Not Started
F20060 | F20070 | FS | Not Started | Not Started
F20070 | S10010 | FS | Not Started | Not Started
S10010 | S10020 | FS | Not Started | Not Started
S10020 | S10030 | FS | Not Started | Not Started
S10030 | S10040 | FS | Not Started | Not Started
S10040 | S10050 | FS | Not Started | Not Started
S10050 | S10060 | FS | Not Started | Not Started
S10060 | S10061 | FS | Not Started | Not Started
S10061 | S10070 | FS | Not Started | Not Started
S10070 | S11010 | FS | Not Started | Not Started
S11010 | S11020 | FS | Not Started | Not Started
S11020 | S11030 | FS | Not Started | Not Started
S11030 | S11040 | FS | Not Started | Not Started
S11040 | S11050 | FS | Not Started | Not Started
S11050 | S11051 | FS | Not Started | Not Started
S11051 | S11060 | FS | Not Started | Not Started
S11060 | A41510 | FS | Not Started | Not Started
A41510 | A44510 | FS | Not Started | Not Started
A44510 | A44520 | FS | Not Started | Not Started
A44520 | A44521 | FS | Not Started | Not Started
A44521 | A45010 | FS | Not Started | Not Started
A45010 | A45011 | FS | Not Started | Not Started
A45011 | A45012 | FS | Not Started | Not Started
A48510 | A48520 | FS | Not Started | Not Started
A48520 | A48530 | FS | Not Started | Not Started
A48530 | A50510 | FS | Not Started | Not Started
A50510 | A50520 | FS | Not Started | Not Started
A50520 | A51010 | FS | Not Started | Not Started
A53010 | A53020 | FS | Not Started | Not Started
A57510 | A57520 | FS | Not Started | Not Started
A57520 | A57530 | FS | Not Started | Not Started
A59010 | A59020 | FS | Not Started | Not Started
A59020 | A59030 | FS | Not Started | Not Started
A60510 | A60520 | FS | Not Started | Not Started
A60520 | A60530 | FS | Not Started | Not Started
A60530 | A61010 | FS | Not Started | Not Started
A61010 | A61020 | FS | Not Started | Not Started
A61020 | A62510 | FS | Not Started | Not Started
A62510 | A64010 | FS | Not Started | Not Started
A43010 | A43020 | FS | Not Started | Not Started
A43020 | A43021 | FS | Not Started | Not Started
A43021 | A43022 | FS | Not Started | Not Started
A45510 | A45520 | FS | Not Started | Not Started
A61510 | A61520 | FS | Not Started | Not Started
A61520 | A61530 | FS | Not Started | Not Started
A61530 | A61540 | FS | Not Started | Not Started
A61540 | A66510 | FS | Not Started | Not Started
A46010 | A46020 | FS | Not Started | Not Started
A53510 | A53520 | FS | Not Started | Not Started
A54510 | A54520 | FS | Not Started | Not Started
A54520 | A54530 | FS | Not Started | Not Started
A54530 | A62010 | FS | Not Started | Not Started
A62010 | A62020 | FS | Not Started | Not Started
A62020 | A62030 | FS | Not Started | Not Started
A62030 | A62040 | FS | Not Started | Not Started
A62040 | A62050 | FS | Not Started | Not Started
A62050 | A63010 | FS | Not Started | Not Started
A63010 | A63020 | FS | Not Started | Not Started
A49510 | A49520 | FS | Not Started | Not Started
A49520 | A49530 | FS | Not Started | Not Started
A49530 | A49540 | FS | Not Started | Not Started
A49540 | A56510 | FS | Not Started | Not Started
A56510 | A56520 | FS | Not Started | Not Started
A57010 | A60010 | FS | Not Started | Not Started
A60010 | A60710 | FS | Not Started | Not Started
A60710 | A60720 | FS | Not Started | Not Started
A60720 | A66010 | FS | Not Started | Not Started
A66010 | A52510 | FS | Not Started | Not Started
A52510 | A52520 | FS | Not Started | Not Started
A52520 | A52530 | FS | Not Started | Not Started
A52530 | A54010 | FS | Not Started | Not Started
A54010 | A54020 | FS | Not Started | Not Started
A54020 | A54030 | FS | Not Started | Not Started
A47510 | A47520 | FS | Not Started | Not Started
A47520 | A47530 | FS | Not Started | Not Started
A51510 | A51520 | FS | Not Started | Not Started
A51520 | A51530 | FS | Not Started | Not Started
A43022 | A41810 | FS | Not Started | Not Started
A48530 | A43010 | FS | Not Started | Not Started
A41510 | A45510 | FS | Not Started | Not Started
A41510 | A46010 | FS | Not Started | Not Started
A41510 | A47510 | FS | Not Started | Not Started
A41510 | A48510 | FS | Not Started | Not Started
A45012 | A49510 | FS | Not Started | Not Started
A48530 | A49510 | FS | Not Started | Not Started
A46020 | A50510 | FS | Not Started | Not Started
A54530 | A51010 | FS | Not Started | Not Started
A52510 | A52010 | FS | Not Started | Not Started
A47520 | A52510 | FS | Not Started | Not Started
A52510 | A52530 | FS | Not Started | Not Started
A48520 | A53010 | FS | Not Started | Not Started
A61020 | A53020 | FS | Not Started | Not Started
A48520 | A53510 | FS | Not Started | Not Started
A67010 | A53520 | FS | Not Started | Not Started
A48530 | A54510 | FS | Not Started | Not Started
A53510 | A54510 | FS | Not Started | Not Started
A48530 | A55010 | FS | Not Started | Not Started
A53010 | A55010 | FS | Not Started | Not Started
A57010 | A56510 | FS | Not Started | Not Started
A49540 | A57010 | FS | Not Started | Not Started
A48530 | A57510 | FS | Not Started | Not Started
A45012 | A57510 | FS | Not Started | Not Started
A43022 | A57510 | FS | Not Started | Not Started
A52530 | A58010 | FS | Not Started | Not Started
A51530 | A58010 | FS | Not Started | Not Started
A51010 | A59010 | FS | Not Started | Not Started
A50520 | A59510 | FS | Not Started | Not Started
A50520 | A60010 | FS | Not Started | Not Started
A56520 | A60010 | FS | Not Started | Not Started
A56520 | A60710 | FS | Not Started | Not Started
A60010 | A60720 | FS | Not Started | Not Started
A59030 | A61020 | FS | Not Started | Not Started
A57520 | A61510 | FS | Not Started | Not Started
A43022 | A61510 | FS | Not Started | Not Started
A58010 | A62040 | FS | Not Started | Not Started
A51010 | A63010 | FS | Not Started | Not Started
A58010 | A63010 | FS | Not Started | Not Started
A43022 | A63010 | FS | Not Started | Not Started
A58010 | A63020 | FS | Not Started | Not Started
A43022 | A63020 | FS | Not Started | Not Started
A67010 | A66510 | FS | Not Started | Not Started
A62050 | A66510 | FS | Not Started | Not Started
A53520 | A66510 | FS | Not Started | Not Started
A53020 | A67010 | FS | Not Started | Not Started
A57530 | A67010 | FS | Not Started | Not Started
A59030 | A67010 | FS | Not Started | Not Started
A63010 | A67010 | FS | Not Started | Not Started
A63020 | A67010 | FS | Not Started | Not Started
A62050 | A67010 | FS | Not Started | Not Started
A60530 | A67010 | FS | Not Started | Not Started
A54030 | A67010 | FS | Not Started | Not Started
M00001 | T10010 | FS | Not Started | Not Started
A55010 | M00009 | FS | Not Started | Not Started
A53510 | A55010 | FS | Not Started | Not Started
A57520 | A50520 | FS | Not Started | Not Started
T10090 | W10010 | FS | Not Started | Not Started
F20070 | T30010 | FS | Not Started | Not Started
F20051 | T30010 | FS | Not Started | Not Started
F20060 | T30010 | FS | Not Started | Not Started
S11060 | A45010 | FS | Not Started | Not Started
A66510 | M00009 | FS | Not Started | Not Started
A59510 | M00009 | FS | Not Started | Not Started
A54530 | A60510 | FS | Not Started | Not Started
A41810 | A67010 | FS | Not Started | Not Started
A41810 | A66510 | FS | Not Started | Not Started
A45520 | A48530 | FS | Not Started | Not Started
S11060 | A60020 | FS | Not Started | Not Started
A48520 | A60020 | FS | Not Started | Not Started
S11060 | A51510 | FS | Not Started | Not Started
A48520 | A51510 | FS | Not Started | Not Started
A47530 | A47540 | FS | Not Started | Not Started
A47540 | M00009 | FS | Not Started | Not Started
A64010 | M00009 | FS | Not Started | Not Started
A62510 | A63020 | FS | Not Started | Not Started
A63020 | A66510 | FS | Not Started | Not Started
S11060 | T35010 | FS | Not Started | Not Started
M00007 | T37010 | FS | Not Started | Not Started
S11060 | M00007 | FS | Not Started | Not Started

## p6_act
task_code | status_code | wbs_id | task_name
Activity ID | Activity Status | WBS Code | Activity Name
T10010 | Not Started | wr | fence-line_marking
T10020 | Not Started | wr | fence-excavation
T10030 | Not Started | wr | fence-compaction
T10040 | Not Started | wr | fence-foundation
T10050 | Not Started | wr | fence-backfilling
T10060 | Not Started | wr | fence-steel
T10070 | Not Started | wr | fence-panel
T10080 | Not Started | wr | fence-wrapping
T10090 | Not Started | wr | fence-inspection
T30010 | Not Started | wr | t-crane_installation-form
T30020 | Not Started | wr | t-crane_installation-rebar
T30030 | Not Started | wr | t-crane_installation-casting
T30031 | Not Started | wr | t-crane_installation-curing1
T30032 | Not Started | wr | t-crane_installation-curing2
T30033 | Not Started | wr | t-crane_installation-curing3
T30034 | Not Started | wr | t-crane_installation-curing4
T30035 | Not Started | wr | t-crane_installation-curing5
T30036 | Not Started | wr | t-crane_installation-curing6
T30040 | Not Started | wr | t-crane_installation-installation
T30050 | Not Started | wr | t-crane_installation-inspection
T32010 | Not Started | wr | t-crane_dismantling-machine
T32020 | Not Started | wr | t-crane_dismantling-dismantling
T35010 | Not Started | wr | lift_installation-form
T35020 | Not Started | wr | lift_installation-rebar
T35030 | Not Started | wr | lift_installation-casting
T35031 | Not Started | wr | lift_installation-curing1
T35032 | Not Started | wr | lift_installation-curing2
T35033 | Not Started | wr | lift_installation-curing3
T35034 | Not Started | wr | lift_installation-curing4
T35035 | Not Started | wr | lift_installation-curing5
T35036 | Not Started | wr | lift_installation-curing6
T35040 | Not Started | wr | lift_installation-installation
T35050 | Not Started | wr | lift_installation-inspection
T37010 | Not Started | wr | lift_dismantling-dismantling
W10010 | Not Started | wr | CIP-line_marking
W10020 | Not Started | wr | CIP-guidebeam
W10030 | Not Started | wr | CIP-soil_compaction_for_machine
W10040 | Not Started | wr | CIP-dig&rebar_1
W10050 | Not Started | wr | CIP-casting_1
W10060 | Not Started | wr | CIP-capbeam
W10070 | Not Started | wr | CIP-capbeam_casting
W11010 | Not Started | wr | waterblock-line_marking
W11020 | Not Started | wr | waterblock-dig&piping
W11030 | Not Started | wr | waterblock-injection
W11040 | Not Started | wr | waterblock-cleaning
D10010 | Not Started | wr | excavation_test-planning
D10020 | Not Started | wr | excavation_test-excavation
D10030 | Not Started | wr | excavation_test-inspection
D11010 | Not Started | wr | excavation-0
R10010 | Not Started | wr | post_pile-line_marking
R10020 | Not Started | wr | post_pile-dig&piling
R11010 | Not Started | wr | strut_installation-wale
R11020 | Not Started | wr | strut_installation-strut
R11030 | Not Started | wr | strut_installation-inspection
R12010 | Not Started | wr | strut_dismatling-check
R12020 | Not Started | wr | strut_dismatling-remove
F20010 | Not Started | wr | foundation-vapor_proof&lean_conc.
F20020 | Not Started | wr | foundation-line_marking
F20030 | Not Started | wr | foundation-re-bar
F20040 | Not Started | wr | foundation-form
F20050 | Not Started | wr | foundation-casting
F20051 | Not Started | wr | foundation-curing
F20060 | Not Started | wr | foundation-form_dismantling
F20070 | Not Started | wr | foundation-backfill
S10010 | Not Started | wr | rc_structure_vertical-line_marking
S10020 | Not Started | wr | rc_structure_vertical-re-bar
S10030 | Not Started | wr | rc_structure_vertical-embedding
S10040 | Not Started | wr | rc_structure_vertical-form
S10050 | Not Started | wr | rc_structure_vertical-inspection
S10060 | Not Started | wr | rc_structure_vertical-casting
S10061 | Not Started | wr | rc_structure_vertical-curing
S10070 | Not Started | wr | rc_structure_vertical-dismantling
S11010 | Not Started | wr | rc_structure_horizontal-form
S11020 | Not Started | wr | rc_structure_horizontal-re-bar
S11030 | Not Started | wr | rc_structure_horizontal-embedding
S11040 | Not Started | wr | rc_structure_horizontal-inspection
S11050 | Not Started | wr | rc_structure_horizontal-casting
S11051 | Not Started | wr | rc_structure_horizontal-curing
S11060 | Not Started | wr | rc_structure_horizontal-dismantling
A41510 | Not Started | wr | finishing_benchmark-0
A44510 | Not Started | wr | masonry-material_delivery
A44520 | Not Started | wr | masonry-1st
A44521 | Not Started | wr | masonry-2nd
A45010 | Not Started | wr | plastering-surface
A45011 | Not Started | wr | plastering-1st
A45012 | Not Started | wr | plastering-final
A48510 | Not Started | wr | drywall-line_marking
A48520 | Not Started | wr | drywall-stud
A48530 | Not Started | wr | drywall-gypsum_board
A50510 | Not Started | wr | ceiling_frame-hanger
A50520 | Not Started | wr | ceiling_frame-frame
A51010 | Not Started | wr | ceiling_board-gypsum_board
A52010 | Not Started | wr | grill_installation-0
A53010 | Not Started | wr | steel_door-frame
A53020 | Not Started | wr | steel_door-door
A55010 | Not Started | wr | finishing stone-0
A57510 | Not Started | wr | inside_wall_painting-surface
A57520 | Not Started | wr | inside_wall_painting-1st
A57530 | Not Started | wr | inside_wall_painting-final
A58010 | Not Started | wr | glazing-0
A59010 | Not Started | wr | ceiling_painting-surface
A59020 | Not Started | wr | ceiling_painting-1st
A59030 | Not Started | wr | ceiling_painting-final
A59510 | Not Started | wr | ceiling_tex-0
A60510 | Not Started | wr | inside_floor_painting-surface
A60520 | Not Started | wr | inside_floor_painting-1st
A60530 | Not Started | wr | inside_floor_painting-final
A61010 | Not Started | wr | stair_floor_tile-surface
A61020 | Not Started | wr | stair_floor_tile-tile
A62510 | Not Started | wr | base_board-0
A64010 | Not Started | wr | miscellaneous-0
A60020 | Not Started | wr | loover-0
A67010 | Not Started | wr | furniture-0
A41810 | Not Started | wr | inside_floor_PVCtile-0
A43010 | Not Started | wr | finishing_concreting-level_marking
A43020 | Not Started | wr | finishing_concreting-casting
A43021 | Not Started | wr | finishing_concreting-floor_plastering
A43022 | Not Started | wr | finishing_concreting-curing
A45510 | Not Started | wr | wall_insulation-surface
A45520 | Not Started | wr | wall_insulation-insulation
A61510 | Not Started | wr | inside_floor_accessfloor-floor_coating
A61520 | Not Started | wr | inside_floor_accessfloor-line_marking
A61530 | Not Started | wr | inside_floor_accessfloor-frame
A61540 | Not Started | wr | inside_floor_accessfloor-tile
A66510 | Not Started | wr | electric_appliances-0
A46010 | Not Started | wr | ceiling_insulation-surface
A46020 | Not Started | wr | ceiling_insulation-insulation
A53510 | Not Started | wr | wood_door-frame
A53520 | Not Started | wr | wood_door-door
A54510 | Not Started | wr | floor_heating_finishing-surface
A54520 | Not Started | wr | floor_heating_finishing-mortar_1st
A54530 | Not Started | wr | floor_heating_finishing-mortar_final
A62010 | Not Started | wr | inside_floor_woodtile-surface
A62020 | Not Started | wr | inside_floor_woodtile-line_marking
A62030 | Not Started | wr | inside_floor_woodtile-frame
A62040 | Not Started | wr | inside_floor_woodtile-woodtile
A62050 | Not Started | wr | inside_floor_woodtile-finishing
A63010 | Not Started | wr | inside_wall_paper-ceiling
A63020 | Not Started | wr | inside_wall_paper-wall
A49510 | Not Started | wr | inside_waterproofing-surface
A49520 | Not Started | wr | inside_waterproofing-waterproofing
A49530 | Not Started | wr | inside_waterproofing-test
A49540 | Not Started | wr | inside_waterproofing-protection
A56510 | Not Started | wr | inside_floor_tile-surface
A56520 | Not Started | wr | inside_floor_tile-tile
A57010 | Not Started | wr | inside_wall_tile-0
A60010 | Not Started | wr | ceiling_tile-0
A60710 | Not Started | wr | washbasin_installation-frame
A60720 | Not Started | wr | washbasin_installation-basin
A66010 | Not Started | wr | toilet_accessaries_nstallation-0
A52510 | Not Started | wr | al_window-frame
A52520 | Not Started | wr | al_window-insulation_filling
A52530 | Not Started | wr | al_window-window
A54010 | Not Started | wr | window_door-surface
A54020 | Not Started | wr | window_door-hardware
A54030 | Not Started | wr | window_door-door
A47510 | Not Started | wr | outside_wall_finishing-line_marking
A47520 | Not Started | wr | outside_wall_finishing-frame
A47530 | Not Started | wr | outside_wall_finishing-panel
A51510 | Not Started | wr | pvc_window-frame
A51520 | Not Started | wr | pvc_window-insulation_filling
A51530 | Not Started | wr | pvc_window-window
M00009 | Not Started | wr | project_completion
M00001 | Not Started | wr | project_start
A47540 | Not Started | wr | outside_wall_finishing-sealant
M00007 | Not Started | wr | elevator