## Sheet1
x | y | z | major_activity | code | minor_activity
1 | 2 | 0 | R100 | R10010 | post_pile-line_marking
1 | 2 | 0 | R100 | R10020 | post_pile-dig&piling
2 | 2 | 0 | R100 | R10010 | post_pile-line_marking
2 | 2 | 0 | R100 | R10020 | post_pile-dig&piling
3 | 2 | 0 | R100 | R10010 | post_pile-line_marking
3 | 2 | 0 | R100 | R10020 | post_pile-dig&piling
1 | 1 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
1 | 1 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
1 | 1 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
1 | 1 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
1 | 1 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
1 | 1 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
1 | 1 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
1 | 1 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
1 | 2 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
1 | 2 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
1 | 2 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
1 | 2 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
1 | 2 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
1 | 2 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
1 | 2 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
1 | 2 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
1 | 3 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
1 | 3 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
1 | 3 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
1 | 3 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
1 | 3 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
1 | 3 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
1 | 3 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
1 | 3 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
2 | 1 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
2 | 1 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
2 | 1 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
2 | 1 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
2 | 1 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
2 | 1 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
2 | 1 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
2 | 1 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
3 | 1 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
3 | 1 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
3 | 1 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
3 | 1 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
3 | 1 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
3 | 1 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
3 | 1 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
3 | 1 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
3 | 2 | 0 | W100 | W10010 | Soil_retaining_wall(CIP)-line_marking
3 | 2 | 0 | W100 | W10020 | Soil_retaining_wall(CIP)-guidebeam
3 | 2 | 0 | W100 | W10030 | Soil_retaining_wall(CIP)-soil_compaction_for_machine
3 | 2 | 0 | W100 | W10040 | Soil_retaining_wall(CIP)-1st_CIP
3 | 2 | 0 | W100 | W10050 | Soil_retaining_wall(CIP)-2nd_CIP
3 | 2 | 0 | W100 | W10060 | Soil_retaining_wall(CIP)-3rd_CIP
3 | 2 | 0 | W100 | W10070 | Soil_retaining_wall(CIP)-capbeam
3 | 2 | 0 | W100 | W10080 | Soil_retaining_wall(CIP)-capbeam_casting
1 | 1 | 0 | W110 | W11010 | waterblock-line_marking
1 | 1 | 0 | W110 | W11020 | waterblock-dig&piping
1 | 1 | 0 | W110 | W11030 | waterblock-injection
1 | 1 | 0 | W110 | W11040 | waterblock-cleaning
1 | 2 | 0 | W110 | W11010 | waterblock-line_marking
1 | 2 | 0 | W110 | W11020 | waterblock-dig&piping
1 | 2 | 0 | W110 | W11030 | waterblock-injection
1 | 2 | 0 | W110 | W11040 | waterblock-cleaning
1 | 3 | 0 | W110 | W11010 | waterblock-line_marking
1 | 3 | 0 | W110 | W11020 | waterblock-dig&piping
1 | 3 | 0 | W110 | W11030 | waterblock-injection
1 | 3 | 0 | W110 | W11040 | waterblock-cleaning
2 | 1 | 0 | W110 | W11010 | waterblock-line_marking
2 | 1 | 0 | W110 | W11020 | waterblock-dig&piping
2 | 1 | 0 | W110 | W11030 | waterblock-injection
2 | 1 | 0 | W110 | W11040 | waterblock-cleaning
3 | 1 | 0 | W110 | W11010 | waterblock-line_marking
3 | 1 | 0 | W110 | W11020 | waterblock-dig&piping
3 | 1 | 0 | W110 | W11030 | waterblock-injection
3 | 1 | 0 | W110 | W11040 | waterblock-cleaning
3 | 2 | 0 | W110 | W11010 | waterblock-line_marking
3 | 2 | 0 | W110 | W11020 | waterblock-dig&piping
3 | 2 | 0 | W110 | W11030 | waterblock-injection
3 | 2 | 0 | W110 | W11040 | waterblock-cleaning
5 | 5 | 0 | M000 | M00001 | Milestone-project_Start
5 | 5 | 0 | M000 | M00009 | Milestone-project_completion

## Sheet2
project_completion | major_activity
project_start | M000
fence-line_marking | T100
fence-excavation | W100
fence-compaction | W110
fence-foundation | R100
fence-backfilling | R110
fence-steel | R120
fence-panel | T350
fence-wrapping | T370
fence-inspection
CIP-line_marking
CIP-guidebeam
CIP-soil_compaction_for_machine
CIP-dig&rebar_1
CIP-casting_1
CIP-dig&rebar_2
CIP-casting_2
CIP-dig&rebar_3
CIP-casting_3
CIP-capbeam
CIP-capbeam_casting
waterblock-line_marking
waterblock-dig&piping
waterblock-injection
waterblock-cleaning
post_pile-dig&piling
strut_installation-wale
strut_installation-strut
strut_installation-inspection
strut_dismatling-check
strut_dismatling-remove
lift_installation-form
lift_installation-rebar
lift_installation-casting
lift_installation-curing1
lift_installation-curing2
lift_installation-curing3
lift_installation-curing4
lift_installation-curing5
lift_installation-curing6
lift_installation-installation
lift_installation-inspection
lift_dismantling-dismantling
post_pile-line_marking