## grid_activity_list
x | y | z | major_activity | code | minor_activity
0 | 0 | 0 | M000 | M00009 | project_completion
0 | 0 | 0 | M000 | M00001 | project_start
0 | 0 | 0 | M000 | M00007 | elevator
1 | 1 | 1 | T100 | T10010 | fence-line_marking
1 | 1 | 1 | T100 | T10020 | fence-excavation
1 | 1 | 1 | T100 | T10030 | fence-compaction
1 | 1 | 1 | T100 | T10040 | fence-foundation
1 | 1 | 1 | T100 | T10050 | fence-backfilling
1 | 1 | 1 | T100 | T10060 | fence-steel
1 | 1 | 1 | T100 | T10070 | fence-panel
1 | 1 | 1 | T100 | T10080 | fence-wrapping
1 | 1 | 1 | T100 | T10090 | fence-inspection
1 | 2 | 1 | T100 | T10010 | fence-line_marking
1 | 2 | 1 | T100 | T10020 | fence-excavation
1 | 2 | 1 | T100 | T10030 | fence-compaction
1 | 2 | 1 | T100 | T10040 | fence-foundation
1 | 2 | 1 | T100 | T10050 | fence-backfilling
1 | 2 | 1 | T100 | T10060 | fence-steel
1 | 2 | 1 | T100 | T10070 | fence-panel
1 | 2 | 1 | T100 | T10080 | fence-wrapping
1 | 2 | 1 | T100 | T10090 | fence-inspection
1 | 3 | 1 | T100 | T10010 | fence-line_marking
1 | 3 | 1 | T100 | T10020 | fence-excavation
1 | 3 | 1 | T100 | T10030 | fence-compaction
1 | 3 | 1 | T100 | T10040 | fence-foundation
1 | 3 | 1 | T100 | T10050 | fence-backfilling
1 | 3 | 1 | T100 | T10060 | fence-steel
1 | 3 | 1 | T100 | T10070 | fence-panel
1 | 3 | 1 | T100 | T10080 | fence-wrapping
1 | 3 | 1 | T100 | T10090 | fence-inspection
3 | 1 | 1 | T100 | T10010 | fence-line_marking
3 | 1 | 1 | T100 | T10020 | fence-excavation
3 | 1 | 1 | T100 | T10030 | fence-compaction
3 | 1 | 1 | T100 | T10040 | fence-foundation
3 | 1 | 1 | T100 | T10050 | fence-backfilling
3 | 1 | 1 | T100 | T10060 | fence-steel
3 | 1 | 1 | T100 | T10070 | fence-panel
3 | 1 | 1 | T100 | T10080 | fence-wrapping
3 | 1 | 1 | T100 | T10090 | fence-inspection
3 | 2 | 1 | T100 | T10010 | fence-line_marking
3 | 2 | 1 | T100 | T10020 | fence-excavation
3 | 2 | 1 | T100 | T10030 | fence-compaction
3 | 2 | 1 | T100 | T10040 | fence-foundation
3 | 2 | 1 | T100 | T10050 | fence-backfilling
3 | 2 | 1 | T100 | T10060 | fence-steel
3 | 2 | 1 | T100 | T10070 | fence-panel
3 | 2 | 1 | T100 | T10080 | fence-wrapping
3 | 2 | 1 | T100 | T10090 | fence-inspection
3 | 3 | 1 | T100 | T10010 | fence-line_marking
3 | 3 | 1 | T100 | T10020 | fence-excavation
3 | 3 | 1 | T100 | T10030 | fence-compaction
3 | 3 | 1 | T100 | T10040 | fence-foundation
3 | 3 | 1 | T100 | T10050 | fence-backfilling
3 | 3 | 1 | T100 | T10060 | fence-steel
3 | 3 | 1 | T100 | T10070 | fence-panel
3 | 3 | 1 | T100 | T10080 | fence-wrapping
3 | 3 | 1 | T100 | T10090 | fence-inspection
2 | 1 | 1 | T100 | T10010 | fence-line_marking
2 | 1 | 1 | T100 | T10020 | fence-excavation
2 | 1 | 1 | T100 | T10030 | fence-compaction
2 | 1 | 1 | T100 | T10040 | fence-foundation
2 | 1 | 1 | T100 | T10050 | fence-backfilling
2 | 1 | 1 | T100 | T10060 | fence-steel
2 | 1 | 1 | T100 | T10070 | fence-panel
2 | 1 | 1 | T100 | T10080 | fence-wrapping
2 | 1 | 1 | T100 | T10090 | fence-inspection
2 | 3 | 1 | T100 | T10010 | fence-line_marking
2 | 3 | 1 | T100 | T10020 | fence-excavation
2 | 3 | 1 | T100 | T10030 | fence-compaction
2 | 3 | 1 | T100 | T10040 | fence-foundation
2 | 3 | 1 | T100 | T10050 | fence-backfilling
2 | 3 | 1 | T100 | T10060 | fence-steel
2 | 3 | 1 | T100 | T10070 | fence-panel
2 | 3 | 1 | T100 | T10080 | fence-wrapping
2 | 3 | 1 | T100 | T10090 | fence-inspection
1 | 2 | 1 | T300 | T30010 | t-crane_installation-form
1 | 2 | 1 | T300 | T30020 | t-crane_installation-rebar
1 | 2 | 1 | T300 | T30030 | t-crane_installation-casting
1 | 2 | 1 | T300 | T30031 | t-crane_installation-curing1
1 | 2 | 1 | T300 | T30032 | t-crane_installation-curing2
1 | 2 | 1 | T300 | T30033 | t-crane_installation-curing3
1 | 2 | 1 | T300 | T30034 | t-crane_installation-curing4
1 | 2 | 1 | T300 | T30035 | t-crane_installation-curing5
1 | 2 | 1 | T300 | T30036 | t-crane_installation-curing6
1 | 2 | 1 | T300 | T30040 | t-crane_installation-installation
1 | 2 | 1 | T300 | T30050 | t-crane_installation-inspection
1 | 2 | 1 | T320 | T32010 | t-crane_dismantling-machine
1 | 2 | 1 | T320 | T32020 | t-crane_dismantling-dismantling
1 | 3 | 1 | T350 | T35010 | lift_installation-form
1 | 3 | 1 | T350 | T35020 | lift_installation-rebar
1 | 3 | 1 | T350 | T35030 | lift_installation-casting
1 | 3 | 1 | T350 | T35031 | lift_installation-curing1
1 | 3 | 1 | T350 | T35032 | lift_installation-curing2
1 | 3 | 1 | T350 | T35033 | lift_installation-curing3
1 | 3 | 1 | T350 | T35034 | lift_installation-curing4
1 | 3 | 1 | T350 | T35035 | lift_installation-curing5
1 | 3 | 1 | T350 | T35036 | lift_installation-curing6
1 | 3 | 1 | T350 | T35040 | lift_installation-installation
1 | 3 | 1 | T350 | T35050 | lift_installation-inspection
1 | 3 | 1 | T370 | T37010 | lift_dismantling-dismantling
1 | 1 | 1 | W100 | W10010 | CIP-line_marking
1 | 1 | 1 | W100 | W10020 | CIP-guidebeam
1 | 1 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
1 | 1 | 1 | W100 | W10040 | CIP-dig&rebar_1
1 | 1 | 1 | W100 | W10041 | CIP-casting_1
1 | 1 | 1 | W100 | W10050 | CIP-dig&rebar_2
1 | 1 | 1 | W100 | W10051 | CIP-casting_2
1 | 1 | 1 | W100 | W10060 | CIP-dig&rebar_3
1 | 1 | 1 | W100 | W10061 | CIP-casting_3
1 | 1 | 1 | W100 | W10070 | CIP-capbeam
1 | 1 | 1 | W100 | W10080 | CIP-capbeam_casting
1 | 1 | 1 | W110 | W11010 | waterblock-line_marking
1 | 1 | 1 | W110 | W11020 | waterblock-dig&piping
1 | 1 | 1 | W110 | W11030 | waterblock-injection
1 | 1 | 1 | W110 | W11040 | waterblock-cleaning
2 | 1 | 1 | W100 | W10010 | CIP-line_marking
2 | 1 | 1 | W100 | W10020 | CIP-guidebeam
2 | 1 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
2 | 1 | 1 | W100 | W10040 | CIP-dig&rebar_1
2 | 1 | 1 | W100 | W10041 | CIP-casting_1
2 | 1 | 1 | W100 | W10050 | CIP-dig&rebar_2
2 | 1 | 1 | W100 | W10051 | CIP-casting_2
2 | 1 | 1 | W100 | W10060 | CIP-dig&rebar_3
2 | 1 | 1 | W100 | W10061 | CIP-casting_3
2 | 1 | 1 | W100 | W10070 | CIP-capbeam
2 | 1 | 1 | W100 | W10080 | CIP-capbeam_casting
2 | 1 | 1 | W110 | W11010 | waterblock-line_marking
2 | 1 | 1 | W110 | W11020 | waterblock-dig&piping
2 | 1 | 1 | W110 | W11030 | waterblock-injection
2 | 1 | 1 | W110 | W11040 | waterblock-cleaning
3 | 1 | 1 | W100 | W10010 | CIP-line_marking
3 | 1 | 1 | W100 | W10020 | CIP-guidebeam
3 | 1 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
3 | 1 | 1 | W100 | W10040 | CIP-dig&rebar_1
3 | 1 | 1 | W100 | W10041 | CIP-casting_1
3 | 1 | 1 | W100 | W10050 | CIP-dig&rebar_2
3 | 1 | 1 | W100 | W10051 | CIP-casting_2
3 | 1 | 1 | W100 | W10060 | CIP-dig&rebar_3
3 | 1 | 1 | W100 | W10061 | CIP-casting_3
3 | 1 | 1 | W100 | W10070 | CIP-capbeam
3 | 1 | 1 | W100 | W10080 | CIP-capbeam_casting
3 | 1 | 1 | W110 | W11010 | waterblock-line_marking
3 | 1 | 1 | W110 | W11020 | waterblock-dig&piping
3 | 1 | 1 | W110 | W11030 | waterblock-injection
3 | 1 | 1 | W110 | W11040 | waterblock-cleaning
1 | 3 | 1 | W100 | W10010 | CIP-line_marking
1 | 3 | 1 | W100 | W10020 | CIP-guidebeam
1 | 3 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
1 | 3 | 1 | W100 | W10040 | CIP-dig&rebar_1
1 | 3 | 1 | W100 | W10041 | CIP-casting_1
1 | 3 | 1 | W100 | W10050 | CIP-dig&rebar_2
1 | 3 | 1 | W100 | W10051 | CIP-casting_2
1 | 3 | 1 | W100 | W10060 | CIP-dig&rebar_3
1 | 3 | 1 | W100 | W10061 | CIP-casting_3
1 | 3 | 1 | W100 | W10070 | CIP-capbeam
1 | 3 | 1 | W100 | W10080 | CIP-capbeam_casting
1 | 3 | 1 | W110 | W11010 | waterblock-line_marking
1 | 3 | 1 | W110 | W11020 | waterblock-dig&piping
1 | 3 | 1 | W110 | W11030 | waterblock-injection
1 | 3 | 1 | W110 | W11040 | waterblock-cleaning
2 | 3 | 1 | W100 | W10010 | CIP-line_marking
2 | 3 | 1 | W100 | W10020 | CIP-guidebeam
2 | 3 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
2 | 3 | 1 | W100 | W10040 | CIP-dig&rebar_1
2 | 3 | 1 | W100 | W10041 | CIP-casting_1
2 | 3 | 1 | W100 | W10050 | CIP-dig&rebar_2
2 | 3 | 1 | W100 | W10051 | CIP-casting_2
2 | 3 | 1 | W100 | W10060 | CIP-dig&rebar_3
2 | 3 | 1 | W100 | W10061 | CIP-casting_3
2 | 3 | 1 | W100 | W10070 | CIP-capbeam
2 | 3 | 1 | W100 | W10080 | CIP-capbeam_casting
2 | 3 | 1 | W110 | W11010 | waterblock-line_marking
2 | 3 | 1 | W110 | W11020 | waterblock-dig&piping
2 | 3 | 1 | W110 | W11030 | waterblock-injection
2 | 3 | 1 | W110 | W11040 | waterblock-cleaning
3 | 3 | 1 | W100 | W10010 | CIP-line_marking
3 | 3 | 1 | W100 | W10020 | CIP-guidebeam
3 | 3 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
3 | 3 | 1 | W100 | W10040 | CIP-dig&rebar_1
3 | 3 | 1 | W100 | W10041 | CIP-casting_1
3 | 3 | 1 | W100 | W10050 | CIP-dig&rebar_2
3 | 3 | 1 | W100 | W10051 | CIP-casting_2
3 | 3 | 1 | W100 | W10060 | CIP-dig&rebar_3
3 | 3 | 1 | W100 | W10061 | CIP-casting_3
3 | 3 | 1 | W100 | W10070 | CIP-capbeam
3 | 3 | 1 | W100 | W10080 | CIP-capbeam_casting
3 | 3 | 1 | W110 | W11010 | waterblock-line_marking
3 | 3 | 1 | W110 | W11020 | waterblock-dig&piping
3 | 3 | 1 | W110 | W11030 | waterblock-injection
3 | 3 | 1 | W110 | W11040 | waterblock-cleaning
1 | 2 | 1 | W100 | W10010 | CIP-line_marking
1 | 2 | 1 | W100 | W10020 | CIP-guidebeam
1 | 2 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
1 | 2 | 1 | W100 | W10040 | CIP-dig&rebar_1
1 | 2 | 1 | W100 | W10041 | CIP-casting_1
1 | 2 | 1 | W100 | W10050 | CIP-dig&rebar_2
1 | 2 | 1 | W100 | W10051 | CIP-casting_2
1 | 2 | 1 | W100 | W10060 | CIP-dig&rebar_3
1 | 2 | 1 | W100 | W10061 | CIP-casting_3
1 | 2 | 1 | W100 | W10070 | CIP-capbeam
1 | 2 | 1 | W100 | W10080 | CIP-capbeam_casting
1 | 2 | 1 | W110 | W11010 | waterblock-line_marking
1 | 2 | 1 | W110 | W11020 | waterblock-dig&piping
1 | 2 | 1 | W110 | W11030 | waterblock-injection
1 | 2 | 1 | W110 | W11040 | waterblock-cleaning
3 | 2 | 1 | W100 | W10010 | CIP-line_marking
3 | 2 | 1 | W100 | W10020 | CIP-guidebeam
3 | 2 | 1 | W100 | W10030 | CIP-soil_compaction_for_machine
3 | 2 | 1 | W100 | W10040 | CIP-dig&rebar_1
3 | 2 | 1 | W100 | W10041 | CIP-casting_1
3 | 2 | 1 | W100 | W10050 | CIP-dig&rebar_2
3 | 2 | 1 | W100 | W10051 | CIP-casting_2
3 | 2 | 1 | W100 | W10060 | CIP-dig&rebar_3
3 | 2 | 1 | W100 | W10061 | CIP-casting_3
3 | 2 | 1 | W100 | W10070 | CIP-capbeam
3 | 2 | 1 | W100 | W10080 | CIP-capbeam_casting
3 | 2 | 1 | W110 | W11010 | waterblock-line_marking
3 | 2 | 1 | W110 | W11020 | waterblock-dig&piping
3 | 2 | 1 | W110 | W11030 | waterblock-injection
3 | 2 | 1 | W110 | W11040 | waterblock-cleaning
3 | 3 | 3 | D100 | D10010 | excavation_test-planning
3 | 3 | 3 | D100 | D10020 | excavation_test-excavation
3 | 3 | 3 | D100 | D10030 | excavation_test-inspection
1 | 1 | 1 | D110 | D11010 | excavation-0
2 | 1 | 1 | D110 | D11010 | excavation-0
3 | 1 | 1 | D110 | D11010 | excavation-0
1 | 2 | 1 | D110 | D11010 | excavation-0
2 | 2 | 1 | D110 | D11010 | excavation-0
3 | 2 | 1 | D110 | D11010 | excavation-0
1 | 3 | 1 | D110 | D11010 | excavation-0
2 | 3 | 1 | D110 | D11010 | excavation-0
3 | 3 | 1 | D110 | D11010 | excavation-0
1 | 1 | -1 | D110 | D11010 | excavation-0
2 | 1 | -1 | D110 | D11010 | excavation-0
3 | 1 | -1 | D110 | D11010 | excavation-0
1 | 2 | -1 | D110 | D11010 | excavation-0
2 | 2 | -1 | D110 | D11010 | excavation-0
3 | 2 | -1 | D110 | D11010 | excavation-0
1 | 3 | -1 | D110 | D11010 | excavation-0
2 | 3 | -1 | D110 | D11010 | excavation-0
3 | 3 | -1 | D110 | D11010 | excavation-0
1 | 1 | -2 | D110 | D11010 | excavation-0
2 | 1 | -2 | D110 | D11010 | excavation-0
3 | 1 | -2 | D110 | D11010 | excavation-0
1 | 2 | -2 | D110 | D11010 | excavation-0
2 | 2 | -2 | D110 | D11010 | excavation-0
3 | 2 | -2 | D110 | D11010 | excavation-0
1 | 3 | -2 | D110 | D11010 | excavation-0
2 | 3 | -2 | D110 | D11010 | excavation-0
3 | 3 | -2 | D110 | D11010 | excavation-0
1 | 1 | 1 | D120 | D12010 | retaining soil-forming
2 | 1 | 1 | D120 | D12010 | retaining soil-forming
3 | 1 | 1 | D120 | D12010 | retaining soil-forming
1 | 3 | 1 | D120 | D12010 | retaining soil-forming
2 | 3 | 1 | D120 | D12010 | retaining soil-forming
3 | 3 | 1 | D120 | D12010 | retaining soil-forming
1 | 1 | -1 | D120 | D12010 | retaining soil-forming
2 | 1 | -1 | D120 | D12010 | retaining soil-forming
3 | 1 | -1 | D120 | D12010 | retaining soil-forming
1 | 3 | -1 | D120 | D12010 | retaining soil-forming
2 | 3 | -1 | D120 | D12010 | retaining soil-forming
3 | 3 | -1 | D120 | D12010 | retaining soil-forming
1 | 1 | -2 | D120 | D12010 | retaining soil-forming
2 | 1 | -2 | D120 | D12010 | retaining soil-forming
3 | 1 | -2 | D120 | D12010 | retaining soil-forming
1 | 3 | -2 | D120 | D12010 | retaining soil-forming
2 | 3 | -2 | D120 | D12010 | retaining soil-forming
3 | 3 | -2 | D120 | D12010 | retaining soil-forming
1 | 1 | 1 | D120 | D12010 | retaining soil-removal
2 | 1 | 1 | D120 | D12010 | retaining soil-removal
3 | 1 | 1 | D120 | D12010 | retaining soil-removal
1 | 3 | 1 | D120 | D12010 | retaining soil-removal
2 | 3 | 1 | D120 | D12010 | retaining soil-removal
3 | 3 | 1 | D120 | D12010 | retaining soil-removal
1 | 1 | -1 | D120 | D12010 | retaining soil-removal
2 | 1 | -1 | D120 | D12010 | retaining soil-removal
3 | 1 | -1 | D120 | D12010 | retaining soil-removal
1 | 3 | -1 | D120 | D12010 | retaining soil-removal
2 | 3 | -1 | D120 | D12010 | retaining soil-removal
3 | 3 | -1 | D120 | D12010 | retaining soil-removal
1 | 1 | -2 | D120 | D12010 | retaining soil-removal
2 | 1 | -2 | D120 | D12010 | retaining soil-removal
3 | 1 | -2 | D120 | D12010 | retaining soil-removal
1 | 3 | -2 | D120 | D12010 | retaining soil-removal
2 | 3 | -2 | D120 | D12010 | retaining soil-removal
3 | 3 | -2 | D120 | D12010 | retaining soil-removal
1 | 1 | 1 | R100 | R10020 | post_pile-dig&piling
1 | 1 | 1 | R110 | R11010 | strut_installation-wale
1 | 1 | 1 | R110 | R11020 | strut_installation-strut
1 | 1 | 1 | R110 | R11030 | strut_installation-inspection
1 | 1 | 1 | R120 | R12010 | strut_dismatling-check
1 | 1 | 1 | R120 | R12020 | strut_dismatling-remove
2 | 1 | 1 | R100 | R10010 | post_pile-line_marking
2 | 1 | 1 | R100 | R10020 | post_pile-dig&piling
2 | 1 | 1 | R110 | R11010 | strut_installation-wale
2 | 1 | 1 | R110 | R11020 | strut_installation-strut
2 | 1 | 1 | R110 | R11030 | strut_installation-inspection
2 | 1 | 1 | R120 | R12010 | strut_dismatling-check
2 | 1 | 1 | R120 | R12020 | strut_dismatling-remove
3 | 1 | 1 | R100 | R10010 | post_pile-line_marking
3 | 1 | 1 | R100 | R10020 | post_pile-dig&piling
3 | 1 | 1 | R110 | R11010 | strut_installation-wale
3 | 1 | 1 | R110 | R11020 | strut_installation-strut
3 | 1 | 1 | R110 | R11030 | strut_installation-inspection
3 | 1 | 1 | R120 | R12010 | strut_dismatling-check
3 | 1 | 1 | R120 | R12020 | strut_dismatling-remove
1 | 3 | 1 | R100 | R10010 | post_pile-line_marking
1 | 3 | 1 | R100 | R10020 | post_pile-dig&piling
1 | 3 | 1 | R110 | R11010 | strut_installation-wale
1 | 3 | 1 | R110 | R11020 | strut_installation-strut
1 | 3 | 1 | R110 | R11030 | strut_installation-inspection
1 | 3 | 1 | R120 | R12010 | strut_dismatling-check
1 | 3 | 1 | R120 | R12020 | strut_dismatling-remove
2 | 3 | 1 | R100 | R10010 | post_pile-line_marking
2 | 3 | 1 | R100 | R10020 | post_pile-dig&piling
2 | 3 | 1 | R110 | R11010 | strut_installation-wale
2 | 3 | 1 | R110 | R11020 | strut_installation-strut
2 | 3 | 1 | R110 | R11030 | strut_installation-inspection
2 | 3 | 1 | R120 | R12010 | strut_dismatling-check
2 | 3 | 1 | R120 | R12020 | strut_dismatling-remove
3 | 3 | 1 | R100 | R10010 | post_pile-line_marking
3 | 3 | 1 | R100 | R10020 | post_pile-dig&piling
3 | 3 | 1 | R110 | R11010 | strut_installation-wale
3 | 3 | 1 | R110 | R11020 | strut_installation-strut
3 | 3 | 1 | R110 | R11030 | strut_installation-inspection
3 | 3 | 1 | R120 | R12010 | strut_dismatling-check
3 | 3 | 1 | R120 | R12020 | strut_dismatling-remove
1 | 1 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
1 | 1 | -2 | F200 | F20020 | foundation-line_marking
1 | 1 | -2 | F200 | F20030 | foundation-re-bar
1 | 1 | -2 | F200 | F20040 | foundation-form
1 | 1 | -2 | F200 | F20050 | foundation-casting
1 | 1 | -2 | F200 | F20051 | foundation-curing
1 | 1 | -2 | F200 | F20060 | foundation-dismantling
1 | 1 | -2 | F200 | F20070 | foundation-backfill
2 | 1 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
2 | 1 | -2 | F200 | F20020 | foundation-line_marking
2 | 1 | -2 | F200 | F20030 | foundation-re-bar
2 | 1 | -2 | F200 | F20040 | foundation-form
2 | 1 | -2 | F200 | F20050 | foundation-casting
2 | 1 | -2 | F200 | F20051 | foundation-curing
2 | 1 | -2 | F200 | F20060 | foundation-dismantling
2 | 1 | -2 | F200 | F20070 | foundation-backfill
3 | 1 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
3 | 1 | -2 | F200 | F20020 | foundation-line_marking
3 | 1 | -2 | F200 | F20030 | foundation-re-bar
3 | 1 | -2 | F200 | F20040 | foundation-form
3 | 1 | -2 | F200 | F20050 | foundation-casting
3 | 1 | -2 | F200 | F20051 | foundation-curing
3 | 1 | -2 | F200 | F20060 | foundation-dismantling
3 | 1 | -2 | F200 | F20070 | foundation-backfill
1 | 2 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
1 | 2 | -2 | F200 | F20020 | foundation-line_marking
1 | 2 | -2 | F200 | F20030 | foundation-re-bar
1 | 2 | -2 | F200 | F20040 | foundation-form
1 | 2 | -2 | F200 | F20050 | foundation-casting
1 | 2 | -2 | F200 | F20051 | foundation-curing
1 | 2 | -2 | F200 | F20060 | foundation-dismantling
1 | 2 | -2 | F200 | F20070 | foundation-backfill
2 | 2 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
2 | 2 | -2 | F200 | F20020 | foundation-line_marking
2 | 2 | -2 | F200 | F20030 | foundation-re-bar
2 | 2 | -2 | F200 | F20040 | foundation-form
2 | 2 | -2 | F200 | F20050 | foundation-casting
2 | 2 | -2 | F200 | F20051 | foundation-curing
2 | 2 | -2 | F200 | F20060 | foundation-dismantling
2 | 2 | -2 | F200 | F20070 | foundation-backfill
3 | 2 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
3 | 2 | -2 | F200 | F20020 | foundation-line_marking
3 | 2 | -2 | F200 | F20030 | foundation-re-bar
3 | 2 | -2 | F200 | F20040 | foundation-form
3 | 2 | -2 | F200 | F20050 | foundation-casting
3 | 2 | -2 | F200 | F20051 | foundation-curing
3 | 2 | -2 | F200 | F20060 | foundation-dismantling
3 | 2 | -2 | F200 | F20070 | foundation-backfill
1 | 3 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
1 | 3 | -2 | F200 | F20020 | foundation-line_marking
1 | 3 | -2 | F200 | F20030 | foundation-re-bar
1 | 3 | -2 | F200 | F20040 | foundation-form
1 | 3 | -2 | F200 | F20050 | foundation-casting
1 | 3 | -2 | F200 | F20051 | foundation-curing
1 | 3 | -2 | F200 | F20060 | foundation-dismantling
1 | 3 | -2 | F200 | F20070 | foundation-backfill
2 | 3 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
2 | 3 | -2 | F200 | F20020 | foundation-line_marking
2 | 3 | -2 | F200 | F20030 | foundation-re-bar
2 | 3 | -2 | F200 | F20040 | foundation-form
2 | 3 | -2 | F200 | F20050 | foundation-casting
2 | 3 | -2 | F200 | F20051 | foundation-curing
2 | 3 | -2 | F200 | F20060 | foundation-dismantling
2 | 3 | -2 | F200 | F20070 | foundation-backfill
3 | 3 | -2 | F200 | F20010 | foundation-vapor_proof&lean_conc.
3 | 3 | -2 | F200 | F20020 | foundation-line_marking
3 | 3 | -2 | F200 | F20030 | foundation-re-bar
3 | 3 | -2 | F200 | F20040 | foundation-form
3 | 3 | -2 | F200 | F20050 | foundation-casting
3 | 3 | -2 | F200 | F20051 | foundation-curing
3 | 3 | -2 | F200 | F20060 | foundation-dismantling
3 | 3 | -2 | F200 | F20070 | foundation-backfill
2 | 1 | -1 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 1 | -1 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 1 | -1 | S100 | S10030 | rc_structure_vertical-embedding
2 | 1 | -1 | S100 | S10040 | rc_structure_vertical-form
2 | 1 | -1 | S100 | S10050 | rc_structure_vertical-inspection
2 | 1 | -1 | S100 | S10060 | rc_structure_vertical-casting
2 | 1 | -1 | S100 | S10061 | rc_structure_vertical-curing
2 | 1 | -1 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 1 | -1 | S110 | S11010 | rc_structure_horizontal-form
2 | 1 | -1 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 1 | -1 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 1 | -1 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 1 | -1 | S110 | S11050 | rc_structure_horizontal-casting
2 | 1 | -1 | S110 | S11051 | rc_structure_horizontal-curing
2 | 1 | -1 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 2 | -1 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 2 | -1 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 2 | -1 | S100 | S10030 | rc_structure_vertical-embedding
2 | 2 | -1 | S100 | S10040 | rc_structure_vertical-form
2 | 2 | -1 | S100 | S10050 | rc_structure_vertical-inspection
2 | 2 | -1 | S100 | S10060 | rc_structure_vertical-casting
2 | 2 | -1 | S100 | S10061 | rc_structure_vertical-curing
2 | 2 | -1 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 2 | -1 | S110 | S11010 | rc_structure_horizontal-form
2 | 2 | -1 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 2 | -1 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 2 | -1 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 2 | -1 | S110 | S11050 | rc_structure_horizontal-casting
2 | 2 | -1 | S110 | S11051 | rc_structure_horizontal-curing
2 | 2 | -1 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 3 | -1 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 3 | -1 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 3 | -1 | S100 | S10030 | rc_structure_vertical-embedding
2 | 3 | -1 | S100 | S10040 | rc_structure_vertical-form
2 | 3 | -1 | S100 | S10050 | rc_structure_vertical-inspection
2 | 3 | -1 | S100 | S10060 | rc_structure_vertical-casting
2 | 3 | -1 | S100 | S10061 | rc_structure_vertical-curing
2 | 3 | -1 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 3 | -1 | S110 | S11010 | rc_structure_horizontal-form
2 | 3 | -1 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 3 | -1 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 3 | -1 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 3 | -1 | S110 | S11050 | rc_structure_horizontal-casting
2 | 3 | -1 | S110 | S11051 | rc_structure_horizontal-curing
2 | 3 | -1 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 1 | -1 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 1 | -1 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 1 | -1 | S100 | S10030 | rc_structure_vertical-embedding
3 | 1 | -1 | S100 | S10040 | rc_structure_vertical-form
3 | 1 | -1 | S100 | S10050 | rc_structure_vertical-inspection
3 | 1 | -1 | S100 | S10060 | rc_structure_vertical-casting
3 | 1 | -1 | S100 | S10061 | rc_structure_vertical-curing
3 | 1 | -1 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 1 | -1 | S110 | S11010 | rc_structure_horizontal-form
3 | 1 | -1 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 1 | -1 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 1 | -1 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 1 | -1 | S110 | S11050 | rc_structure_horizontal-casting
3 | 1 | -1 | S110 | S11051 | rc_structure_horizontal-curing
3 | 1 | -1 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 2 | -1 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 2 | -1 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 2 | -1 | S100 | S10030 | rc_structure_vertical-embedding
3 | 2 | -1 | S100 | S10040 | rc_structure_vertical-form
3 | 2 | -1 | S100 | S10050 | rc_structure_vertical-inspection
3 | 2 | -1 | S100 | S10060 | rc_structure_vertical-casting
3 | 2 | -1 | S100 | S10061 | rc_structure_vertical-curing
3 | 2 | -1 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 2 | -1 | S110 | S11010 | rc_structure_horizontal-form
3 | 2 | -1 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 2 | -1 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 2 | -1 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 2 | -1 | S110 | S11050 | rc_structure_horizontal-casting
3 | 2 | -1 | S110 | S11051 | rc_structure_horizontal-curing
3 | 2 | -1 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 3 | -1 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 3 | -1 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 3 | -1 | S100 | S10030 | rc_structure_vertical-embedding
3 | 3 | -1 | S100 | S10040 | rc_structure_vertical-form
3 | 3 | -1 | S100 | S10050 | rc_structure_vertical-inspection
3 | 3 | -1 | S100 | S10060 | rc_structure_vertical-casting
3 | 3 | -1 | S100 | S10061 | rc_structure_vertical-curing
3 | 3 | -1 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 3 | -1 | S110 | S11010 | rc_structure_horizontal-form
3 | 3 | -1 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 3 | -1 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 3 | -1 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 3 | -1 | S110 | S11050 | rc_structure_horizontal-casting
3 | 3 | -1 | S110 | S11051 | rc_structure_horizontal-curing
3 | 3 | -1 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 1 | 1 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 1 | 1 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 1 | 1 | S100 | S10030 | rc_structure_vertical-embedding
2 | 1 | 1 | S100 | S10040 | rc_structure_vertical-form
2 | 1 | 1 | S100 | S10050 | rc_structure_vertical-inspection
2 | 1 | 1 | S100 | S10060 | rc_structure_vertical-casting
2 | 1 | 1 | S100 | S10061 | rc_structure_vertical-curing
2 | 1 | 1 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 1 | 1 | S110 | S11010 | rc_structure_horizontal-form
2 | 1 | 1 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 1 | 1 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 1 | 1 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 1 | 1 | S110 | S11050 | rc_structure_horizontal-casting
2 | 1 | 1 | S110 | S11051 | rc_structure_horizontal-curing
2 | 1 | 1 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 2 | 1 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 2 | 1 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 2 | 1 | S100 | S10030 | rc_structure_vertical-embedding
2 | 2 | 1 | S100 | S10040 | rc_structure_vertical-form
2 | 2 | 1 | S100 | S10050 | rc_structure_vertical-inspection
2 | 2 | 1 | S100 | S10060 | rc_structure_vertical-casting
2 | 2 | 1 | S100 | S10061 | rc_structure_vertical-curing
2 | 2 | 1 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 2 | 1 | S110 | S11010 | rc_structure_horizontal-form
2 | 2 | 1 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 2 | 1 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 2 | 1 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 2 | 1 | S110 | S11050 | rc_structure_horizontal-casting
2 | 2 | 1 | S110 | S11051 | rc_structure_horizontal-curing
2 | 2 | 1 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 3 | 1 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 3 | 1 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 3 | 1 | S100 | S10030 | rc_structure_vertical-embedding
2 | 3 | 1 | S100 | S10040 | rc_structure_vertical-form
2 | 3 | 1 | S100 | S10050 | rc_structure_vertical-inspection
2 | 3 | 1 | S100 | S10060 | rc_structure_vertical-casting
2 | 3 | 1 | S100 | S10061 | rc_structure_vertical-curing
2 | 3 | 1 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 3 | 1 | S110 | S11010 | rc_structure_horizontal-form
2 | 3 | 1 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 3 | 1 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 3 | 1 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 3 | 1 | S110 | S11050 | rc_structure_horizontal-casting
2 | 3 | 1 | S110 | S11051 | rc_structure_horizontal-curing
2 | 3 | 1 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 1 | 1 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 1 | 1 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 1 | 1 | S100 | S10030 | rc_structure_vertical-embedding
3 | 1 | 1 | S100 | S10040 | rc_structure_vertical-form
3 | 1 | 1 | S100 | S10050 | rc_structure_vertical-inspection
3 | 1 | 1 | S100 | S10060 | rc_structure_vertical-casting
3 | 1 | 1 | S100 | S10061 | rc_structure_vertical-curing
3 | 1 | 1 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 1 | 1 | S110 | S11010 | rc_structure_horizontal-form
3 | 1 | 1 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 1 | 1 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 1 | 1 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 1 | 1 | S110 | S11050 | rc_structure_horizontal-casting
3 | 1 | 1 | S110 | S11051 | rc_structure_horizontal-curing
3 | 1 | 1 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 2 | 1 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 2 | 1 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 2 | 1 | S100 | S10030 | rc_structure_vertical-embedding
3 | 2 | 1 | S100 | S10040 | rc_structure_vertical-form
3 | 2 | 1 | S100 | S10050 | rc_structure_vertical-inspection
3 | 2 | 1 | S100 | S10060 | rc_structure_vertical-casting
3 | 2 | 1 | S100 | S10061 | rc_structure_vertical-curing
3 | 2 | 1 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 2 | 1 | S110 | S11010 | rc_structure_horizontal-form
3 | 2 | 1 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 2 | 1 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 2 | 1 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 2 | 1 | S110 | S11050 | rc_structure_horizontal-casting
3 | 2 | 1 | S110 | S11051 | rc_structure_horizontal-curing
3 | 2 | 1 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 3 | 1 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 3 | 1 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 3 | 1 | S100 | S10030 | rc_structure_vertical-embedding
3 | 3 | 1 | S100 | S10040 | rc_structure_vertical-form
3 | 3 | 1 | S100 | S10050 | rc_structure_vertical-inspection
3 | 3 | 1 | S100 | S10060 | rc_structure_vertical-casting
3 | 3 | 1 | S100 | S10061 | rc_structure_vertical-curing
3 | 3 | 1 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 3 | 1 | S110 | S11010 | rc_structure_horizontal-form
3 | 3 | 1 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 3 | 1 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 3 | 1 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 3 | 1 | S110 | S11050 | rc_structure_horizontal-casting
3 | 3 | 1 | S110 | S11051 | rc_structure_horizontal-curing
3 | 3 | 1 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 1 | 2 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 1 | 2 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 1 | 2 | S100 | S10030 | rc_structure_vertical-embedding
2 | 1 | 2 | S100 | S10040 | rc_structure_vertical-form
2 | 1 | 2 | S100 | S10050 | rc_structure_vertical-inspection
2 | 1 | 2 | S100 | S10060 | rc_structure_vertical-casting
2 | 1 | 2 | S100 | S10061 | rc_structure_vertical-curing
2 | 1 | 2 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 1 | 2 | S110 | S11010 | rc_structure_horizontal-form
2 | 1 | 2 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 1 | 2 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 1 | 2 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 1 | 2 | S110 | S11050 | rc_structure_horizontal-casting
2 | 1 | 2 | S110 | S11051 | rc_structure_horizontal-curing
2 | 1 | 2 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 2 | 2 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 2 | 2 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 2 | 2 | S100 | S10030 | rc_structure_vertical-embedding
2 | 2 | 2 | S100 | S10040 | rc_structure_vertical-form
2 | 2 | 2 | S100 | S10050 | rc_structure_vertical-inspection
2 | 2 | 2 | S100 | S10060 | rc_structure_vertical-casting
2 | 2 | 2 | S100 | S10061 | rc_structure_vertical-curing
2 | 2 | 2 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 2 | 2 | S110 | S11010 | rc_structure_horizontal-form
2 | 2 | 2 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 2 | 2 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 2 | 2 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 2 | 2 | S110 | S11050 | rc_structure_horizontal-casting
2 | 2 | 2 | S110 | S11051 | rc_structure_horizontal-curing
2 | 2 | 2 | S110 | S11060 | rc_structure_horizontal-dismantling
2 | 3 | 2 | S100 | S10010 | rc_structure_vertical-line_marking
2 | 3 | 2 | S100 | S10020 | rc_structure_vertical-re-bar
2 | 3 | 2 | S100 | S10030 | rc_structure_vertical-embedding
2 | 3 | 2 | S100 | S10040 | rc_structure_vertical-form
2 | 3 | 2 | S100 | S10050 | rc_structure_vertical-inspection
2 | 3 | 2 | S100 | S10060 | rc_structure_vertical-casting
2 | 3 | 2 | S100 | S10061 | rc_structure_vertical-curing
2 | 3 | 2 | S100 | S10070 | rc_structure_vertical-dismantling
2 | 3 | 2 | S110 | S11010 | rc_structure_horizontal-form
2 | 3 | 2 | S110 | S11020 | rc_structure_horizontal-re-bar
2 | 3 | 2 | S110 | S11030 | rc_structure_horizontal-embedding
2 | 3 | 2 | S110 | S11040 | rc_structure_horizontal-inspection
2 | 3 | 2 | S110 | S11050 | rc_structure_horizontal-casting
2 | 3 | 2 | S110 | S11051 | rc_structure_horizontal-curing
2 | 3 | 2 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 1 | 2 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 1 | 2 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 1 | 2 | S100 | S10030 | rc_structure_vertical-embedding
3 | 1 | 2 | S100 | S10040 | rc_structure_vertical-form
3 | 1 | 2 | S100 | S10050 | rc_structure_vertical-inspection
3 | 1 | 2 | S100 | S10060 | rc_structure_vertical-casting
3 | 1 | 2 | S100 | S10061 | rc_structure_vertical-curing
3 | 1 | 2 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 1 | 2 | S110 | S11010 | rc_structure_horizontal-form
3 | 1 | 2 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 1 | 2 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 1 | 2 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 1 | 2 | S110 | S11050 | rc_structure_horizontal-casting
3 | 1 | 2 | S110 | S11051 | rc_structure_horizontal-curing
3 | 1 | 2 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 2 | 2 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 2 | 2 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 2 | 2 | S100 | S10030 | rc_structure_vertical-embedding
3 | 2 | 2 | S100 | S10040 | rc_structure_vertical-form
3 | 2 | 2 | S100 | S10050 | rc_structure_vertical-inspection
3 | 2 | 2 | S100 | S10060 | rc_structure_vertical-casting
3 | 2 | 2 | S100 | S10061 | rc_structure_vertical-curing
3 | 2 | 2 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 2 | 2 | S110 | S11010 | rc_structure_horizontal-form
3 | 2 | 2 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 2 | 2 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 2 | 2 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 2 | 2 | S110 | S11050 | rc_structure_horizontal-casting
3 | 2 | 2 | S110 | S11051 | rc_structure_horizontal-curing
3 | 2 | 2 | S110 | S11060 | rc_structure_horizontal-dismantling
3 | 3 | 2 | S100 | S10010 | rc_structure_vertical-line_marking
3 | 3 | 2 | S100 | S10020 | rc_structure_vertical-re-bar
3 | 3 | 2 | S100 | S10030 | rc_structure_vertical-embedding
3 | 3 | 2 | S100 | S10040 | rc_structure_vertical-form
3 | 3 | 2 | S100 | S10050 | rc_structure_vertical-inspection
3 | 3 | 2 | S100 | S10060 | rc_structure_vertical-casting
3 | 3 | 2 | S100 | S10061 | rc_structure_vertical-curing
3 | 3 | 2 | S100 | S10070 | rc_structure_vertical-dismantling
3 | 3 | 2 | S110 | S11010 | rc_structure_horizontal-form
3 | 3 | 2 | S110 | S11020 | rc_structure_horizontal-re-bar
3 | 3 | 2 | S110 | S11030 | rc_structure_horizontal-embedding
3 | 3 | 2 | S110 | S11040 | rc_structure_horizontal-inspection
3 | 3 | 2 | S110 | S11050 | rc_structure_horizontal-casting
3 | 3 | 2 | S110 | S11051 | rc_structure_horizontal-curing
3 | 3 | 2 | S110 | S11060 | rc_structure_horizontal-dismantling
1,3
1,2
1,1
2,3
2,2
2,1
3,3
3,2
3,1
1,3,2
1,3,1
1,3,-1
1,2,2
1,2,1
1,2,-1
1,1,3
1,1,1
1,1,-1
1,3,-2
1,2,-2
1,1,-2

## grid_wp_list
x | y | z | wp_code | wp_name_en
0 | 0 | 0 | M000 | milestone
1 | 1 | 1 | T100 | fence
1 | 2 | 1 | T100 | fence
1 | 3 | 1 | T100 | fence
3 | 1 | 1 | T100 | fence
3 | 2 | 1 | T100 | fence
3 | 3 | 1 | T100 | fence
2 | 1 | 1 | T100 | fence
2 | 3 | 1 | T100 | fence
1 | 2 | 1 | T300 | t-crane_installation
1 | 2 | 1 | T320 | t-crane_dismantling
1 | 3 | 1 | T350 | lift_installation
1 | 3 | 1 | T370 | lift_dismantling
1 | 1 | 1 | W100 | CIP
1 | 1 | 1 | W110 | waterblock
2 | 1 | 1 | W100 | CIP
2 | 1 | 1 | W110 | waterblock
3 | 1 | 1 | W100 | CIP
3 | 1 | 1 | W110 | waterblock
1 | 3 | 1 | W100 | CIP
1 | 3 | 1 | W110 | waterblock
2 | 3 | 1 | W100 | CIP
2 | 3 | 1 | W110 | waterblock
3 | 3 | 1 | W100 | CIP
3 | 3 | 1 | W110 | waterblock
1 | 2 | 1 | W100 | CIP
1 | 2 | 1 | W110 | waterblock
3 | 2 | 1 | W100 | CIP
3 | 2 | 1 | W110 | waterblock
3 | 3 | 1 | D100 | excavation_test
1 | 1 | 1 | D110 | excavation
2 | 1 | 1 | D110 | excavation
3 | 1 | 1 | D110 | excavation
1 | 2 | 1 | D110 | excavation
2 | 2 | 1 | D110 | excavation
3 | 2 | 1 | D110 | excavation
1 | 3 | 1 | D110 | excavation
2 | 3 | 1 | D110 | excavation
3 | 3 | 1 | D110 | excavation
1 | 1 | -1 | D110 | excavation
2 | 1 | -1 | D110 | excavation
3 | 1 | -1 | D110 | excavation
1 | 2 | -1 | D110 | excavation
2 | 2 | -1 | D110 | excavation
3 | 2 | -1 | D110 | excavation
1 | 3 | -1 | D110 | excavation
2 | 3 | -1 | D110 | excavation
3 | 3 | -1 | D110 | excavation
1 | 1 | -2 | D110 | excavation
2 | 1 | -2 | D110 | excavation
3 | 1 | -2 | D110 | excavation
1 | 2 | -2 | D110 | excavation
2 | 2 | -2 | D110 | excavation
3 | 2 | -2 | D110 | excavation
1 | 3 | -2 | D110 | excavation
2 | 3 | -2 | D110 | excavation
3 | 3 | -2 | D110 | excavation
1 | 1 | 1 | R100 | post_pile
1 | 1 | 1 | R110 | strut_installation
1 | 1 | 1 | R120 | strut_dismantling
2 | 1 | 1 | R100 | post_pile
2 | 1 | 1 | R110 | strut_installation
2 | 1 | 1 | R120 | strut_dismantling
3 | 1 | 1 | R100 | post_pile
3 | 1 | 1 | R110 | strut_installation
3 | 1 | 1 | R120 | strut_dismantling
1 | 3 | 1 | R100 | post_pile
1 | 3 | 1 | R110 | strut_installation
1 | 3 | 1 | R120 | strut_dismantling
2 | 3 | 1 | R100 | post_pile
2 | 3 | 1 | R110 | strut_installation
2 | 3 | 1 | R120 | strut_dismantling
3 | 3 | 1 | R100 | post_pile
3 | 3 | 1 | R110 | strut_installation
3 | 3 | 1 | R120 | strut_dismantling
1 | 1 | -2 | F200 | foundation
2 | 1 | -2 | F200 | foundation
3 | 1 | -2 | F200 | foundation
1 | 2 | -2 | F200 | foundation
2 | 2 | -2 | F200 | foundation
3 | 2 | -2 | F200 | foundation
1 | 3 | -2 | F200 | foundation
2 | 3 | -2 | F200 | foundation
3 | 3 | -2 | F200 | foundation
2 | 1 | -1 | S100 | rc_structure_vertical
2 | 1 | -1 | S110 | rc_structure_horizontal
2 | 2 | -1 | S100 | rc_structure_vertical
2 | 2 | -1 | S110 | rc_structure_horizontal
2 | 3 | -1 | S100 | rc_structure_vertical
2 | 3 | -1 | S110 | rc_structure_horizontal
3 | 1 | -1 | S100 | rc_structure_vertical
3 | 1 | -1 | S110 | rc_structure_horizontal
3 | 2 | -1 | S100 | rc_structure_vertical
3 | 2 | -1 | S110 | rc_structure_horizontal
3 | 3 | -1 | S100 | rc_structure_vertical
3 | 3 | -1 | S110 | rc_structure_horizontal
2 | 1 | 1 | S100 | rc_structure_vertical
2 | 1 | 1 | S110 | rc_structure_horizontal
2 | 2 | 1 | S100 | rc_structure_vertical
2 | 2 | 1 | S110 | rc_structure_horizontal
2 | 3 | 1 | S100 | rc_structure_vertical
2 | 3 | 1 | S110 | rc_structure_horizontal
3 | 1 | 1 | S100 | rc_structure_vertical
3 | 1 | 1 | S110 | rc_structure_horizontal
3 | 2 | 1 | S100 | rc_structure_vertical
3 | 2 | 1 | S110 | rc_structure_horizontal
3 | 3 | 1 | S100 | rc_structure_vertical
3 | 3 | 1 | S110 | rc_structure_horizontal
2 | 1 | 2 | S100 | rc_structure_vertical
2 | 1 | 2 | S110 | rc_structure_horizontal
2 | 2 | 2 | S100 | rc_structure_vertical
2 | 2 | 2 | S110 | rc_structure_horizontal
2 | 3 | 2 | S100 | rc_structure_vertical
2 | 3 | 2 | S110 | rc_structure_horizontal
3 | 1 | 2 | S100 | rc_structure_vertical
3 | 1 | 2 | S110 | rc_structure_horizontal
3 | 2 | 2 | S100 | rc_structure_vertical
3 | 2 | 2 | S110 | rc_structure_horizontal
3 | 3 | 2 | S100 | rc_structure_vertical
3 | 3 | 2 | S110 | rc_structure_horizontal
1,3
1,2
1,1
2,3
2,2
2,1
3,3
3,2
3,1
1,3,2
1,3,1
1,3,-1
1,2,2
1,2,1
1,2,-1
1,1,3
1,1,1
1,1,-1
1,3,-2
1,2,-2
1,1,-2