## activity_list
category | major_activity | minor_activity | code | productivity
milestone | milestone | project_completion | M00009 | 1
milestone | milestone | project_start | M00001 | 1
milestone | milestone | elevator | M00007 | 1
가설공사 | fence | fence_line_marking | T10010 | 5
가설공사 | fence | fence_excavation | T10020 | 3
가설공사 | fence | fence_compaction | T10030 | 3
가설공사 | fence | fence_foundation | T10040 | 3
가설공사 | fence | fence_backfilling | T10050 | 3
가설공사 | fence | fence_steel | T10060 | 3
가설공사 | fence | fence_panel | T10070 | 5
가설공사 | fence | fence_wrapping | T10080 | 10
가설공사 | fence | fence_inspection | T10090 | 20
가설공사 | t_crane_installation | t_crane_installation_form | T30010 | 1
가설공사 | t_crane_installation | t_crane_installation_rebar | T30020 | 1
가설공사 | t_crane_installation | t_crane_installation_casting | T30030 | 1
가설공사 | t_crane_installation | t_crane_installation_curing1 | T30031 | 1
가설공사 | t_crane_installation | t_crane_installation_curing2 | T30032 | 1
가설공사 | t_crane_installation | t_crane_installation_curing3 | T30033 | 1
가설공사 | t_crane_installation | t_crane_installation_curing4 | T30034 | 1
가설공사 | t_crane_installation | t_crane_installation_curing5 | T30035 | 1
가설공사 | t_crane_installation | t_crane_installation_curing6 | T30036 | 1
가설공사 | t_crane_installation | t_crane_installation_installation | T30040 | 1
가설공사 | t_crane_installation | t_crane_installation_inspection | T30050 | 1
가설공사 | t_crane_dismantling | t_crane_dismantling_machine | T32010 | 1
가설공사 | t_crane_dismantling | t_crane_dismantling_dismantling | T32020 | 1
가설공사 | lift_installation | lift_installation_form | T35010 | 1
가설공사 | lift_installation | lift_installation_rebar | T35020 | 1
가설공사 | lift_installation | lift_installation_casting | T35030 | 1
가설공사 | lift_installation | lift_installation_curing1 | T35031 | 1
가설공사 | lift_installation | lift_installation_curing2 | T35032 | 1
가설공사 | lift_installation | lift_installation_curing3 | T35033 | 1
가설공사 | lift_installation | lift_installation_curing4 | T35034 | 1
가설공사 | lift_installation | lift_installation_curing5 | T35035 | 1
가설공사 | lift_installation | lift_installation_curing6 | T35036 | 1
가설공사 | lift_installation | lift_installation_installation | T35040 | 1
가설공사 | lift_installation | lift_installation_inspection | T35050 | 1
가설공사 | lift_dismantling | lift_dismantling_dismantling | T37010 | 1
흙막이공사 | CIP | CIP_line_marking | W10010 | 10
흙막이공사 | CIP | CIP_guidebeam | W10020 | 5
흙막이공사 | CIP | CIP_soil_compaction_for_machine | W10030 | 4
흙막이공사 | CIP | CIP_dig&rebar_1 | W10040 | 3
흙막이공사 | CIP | CIP_casting_1 | W10050 | 3
흙막이공사 | CIP | CIP_dig&rebar_2 | W10050 | 3
흙막이공사 | CIP | CIP_casting_2 | W10050 | 3
흙막이공사 | CIP | CIP_dig&rebar_3 | W10050 | 3
흙막이공사 | CIP | CIP_casting_3 | W10050 | 3
흙막이공사 | CIP | CIP_capbeam | W10060 | 10
흙막이공사 | CIP | CIP_capbeam_casting | W10070 | 10
흙막이공사 | waterblock | waterblock_line_marking | W11010 | 10
흙막이공사 | waterblock | waterblock_dig&piping | W11020 | 5
흙막이공사 | waterblock | waterblock_injection | W11030 | 5
흙막이공사 | waterblock | waterblock_cleaning | W11040 | 10
토공사 | excavation_test | excavation_test_planning | D10010 | 10
토공사 | excavation_test | excavation_test_excavation | D10020 | 1
토공사 | excavation_test | excavation_test_inspection | D10030 | 1
토공사 | excavation | excavation_0 | D11010 | 5
토공사 | retaining soil | retaining soil-forming | D12010 | 2
토공사 | retaining soil | retaining soil-removal | D12020 | 2
흙막이지지공사 | post_pile | post_pile_line_marking | R10010 | 10
흙막이지지공사 | post_pile | post_pile_dig&piling | R10020 | 3
흙막이지지공사 | strut_installation | strut_installation_wale | R11010 | 3
흙막이지지공사 | strut_installation | strut_installation_strut | R11020 | 3
흙막이지지공사 | strut_installation | strut_installation_inspection | R11030 | 3
흙막이지지공사 | strut_dismatling | strut_dismatling_check | R12010 | 5
흙막이지지공사 | strut_dismatling | strut_dismatling_remove | R12020 | 4
기초공사 | foundation | foundation_vapor_proof&lean_conc. | F20010 | 4
기초공사 | foundation | foundation_line_marking | F20020 | 4
기초공사 | foundation | foundation_re_bar | F20030 | 2
기초공사 | foundation | foundation_form | F20040 | 2
기초공사 | foundation | foundation_casting | F20050 | 3
기초공사 | foundation | foundation_curing | F20051 | 3
기초공사 | foundation | foundation_dismantling | F20060 | 3
기초공사 | foundation | foundation_backfill | F20070 | 5
골조공사 | rc_structure_vertical | rc_structure_vertical_line_marking | S10010 | 5
골조공사 | rc_structure_vertical | rc_structure_vertical_re_bar | S10020 | 3
골조공사 | rc_structure_vertical | rc_structure_vertical_embedding | S10030 | 3
골조공사 | rc_structure_vertical | rc_structure_vertical_form | S10040 | 3
골조공사 | rc_structure_vertical | rc_structure_vertical_inspection | S10050 | 5
골조공사 | rc_structure_vertical | rc_structure_vertical_casting | S10060 | 5
골조공사 | rc_structure_vertical | rc_structure_vertical_curing | S10061 | 5
골조공사 | rc_structure_vertical | rc_structure_vertical_dismantling | S10070 | 3
골조공사 | rc_structure_horizontal | rc_structure_horizontal_form | S11010 | 2
골조공사 | rc_structure_horizontal | rc_structure_horizontal_re_bar | S11020 | 3
골조공사 | rc_structure_horizontal | rc_structure_horizontal_embedding | S11030 | 3
골조공사 | rc_structure_horizontal | rc_structure_horizontal_inspection | S11040 | 5
골조공사 | rc_structure_horizontal | rc_structure_horizontal_casting | S11050 | 5
골조공사 | rc_structure_horizontal | rc_structure_horizontal_curing | S11051 | 5
골조공사 | rc_structure_horizontal | rc_structure_horizontal_dismantling | S11060 | 3
칸막이벽공사 | benchmark | benchmark_0 | A41510 | 2
칸막이벽공사 | masonry | masonry_material_delivery | A44510 | 2
칸막이벽공사 | masonry | masonry_1st | A44520 | 1
칸막이벽공사 | masonry | masonry_2nd | A44521 | 1
칸막이벽공사 | plastering | plastering_surface | A45010 | 2
칸막이벽공사 | plastering | plastering_1st | A45011 | 1
칸막이벽공사 | plastering | plastering_final | A45012 | 1
칸막이벽공사 | drywall | drywall_line_marking | A48510 | 2
칸막이벽공사 | drywall | drywall_stud | A48520 | 1
칸막이벽공사 | drywall | drywall_gypsum_board | A48530 | 1
마감공사 | ceiling_frame | ceiling_frame_hanger | A50510 | 1
마감공사 | ceiling_frame | ceiling_frame_frame | A50520 | 1
마감공사 | ceiling_board | ceiling_board_gypsum_board | A51010 | 1
마감공사 | grill_installation | grill_installation_0 | A52010 | 1
마감공사 | steel_door | steel_door_frame | A53010 | 1
마감공사 | steel_door | steel_door_door | A53020 | 1
마감공사 | finishing stone | finishing stone_0 | A55010 | 1
마감공사 | inside_wall_painting | inside_wall_painting_surface | A57510 | 2
마감공사 | inside_wall_painting | inside_wall_painting_1st | A57520 | 1
마감공사 | inside_wall_painting | inside_wall_painting_final | A57530 | 1
마감공사 | glazing | glazing_0 | A58010 | 1
마감공사 | ceiling_painting | ceiling_painting_surface | A59010 | 1
마감공사 | ceiling_painting | ceiling_painting_1st | A59020 | 1
마감공사 | ceiling_painting | ceiling_painting_final | A59030 | 1
마감공사 | ceiling_tex | ceiling_tex_0 | A59510 | 1
마감공사 | inside_floor_painting | inside_floor_painting_surface | A60510 | 1
마감공사 | inside_floor_painting | inside_floor_painting_1st | A60520 | 1
마감공사 | inside_floor_painting | inside_floor_painting_final | A60530 | 1
마감공사 | stair_floor_tile | stair_floor_tile_surface | A61010 | 1
마감공사 | stair_floor_tile | stair_floor_tile_tile | A61020 | 1
마감공사 | base_board | base_board_0 | A62510 | 2
마감공사 | miscellaneous | miscellaneous_0 | A64010 | 1
마감공사 | loover | loover_0 | A60020 | 1
마감공사 | furniture | furniture_0 | A67010 | 1
마감공사 | 마감공사 | 마감공사_0 | A41810 | 1
마감공사 | 마감공사 | 마감공사_level_marking | A43010 | 1
마감공사 | 마감공사 | 마감공사_casting | A43020 | 1
마감공사 | concreting | concreting_floor_plastering | A43021 | 2
마감공사 | concreting | concreting_curing | A43022 | 2
마감공사 | wall_insulation | wall_insulation_surface | A45510 | 2
마감공사 | wall_insulation | wall_insulation_insulation | A45520 | 1
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor_floor_coating | A61510 | 1
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor_line_marking | A61520 | 2
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor_frame | A61530 | 1
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor_tile | A61540 | 1
마감공사 | electric_appliances | electric_appliances_0 | A66510 | 1
마감공사 | ceiling_insulation | ceiling_insulation_surface | A46010 | 2
마감공사 | ceiling_insulation | ceiling_insulation_insulation | A46020 | 1
마감공사 | wood_door | wood_door_frame | A53510 | 2
마감공사 | wood_door | wood_door_door | A53520 | 2
마감공사 | floor_heating_finishing | floor_heating_finishing_surface | A54510 | 1
마감공사 | floor_heating_finishing | floor_heating_finishing_mortar_1st | A54520 | 2
마감공사 | floor_heating_finishing | floor_heating_finishing_mortar_final | A54530 | 2
마감공사 | inside_floor_woodtile | inside_floor_woodtile_surface | A62010 | 1
마감공사 | inside_floor_woodtile | inside_floor_woodtile_line_marking | A62020 | 2
마감공사 | inside_floor_woodtile | inside_floor_woodtile_frame | A62030 | 1
마감공사 | inside_floor_woodtile | inside_floor_woodtile_woodtile | A62040 | 1
마감공사 | inside_floor_woodtile | inside_floor_woodtile_finishing | A62050 | 1
마감공사 | inside_wall_paper | inside_wall_paper_ceiling | A63010 | 1
마감공사 | inside_wall_paper | inside_wall_paper_wall | A63020 | 1
마감공사 | inside_waterproofing | inside_waterproofing_surface | A49510 | 1
마감공사 | inside_waterproofing | inside_waterproofing_waterproofing | A49520 | 1
마감공사 | inside_waterproofing | inside_waterproofing_test | A49530 | 1
마감공사 | inside_waterproofing | inside_waterproofing_protection | A49540 | 1
마감공사 | inside_floor_tile | inside_floor_tile_surface | A56510 | 1
마감공사 | inside_floor_tile | inside_floor_tile_tile | A56520 | 1
마감공사 | inside_wall_tile | inside_wall_tile_0 | A57010 | 1
마감공사 | ceiling_tile | ceiling_tile_0 | A60010 | 1
마감공사 | washbasin_installation | washbasin_installation_frame | A60710 | 1
마감공사 | washbasin_installation | washbasin_installation_basin | A60720 | 1
마감공사 | toilet_accessaries_nstallation | toilet_accessaries_nstallation_0 | A66010 | 1
외장공사 | al_window | al_window_frame | A52510 | 1
외장공사 | al_window | al_window_insulation_filling | A52520 | 1
외장공사 | al_window | al_window_window | A52530 | 1
외장공사 | window_door | window_door_surface | A54010 | 1
외장공사 | window_door | window_door_hardware | A54020 | 1
외장공사 | window_door | window_door_door | A54030 | 1
외장공사 | outside_wall_finishing | outside_wall_finishing_line_marking | A47510 | 2
외장공사 | outside_wall_finishing | outside_wall_finishing_frame | A47520 | 1
외장공사 | outside_wall_finishing | outside_wall_finishing_panel | A47530 | 1
외장공사 | pvc_window | pvc_window_frame | A51510 | 1
외장공사 | pvc_window | pvc_window_insulation_filling | A51520 | 1
외장공사 | pvc_window | pvc_window_window | A51530 | 1