## grid_activity_list
x | y | z | major_activity | code | minor_activity
1 | 1 | 1 | fence | T10010 | fence_line_marking
1 | 1 | 1 | fence | T10020 | fence_excavation
1 | 1 | 1 | fence | T10030 | fence_compaction
1 | 1 | 1 | fence | T10040 | fence_foundation
1 | 1 | 1 | fence | T10050 | fence_backfilling
1 | 1 | 1 | fence | T10060 | fence_steel
1 | 1 | 1 | fence | T10070 | fence_panel
1 | 1 | 1 | fence | T10080 | fence_wrapping
1 | 1 | 1 | fence | T10090 | fence_inspection
1 | 2 | 1 | fence | T10010 | fence_line_marking
1 | 2 | 1 | fence | T10020 | fence_excavation
1 | 2 | 1 | fence | T10030 | fence_compaction
1 | 2 | 1 | fence | T10040 | fence_foundation
1 | 2 | 1 | fence | T10050 | fence_backfilling
1 | 2 | 1 | fence | T10060 | fence_steel
1 | 2 | 1 | fence | T10070 | fence_panel
1 | 2 | 1 | fence | T10080 | fence_wrapping
1 | 2 | 1 | fence | T10090 | fence_inspection
1 | 3 | 1 | fence | T10010 | fence_line_marking
1 | 3 | 1 | fence | T10020 | fence_excavation
1 | 3 | 1 | fence | T10030 | fence_compaction
1 | 3 | 1 | fence | T10040 | fence_foundation
1 | 3 | 1 | fence | T10050 | fence_backfilling
1 | 3 | 1 | fence | T10060 | fence_steel
1 | 3 | 1 | fence | T10070 | fence_panel
1 | 3 | 1 | fence | T10080 | fence_wrapping
1 | 3 | 1 | fence | T10090 | fence_inspection
3 | 1 | 1 | fence | T10010 | fence_line_marking
3 | 1 | 1 | fence | T10020 | fence_excavation
3 | 1 | 1 | fence | T10030 | fence_compaction
3 | 1 | 1 | fence | T10040 | fence_foundation
3 | 1 | 1 | fence | T10050 | fence_backfilling
3 | 1 | 1 | fence | T10060 | fence_steel
3 | 1 | 1 | fence | T10070 | fence_panel
3 | 1 | 1 | fence | T10080 | fence_wrapping
3 | 1 | 1 | fence | T10090 | fence_inspection
3 | 2 | 1 | fence | T10010 | fence_line_marking
3 | 2 | 1 | fence | T10020 | fence_excavation
3 | 2 | 1 | fence | T10030 | fence_compaction
3 | 2 | 1 | fence | T10040 | fence_foundation
3 | 2 | 1 | fence | T10050 | fence_backfilling
3 | 2 | 1 | fence | T10060 | fence_steel
3 | 2 | 1 | fence | T10070 | fence_panel
3 | 2 | 1 | fence | T10080 | fence_wrapping
3 | 2 | 1 | fence | T10090 | fence_inspection
3 | 3 | 1 | fence | T10010 | fence_line_marking
3 | 3 | 1 | fence | T10020 | fence_excavation
3 | 3 | 1 | fence | T10030 | fence_compaction
3 | 3 | 1 | fence | T10040 | fence_foundation
3 | 3 | 1 | fence | T10050 | fence_backfilling
3 | 3 | 1 | fence | T10060 | fence_steel
3 | 3 | 1 | fence | T10070 | fence_panel
3 | 3 | 1 | fence | T10080 | fence_wrapping
3 | 3 | 1 | fence | T10090 | fence_inspection
2 | 1 | 1 | fence | T10010 | fence_line_marking
2 | 1 | 1 | fence | T10020 | fence_excavation
2 | 1 | 1 | fence | T10030 | fence_compaction
2 | 1 | 1 | fence | T10040 | fence_foundation
2 | 1 | 1 | fence | T10050 | fence_backfilling
2 | 1 | 1 | fence | T10060 | fence_steel
2 | 1 | 1 | fence | T10070 | fence_panel
2 | 1 | 1 | fence | T10080 | fence_wrapping
2 | 1 | 1 | fence | T10090 | fence_inspection
2 | 3 | 1 | fence | T10010 | fence_line_marking
2 | 3 | 1 | fence | T10020 | fence_excavation
2 | 3 | 1 | fence | T10030 | fence_compaction
2 | 3 | 1 | fence | T10040 | fence_foundation
2 | 3 | 1 | fence | T10050 | fence_backfilling
2 | 3 | 1 | fence | T10060 | fence_steel
2 | 3 | 1 | fence | T10070 | fence_panel
2 | 3 | 1 | fence | T10080 | fence_wrapping
2 | 3 | 1 | fence | T10090 | fence_inspection
1 | 2 | 1 | t_crane_installation | T30010 | t_crane_installation_form
1 | 2 | 1 | t_crane_installation | T30020 | t_crane_installation_rebar
1 | 2 | 1 | t_crane_installation | T30030 | t_crane_installation_casting
1 | 2 | 1 | t_crane_installation | T30031 | t_crane_installation_curing1
1 | 2 | 1 | t_crane_installation | T30032 | t_crane_installation_curing2
1 | 2 | 1 | t_crane_installation | T30033 | t_crane_installation_curing3
1 | 2 | 1 | t_crane_installation | T30034 | t_crane_installation_curing4
1 | 2 | 1 | t_crane_installation | T30035 | t_crane_installation_curing5
1 | 2 | 1 | t_crane_installation | T30036 | t_crane_installation_curing6
1 | 2 | 1 | t_crane_installation | T30040 | t_crane_installation_installation
1 | 2 | 1 | t_crane_installation | T30050 | t_crane_installation_inspection
1 | 2 | 1 | t_crane_dismantling | T32010 | t_crane_dismantling_machine
1 | 2 | 1 | t_crane_dismantling | T32020 | t_crane_dismantling_dismantling
1 | 3 | 1 | lift_installation | T35010 | lift_installation_form
1 | 3 | 1 | lift_installation | T35020 | lift_installation_rebar
1 | 3 | 1 | lift_installation | T35030 | lift_installation_casting
1 | 3 | 1 | lift_installation | T35031 | lift_installation_curing1
1 | 3 | 1 | lift_installation | T35032 | lift_installation_curing2
1 | 3 | 1 | lift_installation | T35033 | lift_installation_curing3
1 | 3 | 1 | lift_installation | T35034 | lift_installation_curing4
1 | 3 | 1 | lift_installation | T35035 | lift_installation_curing5
1 | 3 | 1 | lift_installation | T35036 | lift_installation_curing6
1 | 3 | 1 | lift_installation | T35040 | lift_installation_installation
1 | 3 | 1 | lift_installation | T35050 | lift_installation_inspection
1 | 3 | 1 | lift_dismantling

## grid_wp_list
x | y | z | wp_code | wp_name_en
0 | 0 | 0 | M000 | milestone
1 | 1 | 1 | T100 | fence
1 | 2 | 1 | T100 | fence
1 | 3 | 1 | T100 | fence
3 | 1 | 1 | T100 | fence
3 | 2 | 1 | T100 | fence
3 | 3 | 1 | T100 | fence
2 | 1 | 1 | T100 | fence
2 | 3 | 1 | T100 | fence
1 | 2 | 1 | T300 | t-crane_installation
1 | 2 | 1 | T320 | t-crane_dismantling
1 | 3 | 1 | T350 | lift_installation
1 | 3 | 1 | T370 | lift_dismantling
1 | 1 | 1 | W100 | CIP
1 | 1 | 1 | W110 | waterblock
2 | 1 | 1 | W100 | CIP
2 | 1 | 1 | W110 | waterblock
3 | 1 | 1 | W100 | CIP
3 | 1 | 1 | W110 | waterblock
1 | 3 | 1 | W100 | CIP
1 | 3 | 1 | W110 | waterblock
2 | 3 | 1 | W100 | CIP
2 | 3 | 1 | W110 | waterblock
3 | 3 | 1 | W100 | CIP
3 | 3 | 1 | W110 | waterblock
1 | 2 | 1 | W100 | CIP
1 | 2 | 1 | W110 | waterblock
3 | 2 | 1 | W100 | CIP
3 | 2 | 1 | W110 | waterblock
3 | 3 | 1 | D100 | excavation_test
1 | 1 | 1 | D110 | excavation
2 | 1 | 1 | D110 | excavation
3 | 1 | 1 | D110 | excavation
1 | 2 | 1 | D110 | excavation
2 | 2 | 1 | D110 | excavation
3 | 2 | 1 | D110 | excavation
1 | 3 | 1 | D110 | excavation
2 | 3 | 1 | D110 | excavation
3 | 3 | 1 | D110 | excavation
1 | 1 | -1 | D110 | excavation
2 | 1 | -1 | D110 | excavation
3 | 1 | -1 | D110 | excavation
1 | 2 | -1 | D110 | excavation
2 | 2 | -1 | D110 | excavation
3 | 2 | -1 | D110 | excavation
1 | 3 | -1 | D110 | excavation
2 | 3 | -1 | D110 | excavation
3 | 3 | -1 | D110 | excavation
1 | 1 | -2 | D110 | excavation
2 | 1 | -2 | D110 | excavation
3 | 1 | -2 | D110 | excavation
1 | 2 | -2 | D110 | excavation
2 | 2 | -2 | D110 | excavation
3 | 2 | -2 | D110 | excavation
1 | 3 | -2 | D110 | excavation
2 | 3 | -2 | D110 | excavation
3 | 3 | -2 | D110 | excavation
1 | 1 | 1 | R100 | post_pile
1 | 1 | 1 | R110 | strut_installation
1 | 1 | 1 | R120 | strut_dismatling
2 | 1 | 1 | R100 | post_pile
2 | 1 | 1 | R110 | strut_installation
2 | 1 | 1 | R120 | strut_dismatling
3 | 1 | 1 | R100 | post_pile
3 | 1 | 1 | R110 | strut_installation
3 | 1 | 1 | R120 | strut_dismatling
1 | 3 | 1 | R100 | post_pile
1 | 3 | 1 | R110 | strut_installation
1 | 3 | 1 | R120 | strut_dismatling
2 | 3 | 1 | R100 | post_pile
2 | 3 | 1 | R110 | strut_installation
2 | 3 | 1 | R120 | strut_dismatling
3 | 3 | 1 | R100 | post_pile
3 | 3 | 1 | R110 | strut_installation
3 | 3 | 1 | R120 | strut_dismatling
1 | 1 | -2 | F200 | foundation
2 | 1 | -2 | F200 | foundation
3 | 1 | -2 | F200 | foundation
1 | 2 | -2 | F200 | foundation
2 | 2 | -2 | F200 | foundation
3 | 2 | -2 | F200 | foundation
1 | 3 | -2 | F200 | foundation
2 | 3 | -2 | F200 | foundation
3 | 3 | -2 | F200 | foundation
2 | 1 | -1 | S100 | rc_structure_vertical
2 | 1 | -1 | S110 | rc_structure_horizontal
2 | 2 | -1 | S100 | rc_structure_vertical
2 | 2 | -1 | S110 | rc_structure_horizontal
2 | 3 | -1 | S100 | rc_structure_vertical
2 | 3 | -1 | S110 | rc_structure_horizontal
3 | 1 | -1 | S100 | rc_structure_vertical
3 | 1 | -1 | S110 | rc_structure_horizontal
3 | 2 | -1 | S100 | rc_structure_vertical
3 | 2 | -1 | S110 | rc_structure_horizontal
3 | 3 | -1 | S100 | rc_structure_vertical
3 | 3 | -1 | S110 | rc_structure_horizontal
2 | 1 | 1 | S100 | rc_structure_vertical
2 | 1 | 1 | S110 | rc_structure_horizontal
2 | 2 | 1 | S100 | rc_structure_vertical
2 | 2 | 1 | S110 | rc_structure_horizontal
2 | 3 | 1 | S100 | rc_structure_vertical
2 | 3 | 1 | S110 | rc_structure_horizontal
3 | 1 | 1 | S100 | rc_structure_vertical
3 | 1 | 1 | S110 | rc_structure_horizontal
3 | 2 | 1 | S100 | rc_structure_vertical
3 | 2 | 1 | S110 | rc_structure_horizontal
3 | 3 | 1 | S100 | rc_structure_vertical
3 | 3 | 1 | S110 | rc_structure_horizontal
2 | 1 | 2 | S100 | rc_structure_vertical
2 | 1 | 2 | S110 | rc_structure_horizontal
2 | 2 | 2 | S100 | rc_structure_vertical
2 | 2 | 2 | S110 | rc_structure_horizontal
2 | 3 | 2 | S100 | rc_structure_vertical
2 | 3 | 2 | S110 | rc_structure_horizontal
3 | 1 | 2 | S100 | rc_structure_vertical
3 | 1 | 2 | S110 | rc_structure_horizontal
3 | 2 | 2 | S100 | rc_structure_vertical
3 | 2 | 2 | S110 | rc_structure_horizontal
3 | 3 | 2 | S100 | rc_structure_vertical
3 | 3 | 2 | S110 | rc_structure_horizontal