## activity_list
category | major_activity | minor_activity | code | productivity | pre_dist
milestone | milestone | project_completion | M00009 | 1 | 0
milestone | milestone | project_start | M00001 | 1 | 2
milestone | milestone | elevator | M00007 | 1 | 2
가설공사 | fence | fence-line_marking | T10010 | 5 | 0
가설공사 | fence | fence-excavation | T10020 | 3 | 1
가설공사 | fence | fence-compaction | T10030 | 3 | 2
가설공사 | fence | fence-foundation | T10040 | 3 | 2
가설공사 | fence | fence-backfilling | T10050 | 3 | 1
가설공사 | fence | fence-steel | T10060 | 3 | 1
가설공사 | fence | fence-panel | T10070 | 5 | 0
가설공사 | fence | fence-wrapping | T10080 | 10 | 2
가설공사 | fence | fence-inspection | T10090 | 20 | 1
가설공사 | t-crane_installation | t-crane_installation-form | T30010 | 1 | 2
가설공사 | t-crane_installation | t-crane_installation-rebar | T30020 | 1 | 0
가설공사 | t-crane_installation | t-crane_installation-casting | T30030 | 1 | 1
가설공사 | t-crane_installation | t-crane_installation-curing1 | T30031 | 1 | 2
가설공사 | t-crane_installation | t-crane_installation-curing2 | T30032 | 1 | 0
가설공사 | t-crane_installation | t-crane_installation-curing3 | T30033 | 1 | 0
가설공사 | t-crane_installation | t-crane_installation-curing4 | T30034 | 1 | 2
가설공사 | t-crane_installation | t-crane_installation-curing5 | T30035 | 1 | 2
가설공사 | t-crane_installation | t-crane_installation-curing6 | T30036 | 1 | 0
가설공사 | t-crane_installation | t-crane_installation-installation | T30040 | 1 | 1
가설공사 | t-crane_installation | t-crane_installation-inspection | T30050 | 1 | 2
가설공사 | t-crane_dismantling | t-crane_dismantling-machine | T32010 | 1 | 1
가설공사 | t-crane_dismantling | t-crane_dismantling-dismantling | T32020 | 1 | 2
가설공사 | lift_installation | lift_installation-form | T35010 | 1 | 0
가설공사 | lift_installation | lift_installation-rebar | T35020 | 1 | 0
가설공사 | lift_installation | lift_installation-casting | T35030 | 1 | 0
가설공사 | lift_installation | lift_installation-curing1 | T35031 | 1 | 2
가설공사 | lift_installation | lift_installation-curing2 | T35032 | 1 | 0
가설공사 | lift_installation | lift_installation-curing3 | T35033 | 1 | 1
가설공사 | lift_installation | lift_installation-curing4 | T35034 | 1 | 2
가설공사 | lift_installation | lift_installation-curing5 | T35035 | 1 | 0
가설공사 | lift_installation | lift_installation-curing6 | T35036 | 1 | 2
가설공사 | lift_installation | lift_installation-installation | T35040 | 1 | 1
가설공사 | lift_installation | lift_installation-inspection | T35050 | 1 | 2
가설공사 | lift_dismantling | lift_dismantling-dismantling | T37010 | 1 | 1
흙막이공사 | CIP | CIP-line_marking | W10010 | 3 | 1
흙막이공사 | CIP | CIP-guidebeam | W10020 | 2 | 0
흙막이공사 | CIP | CIP-soil_compaction_for_machine | W10030 | 2 | 0
흙막이공사 | CIP | CIP-dig&rebar_1 | W10040 | 1 | 0
흙막이공사 | CIP | CIP-casting_1 | W10041 | 1 | 2
흙막이공사 | CIP | CIP-dig&rebar_2 | W10050 | 1 | 2
흙막이공사 | CIP | CIP-casting_2 | W10051 | 1 | 0
흙막이공사 | CIP | CIP-dig&rebar_3 | W10060 | 1 | 1
흙막이공사 | CIP | CIP-casting_3 | W10061 | 1 | 1
흙막이공사 | CIP | CIP-capbeam | W10070 | 2 | 1
흙막이공사 | CIP | CIP-capbeam_casting | W10080 | 2 | 1
흙막이공사 | waterblock | waterblock-line_marking | W11010 | 10 | 2
흙막이공사 | waterblock | waterblock-dig&piping | W11020 | 5 | 0
흙막이공사 | waterblock | waterblock-injection | W11030 | 5 | 2
흙막이공사 | waterblock | waterblock-cleaning | W11040 | 10 | 0
토공사 | excavation_test | excavation_test-planning | D10010 | 10 | 1
토공사 | excavation_test | excavation_test-excavation | D10020 | 1 | 0
토공사 | excavation_test | excavation_test-inspection | D10030 | 1 | 1
토공사 | excavation | excavation-0 | D11010 | 5 | 2
흙막이지지공사 | post_pile | post_pile-line_marking | R10010 | 10 | 2
흙막이지지공사 | post_pile | post_pile-dig&piling | R10020 | 3 | 2
흙막이지지공사 | strut_installation | strut_installation-wale | R11010 | 3 | 0
흙막이지지공사 | strut_installation | strut_installation-strut | R11020 | 3 | 1
흙막이지지공사 | strut_installation | strut_installation-inspection | R11030 | 3 | 0
흙막이지지공사 | strut_dismatling | strut_dismatling-check | R12010 | 5 | 0
흙막이지지공사 | strut_dismatling | strut_dismatling-remove | R12020 | 4 | 1
기초공사 | foundation | foundation-vapor_proof&lean_conc. | F20010 | 4 | 1
기초공사 | foundation | foundation-line_marking | F20020 | 4 | 1
기초공사 | foundation | foundation-re-bar | F20030 | 2 | 2
기초공사 | foundation | foundation-form | F20040 | 2 | 2
기초공사 | foundation | foundation-casting | F20050 | 3 | 2
기초공사 | foundation | foundation-curing | F20051 | 3 | 0
기초공사 | foundation | foundation-dismantling | F20060 | 3 | 1
기초공사 | foundation | foundation-backfill | F20070 | 5 | 2
골조공사 | rc_structure_vertical | rc_structure_vertical-line_marking | S10010 | 5 | 0
골조공사 | rc_structure_vertical | rc_structure_vertical-re-bar | S10020 | 3 | 1
골조공사 | rc_structure_vertical | rc_structure_vertical-embedding | S10030 | 3 | 0
골조공사 | rc_structure_vertical | rc_structure_vertical-form | S10040 | 3 | 2
골조공사 | rc_structure_vertical | rc_structure_vertical-inspection | S10050 | 5 | 0
골조공사 | rc_structure_vertical | rc_structure_vertical-casting | S10060 | 5 | 0
골조공사 | rc_structure_vertical | rc_structure_vertical-curing | S10061 | 5 | 2
골조공사 | rc_structure_vertical | rc_structure_vertical-dismantling | S10070 | 3 | 0
골조공사 | rc_structure_horizontal | rc_structure_horizontal-form | S11010 | 2 | 0
골조공사 | rc_structure_horizontal | rc_structure_horizontal-re-bar | S11020 | 3 | 0
골조공사 | rc_structure_horizontal | rc_structure_horizontal-embedding | S11030 | 3 | 1
골조공사 | rc_structure_horizontal | rc_structure_horizontal-inspection | S11040 | 5 | 1
골조공사 | rc_structure_horizontal | rc_structure_horizontal-casting | S11050 | 5 | 0
골조공사 | rc_structure_horizontal | rc_structure_horizontal-curing | S11051 | 5 | 1
골조공사 | rc_structure_horizontal | rc_structure_horizontal-dismantling | S11060 | 3 | 0
칸막이벽공사 | benchmark | benchmark-0 | A41510 | 2 | 2
칸막이벽공사 | masonry | masonry-material_delivery | A44510 | 2 | 0
칸막이벽공사 | masonry | masonry-1st | A44520 | 1 | 1
칸막이벽공사 | masonry | masonry-2nd | A44521 | 1 | 1
칸막이벽공사 | plastering | plastering-surface | A45010 | 2 | 0
칸막이벽공사 | plastering | plastering-1st | A45011 | 1 | 0
칸막이벽공사 | plastering | plastering-final | A45012 | 1 | 1
칸막이벽공사 | drywall | drywall-line_marking | A48510 | 2 | 2
칸막이벽공사 | drywall | drywall-stud | A48520 | 1 | 0
칸막이벽공사 | drywall | drywall-gypsum_board | A48530 | 1 | 1
마감공사 | ceiling_frame | ceiling_frame-hanger | A50510 | 1 | 0
마감공사 | ceiling_frame | ceiling_frame-frame | A50520 | 1 | 1
마감공사 | ceiling_board | ceiling_board-gypsum_board | A51010 | 1 | 2
마감공사 | grill_installation | grill_installation-0 | A52010 | 1 | 0
마감공사 | steel_door | steel_door-frame | A53010 | 1 | 0
마감공사 | steel_door | steel_door-door | A53020 | 1 | 0
마감공사 | finishing stone | finishing stone-0 | A55010 | 1 | 2
마감공사 | inside_wall_painting | inside_wall_painting-surface | A57510 | 2 | 1
마감공사 | inside_wall_painting | inside_wall_painting-1st | A57520 | 1 | 1
마감공사 | inside_wall_painting | inside_wall_painting-final | A57530 | 1 | 2
마감공사 | glazing | glazing-0 | A58010 | 1 | 0
마감공사 | ceiling_painting | ceiling_painting-surface | A59010 | 1 | 1
마감공사 | ceiling_painting | ceiling_painting-1st | A59020 | 1 | 2
마감공사 | ceiling_painting | ceiling_painting-final | A59030 | 1 | 0
마감공사 | ceiling_tex | ceiling_tex-0 | A59510 | 1 | 0
마감공사 | inside_floor_painting | inside_floor_painting-surface | A60510 | 1 | 2
마감공사 | inside_floor_painting | inside_floor_painting-1st | A60520 | 1 | 1
마감공사 | inside_floor_painting | inside_floor_painting-final | A60530 | 1 | 1
마감공사 | stair_floor_tile | stair_floor_tile-surface | A61010 | 1 | 2
마감공사 | stair_floor_tile | stair_floor_tile-tile | A61020 | 1 | 0
마감공사 | base_board | base_board-0 | A62510 | 2 | 0
마감공사 | miscellaneous | miscellaneous-0 | A64010 | 1 | 2
마감공사 | loover | loover-0 | A60020 | 1 | 2
마감공사 | furniture | furniture-0 | A67010 | 1 | 2
마감공사 | floor_tile | floor_tile-0 | A41810 | 1 | 0
마감공사 | concreting | concreting-level_marking | A43010 | 1 | 0
마감공사 | concreting | concreting-casting | A43020 | 1 | 2
마감공사 | concreting | concreting-floor_plastering | A43021 | 2 | 1
마감공사 | concreting | concreting-curing | A43022 | 2 | 0
마감공사 | wall_insulation | wall_insulation-surface | A45510 | 2 | 2
마감공사 | wall_insulation | wall_insulation-insulation | A45520 | 1 | 2
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor-floor_coating | A61510 | 1 | 2
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor-line_marking | A61520 | 2 | 2
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor-frame | A61530 | 1 | 0
마감공사 | inside_floor_accessfloor | inside_floor_accessfloor-tile | A61540 | 1 | 2
마감공사 | electric_appliances | electric_appliances-0 | A66510 | 1 | 2
마감공사 | ceiling_insulation | ceiling_insulation-surface | A46010 | 2 | 2
마감공사 | ceiling_insulation | ceiling_insulation-insulation | A46020 | 1 | 2
마감공사 | wood_door | wood_door-frame | A53510 | 2 | 1
마감공사 | wood_door | wood_door-door | A53520 | 2 | 1
마감공사 | floor_heating_finishing | floor_heating_finishing-surface | A54510 | 1 | 0
마감공사 | floor_heating_finishing | floor_heating_finishing-mortar_1st | A54520 | 2 | 1
마감공사 | floor_heating_finishing | floor_heating_finishing-mortar_final | A54530 | 2 | 2
마감공사 | inside_floor_woodtile | inside_floor_woodtile-surface | A62010 | 1 | 0
마감공사 | inside_floor_woodtile | inside_floor_woodtile-line_marking | A62020 | 2 | 2
마감공사 | inside_floor_woodtile | inside_floor_woodtile-frame | A62030 | 1 | 0
마감공사 | inside_floor_woodtile | inside_floor_woodtile-woodtile | A62040 | 1 | 2
마감공사 | inside_floor_woodtile | inside_floor_woodtile-finishing | A62050 | 1 | 2
마감공사 | inside_wall_paper | inside_wall_paper-ceiling | A63010 | 1 | 0
마감공사 | inside_wall_paper | inside_wall_paper-wall | A63020 | 1 | 2
마감공사 | inside_waterproofing | inside_waterproofing-surface | A49510 | 1 | 1
마감공사 | inside_waterproofing | inside_waterproofing-waterproofing | A49520 | 1 | 2
마감공사 | inside_waterproofing | inside_waterproofing-test | A49530 | 1 | 2
마감공사 | inside_waterproofing | inside_waterproofing-protection | A49540 | 1 | 1
마감공사 | inside_floor_tile | inside_floor_tile-surface | A56510 | 1 | 1
마감공사 | inside_floor_tile | inside_floor_tile-tile | A56520 | 1 | 0
마감공사 | inside_wall_tile | inside_wall_tile-0 | A57010 | 1 | 0
마감공사 | ceiling_tile | ceiling_tile-0 | A60010 | 1 | 2
마감공사 | washbasin_installation | washbasin_installation-frame | A60710 | 1 | 0
마감공사 | washbasin_installation | washbasin_installation-basin | A60720 | 1 | 1
마감공사 | toilet_accessaries_nstallation | toilet_accessaries_nstallation-0 | A66010 | 1 | 2
외장공사 | al_window | al_window-frame | A52510 | 1 | 1
외장공사 | al_window | al_window-insulation_filling | A52520 | 1 | 0
외장공사 | al_window | al_window-window | A52530 | 1 | 1
외장공사 | window_door | window_door-surface | A54010 | 1 | 2
외장공사 | window_door | window_door-hardware | A54020 | 1 | 1
외장공사 | window_door | window_door-door | A54030 | 1 | 0
외장공사 | outside_wall_finishing | outside_wall_finishing-line_marking | A47510 | 2 | 2
외장공사 | outside_wall_finishing | outside_wall_finishing-frame | A47520 | 1 | 0
외장공사 | outside_wall_finishing | outside_wall_finishing-panel | A47530 | 1 | 2
외장공사 | pvc_window | pvc_window-frame | A51510 | 1 | 0
외장공사 | pvc_window | pvc_window-insulation_filling | A51520 | 1 | 2
외장공사 | pvc_window | pvc_window-window | A51530 | 1 | 1
토공사 | retaining soil | retaining soil-forming | D12010 | 2 | 2
토공사 | retaining soil | retaining soil-removal | D12020 | 2 | 1